## PM.com End lines
| Task Name | Project ID | Project Title | WBS | Project Name | Project Status | Customer | Project Manager | Planned Start Date | Planned Finish Date | Person | Actual Start Date | Actual Finish Date | Actual Cost | Milestone | Complete | Tags | Current Project Budget | Budgeted Engineering Hours | TRP Chair(s) | Current IDOT Budget | Research Conducted By | Original IDOT Budget | Original Project Budget | PI | TAG | Actual Engineering Hours
0 | R27-001 Research Project Ends | R27-001 | Char. IL Aggregates Subgrade/Subbase | 3 | R27-001: Char. IL Aggregates Subgrade/Subbase | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-06-30 | 2009-06-30 | ICT Project Management | 2009-12-01 | 2009-12-01 | 0 | TRUE | TRUE
1 | R27-002 Research Project Ends | R27-002 | Lighting Glare | 3 | R27-002: Lighting Glare | FY06-FY08 IGA |  | Nick York | 2007-12-31 | 2007-12-31 | ICT Project Management [0.00 %] | 2008-01-01 | 2008-01-01 | 0 | TRUE | TRUE
2 | R27-003 Research Project Ends | R27-003 | Ultra-Thin Whitetopping | 3 | R27-003: Ultra-Thin Whitetopping | FY06-FY08 IGA |  | Nick York | 2008-03-31 | 2008-03-31 | ICT Project Management [0.00 %] | 2008-06-01 | 2008-06-01 | 0 | TRUE | TRUE
3 | R27-004 Research Project Ends | R27-004 | Radiation Detection | 2 | R27-004: Radiation Detection | FY06-FY08 IGA |  | Nick York | 2007-06-30 | 2007-06-30 | ICT Project Management [0.00 %] | 2007-06-30 | 2007-06-30 | 0 | TRUE | TRUE
4 | R27-005 Research Project Ends | R27-005 | Bus-Only Shoulder Riding | 3 | R27-005: Bus-Only Shoulder Riding | FY09-FY11 IGA |  | Nick York | 2009-01-31 | 2009-01-31 | ICT Project Management [0.00 %] | 2010-08-01 | 2010-08-01 | 0 | TRUE | TRUE
5 | R27-006 Research Project Ends | R27-006 | Illinois StreamStats | 3 | R27-006: Illinois StreamStats | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2008-06-30 | 2008-06-30 | 0 | TRUE | TRUE
6 | R27-007 Research Project Ends | R27-007 | Carbon Monoxide Screen | 2 | R27-007: Carbon Monoxide Screen | FY06-FY08 IGA |  | Nick York | 2007-08-31 | 2007-08-31 | ICT Project Management [0.00 %] | 2008-07-01 | 2008-07-01 | 0 | TRUE | TRUE
7 | R27-008 Research Project Ends | R27-008 | Hot Mix Asphalt | 2 | R27-008: Hot Mix Asphalt | FY06-FY08 IGA |  | Nick York | 2007-06-30 | 2007-06-30 | ICT Project Management [0.00 %] | 2007-08-01 | 2007-08-01 | 0 | TRUE | TRUE
8 | R27-009 Research Project Ends | R27-009 | Kishwaukee Bridge Monitoring | 2 | R27-009: Kishwaukee Bridge Monitoring | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 |  | 2010-01-01 | 2010-01-01 | 0 | TRUE | TRUE
9 | R27-010 Research Project Ends | R27-010 | Mobile Source Air Toxics | 2 | R27-010: Mobile Source Air Toxics | FY06-FY08 IGA |  | Nick York | 2007-02-28 | 2007-02-28 | ICT Project Management [0.00 %] | 2006-12-01 | 2006-12-01 | 0 | TRUE | TRUE
10 | R27-011 Research Project Ends | R27-011 | Residual Asphalt Binder in RAP | 2 | R27-011: Residual Asphalt Binder in RAP | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2009-01-01 | 2009-01-01 | 0 | TRUE | TRUE
11 | R27-012 Research Project Ends | R27-012 | CI & FDRwAP | 2 | R27-012: CI & FDRwAP | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-08-31 | 2008-08-31 | ICT Project Management | 2009-03-01 | 2009-03-01 | 0 | TRUE | TRUE
12 | R27-013 Research Project Ends | R27-013 | Calculation/Prediction Models | 2 | R27-013: Calculation/Prediction Models | FY06-FY08 IGA |  | Nick York | 2007-08-31 | 2007-08-31 | ICT Project Management [0.00 %] | 2007-08-01 | 2007-08-01 | 0 | TRUE | TRUE
13 | R27-014 Research Project Ends | R27-014 | Commercial Vehicle Information Systems | 2 | R27-014: Commercial Vehicle Information Systems | FY06-FY08 IGA |  | Nick York | 2007-03-31 | 2007-03-31 | ICT Project Management [0.00 %] | 2007-03-01 | 2007-03-01 | 0 | TRUE | TRUE
14 | R27-015 Research Project Ends | R27-015 | Regional Warehouse Trip Production | 3 | R27-015: Regional Warehouse Trip Production | FY09-FY11 IGA |  | Nick York | 2008-07-31 | 2008-07-31 | ICT Project Management [0.00 %] | 2008-10-01 | 2008-10-01 | 0 | TRUE | TRUE
15 | R27-016 Research Project Ends | R27-016 | Truck Parking Facilities | 2 | R27-016: Truck Parking Facilities | FY06-FY08 IGA |  | Nick York | 2008-03-31 | 2008-03-31 | ICT Project Management [0.00 %] | 2008-07-01 | 2008-07-01 | 0 | TRUE | TRUE
16 | R27-017 Research Project Ends | R27-017 | Traffic Strategies Targeting Elderly People | 3 | R27-017: Traffic Strategies Targeting Elderly People | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-11-30 | 2008-11-30 | ICT Project Management | 2009-02-01 | 2009-02-01 | 0 | TRUE | TRUE
17 | R27-018 Research Project Ends | R27-018 | Crash Data Analysis | 6 | R27-018: Crash Data Analysis | FY09-FY11 IGA |  | Nick York | 2008-12-31 | 2008-12-31 | ICT Project Management [0.00 %] | 2009-09-01 | 2009-09-01 | 0 | TRUE | TRUE
18 | R27-019 Research Project Ends | R27-019 | Pier Scour Prediction | 3 | R27-019: Pier Scour Prediction | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-06-30 | 2010-06-30 | ICT Project Management | 2009-08-01 | 2009-08-01 | 0 | TRUE | TRUE
19 | R27-020 Research Project Ends | R27-020 | Safety Performance Functions | 2 | R27-020: Safety Performance Functions | FY09-FY11 IGA |  | Nick York | 2008-12-31 | 2008-12-31 | ICT Project Management [0.00 %] | 2010-03-01 | 2010-03-01 | 0 | TRUE | TRUE
20 | R27-021 Research Project Ends | R27-021 | Alternative Intersections | 3 | R27-021: Alternative Intersections | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-08-31 | 2008-08-31 | ICT Project Management | 2009-07-01 | 2009-07-01 | 0 | TRUE | TRUE
21 | R27-022 Research Project Ends | R27-022 | Regional Data Archiving | 3 | R27-022: Regional Data Archiving | FY09-FY11 IGA |  | Nick York | 2008-08-31 | 2008-08-31 | ICT Project Management [0.00 %] | 2009-06-01 | 2009-06-01 | 0 | TRUE | TRUE
22 | R27-023 Research Project Ends | R27-023 | HMA Overlays | 3 | R27-023: HMA Overlays | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-08-31 | 2008-08-31 | ICT Project Management | 2009-09-01 | 2009-09-01 | 0 | TRUE | TRUE
23 | R27-024 Research Project Ends | R27-024 | Foundation Piling Design | 3 | R27-024: Foundation Piling Design | FY09-FY11 IGA |  | Nick York | 2009-03-31 | 2009-03-31 | ICT Project Management [0.00 %] | 2009-03-01 | 2009-03-01 | 0 | TRUE | TRUE
24 | R27-025 Research Project Ends | R27-025 | Integral Abutment Design | 3 | R27-025: Integral Abutment Design | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-03-31 | 2009-03-31 | ICT Project Management | 2009-08-01 | 2009-08-01 | 0 | TRUE | TRUE
25 | R27-026 Research Project Ends | R27-026 | Brass Breakaway Couplings | 3 | R27-026: Brass Breakaway Couplings | FY09-FY11 IGA |  | Nick York | 2009-04-30 | 2009-04-30 | ICT Project Management [0.00 %] | 2011-09-01 | 2011-09-01 | 0 | TRUE | TRUE
26 | R27-027 Research Project Ends | R27-027 | Reclaimed Asphalt | 3 | R27-027: Reclaimed Asphalt | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-04-30 | 2009-04-30 | ICT Project Management | 2009-08-01 | 2009-08-01 | 0 | TRUE | TRUE
27 | R27-028-T1 Research Project Ends | R27-028-T1 | Conference and Training Support | 3 | R27-028-T1: Conference and Training Support | FY09-FY11 IGA |  | Nick York | 2011-06-30 | 2011-06-30 | ICT Project Management [0.00 %] | 2011-06-30 | 2011-06-30 | 0 | TRUE | TRUE
28 | R27-028-T2 Research Project Ends | R27-028-T2 | LTAP GIS Software | 2 | R27-028-T2: LTAP GIS Software | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-10-31 | 2008-10-31 | ICT Project Management | 2008-10-31 | 2008-10-31 | 0 | TRUE | TRUE
29 | R27-028-T3 Research Project Ends | R27-028-T3 | Bearing Capacity Conference | 2 | R27-028-T3: Bearing Capacity Conference | FY09-FY11 IGA |  | Nick York | 2009-09-30 | 2009-09-30 | ICT Project Management [0.00 %] | 2009-09-30 | 2009-09-30 | 0 | TRUE | TRUE
30 | R27-029 Research Project Ends | R27-029 | Particulate Matter 2.5 | 3 | R27-029: Particulate Matter 2.5 | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2008-04-01 | 2008-04-01 | 0 | TRUE | TRUE
31 | R27-030 Research Project Ends | R27-030 | 3-D Laser Scanning for Constr. | 3 | R27-030: 3-D Laser Scanning for Constr. | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-08-15 | 2009-08-15 | ICT Project Management | 2010-04-01 | 2010-04-01 | 0 | TRUE | TRUE
32 | R27-031 Research Project Ends | R27-031 | Wind Powered Electrical Systems | 4 | R27-031: Wind Powered Electrical Systems | FY09-FY11 IGA |  | Nick York | 2008-12-31 | 2008-12-31 | ICT Project Management [0.00 %] | 2009-02-01 | 2009-02-01 | 0 | TRUE | TRUE
33 | R27-032 Research Project Ends | R27-032 | Rolling Lane Closures | 3 | R27-032: Rolling Lane Closures | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-12-31 | 2008-12-31 | ICT Project Management | 2009-06-01 | 2009-06-01 | 0 | TRUE | TRUE
34 | R27-033 Research Project Ends | R27-033 | Cost in Highway Work Zones | 3 | R27-033: Cost in Highway Work Zones | FY09-FY11 IGA |  | Nick York | 2010-08-31 | 2010-08-31 | ICT Project Management [0.00 %] | 2010-09-01 | 2010-09-01 | 0 | TRUE | TRUE
35 | R27-034 Research Project Ends | R27-034 | Benefit-Cost Program Planning | 3 | R27-034: Benefit-Cost Program Planning | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-04-30 | 2009-04-30 | ICT Project Management | 2010-03-01 | 2010-03-01 | 0 | TRUE | TRUE
36 | R27-035 Research Project Ends | R27-035 | Cost Effective Scour Sensor | 3 | R27-035: Cost Effective Scour Sensor | FY09-FY11 IGA |  | Nick York | 2008-10-31 | 2008-10-31 | ICT Project Management [0.00 %] | 2008-10-31 | 2008-10-31 | 0 | TRUE | TRUE
37 | R27-036 Research Project Ends | R27-036 | Tendons in SCC Girders | 3 | R27-036: Tendons in SCC Girders | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-09-30 | 2008-09-30 | ICT Project Management | 2009-03-01 | 2009-03-01 | 0 | TRUE | TRUE
38 | R27-037 Research Project Ends | R27-037 | High RAP Content on Pavement | 30 | R27-037: High RAP Content on Pavement | FY12-FY17 IGA |  | Nick York | 2011-12-31 | 2011-12-31 | ICT Project Management | 2012-06-01 | 2012-06-01 | 0 | TRUE | TRUE
39 | R27-038 Research Project Ends | R27-038 | Concrete Temperatures | 2 | R27-038: Concrete Temperatures | FY09-FY11 IGA |  | Nick York | 2010-06-30 | 2010-06-30 | ICT Project Management [0.00 %] | 2011-08-01 | 2011-08-01 | 0 | TRUE | TRUE
40 | R27-039 Research Project Ends | R27-039 | Context Sensitive Solns Training | 3 | R27-039: Context Sensitive Solns Training | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-09-30 | 2008-09-30 | ICT Project Management | 2009-04-01 | 2009-04-01 | 0 | TRUE | TRUE
41 | R27-040 Research Project Ends | R27-040 | Highway Shoulder Attributes | 3 | R27-040: Highway Shoulder Attributes | FY09-FY11 IGA |  | Nick York | 2010-09-30 | 2010-09-30 | ICT Project Management [0.00 %] | 2011-04-01 | 2011-04-01 | 0 | TRUE | TRUE
42 | R27-041 Research Project Ends | R27-041 | I-57 Recycled Concrete Pvmt. | 3 | R27-041: I-57 Recycled Concrete Pvmt. | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-11-30 | 2008-11-30 | ICT Project Management | 2009-01-01 | 2009-01-01 | 0 | TRUE | TRUE
43 | R27-042 Research Project Ends | R27-042 | High Friction Surface Layer | 38 | R27-042: High Friction Surface Layer | FY12-FY17 IGA |  | Brian Lorbiecki | 2013-03-31 | 2013-03-31 | ICT Project Management | 2013-03-29 | 2013-03-29 | 0 | TRUE | TRUE
44 | R27-043 Research Project Ends | R27-043 | Utah LTAP GIS Software Conversion | 2 | R27-043: Utah LTAP GIS Software Conversion | FY09-FY11 IGA |  | Nick York | 2008-10-31 | 2008-10-31 | ICT Project Management [0.00 %] | 2008-10-31 | 2008-10-31 | 0 | TRUE | TRUE
45 | R27-044 (FY09-11 IGA) Research Project Ends | R27-044 (FY09-11 IGA) | Tech Transfer (FY09-11 IGA) | 2 | R27-044 (FY09-11 IGA): Tech Transfer (FY09-11 IGA) | FY09-FY11 IGA |  | Audrey Donoho | 2011-06-30 | 2011-06-30 | ICT Project Management | 2011-06-30 | 2011-06-30 | 0 | TRUE | TRUE
46 | R27-044 (FY12-17 IGA) Research Project Ends | R27-044 (FY12-17 IGA) | Tech Transfer (FY12-17 IGA) | 25 | R27-044 (FY12-17 IGA): Tech Transfer (FY12-17 IGA) | FY12-FY17 IGA |  | Audrey Donoho | 2017-06-30 | 2017-06-30 | ICT Project Management | 2017-06-30 | 2017-06-30 | 0 | TRUE | TRUE
47 | R27-044-T1 Research Project Ends | R27-044-T1 | Pavement Design Course | 20 | R27-044-T1: Pavement Design Course | FY12-FY17 IGA |  | Brian Lorbiecki | 2013-07-31 | 2013-07-31 | ICT Project Management | 2013-07-31 | 2013-07-31 | 0 | TRUE | TRUE
48 | R27-045 (FY09-11 IGA) Research Project Ends | R27-045 (FY09-11 IGA) | IT Support (FY09-11 IGA) | 2 | R27-045 (FY09-11 IGA): IT Support (FY09-11 IGA) | FY09-FY11 IGA |  | Audrey Donoho | 2011-06-30 | 2011-06-30 | ICT Project Management | 2011-06-30 | 2011-06-30 | 0 | TRUE | TRUE
49 | R27-045 (FY12-17 IGA) Research Project Ends | R27-045 (FY12-17 IGA) | IT Support (FY12-17 IGA) | 25 | R27-045 (FY12-17 IGA): IT Support (FY12-17 IGA) | FY12-FY17 IGA |  | Audrey Donoho | 2017-06-30 | 2017-06-30 | ICT Project Management | 2017-06-30 | 2017-06-30 | 0 | TRUE | TRUE
50 | R27-045-T1 Research Project Ends | R27-045-T1 | Laser Scanner | 38 | R27-045-T1: Laser Scanner | FY18-FY24 IGA |  | ICT Project Management | 2018-06-30 | 2018-06-30 | ICT Project Management | 2018-05-31 | 2018-05-31 | 0 | TRUE | TRUE
51 | R27-046 (FY09-11 IGA) Research Project Ends | R27-046 (FY09-11 IGA) | Special Projects Eng (FY09-11 IGA) | 2 | R27-046 (FY09-11 IGA): Special Projects Eng (FY09-11 IGA) | FY09-FY11 IGA |  | Audrey Donoho | 2011-06-30 | 2011-06-30 | ICT Project Management | 2011-06-30 | 2011-06-30 | 0 | TRUE | TRUE
52 | R27-046 (FY12-17 IGA) Research Project Ends | R27-046 (FY12-17 IGA) | Special Projects Eng (FY12-17 IGA) | 25 | R27-046 (FY12-17 IGA): Special Projects Eng (FY12-17 IGA) | FY12-FY17 IGA |  | Audrey Donoho | 2017-06-30 | 2017-06-30 | ICT Project Management | 2017-06-30 | 2017-06-30 | 0 | TRUE | TRUE
53 | R27-048 Research Project Ends | R27-048 | Travel Demand Modeling for IL MPOs | 3 | R27-048: Travel Demand Modeling for IL MPOs | FY09-FY11 IGA |  | Brian Lorbiecki | 2011-06-30 | 2011-06-30 | ICT Project Management | 2010-10-31 | 2010-10-31 | 0 | TRUE | TRUE
54 | R27-049 Research Project Ends | R27-049 | Documentation | 3 | R27-049: Documentation | FY09-FY11 IGA |  | Nick York | 2010-06-30 | 2010-06-30 | ICT Project Management [0.00 %] | 2010-06-30 | 2010-06-30 | 0 | TRUE | TRUE
55 | R27-050 Research Project Ends | R27-050 | Seniors' Trip Chaining Behavior | 3 | R27-050: Seniors' Trip Chaining Behavior | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-12-31 | 2010-12-31 | ICT Project Management | 2011-08-01 | 2011-08-01 | 0 | TRUE | TRUE
56 | R27-051 Research Project Ends | R27-051 | Truck Parking/Rest Facilities | 4 | R27-051: Truck Parking/Rest Facilities | FY09-FY11 IGA |  | Nick York | 2010-09-30 | 2010-09-30 | ICT Project Management [0.00 %] | 2010-09-30 | 2010-09-30 | 0 | TRUE | TRUE
57 | R27-052 Research Project Ends | R27-052 | Traffic Related WZ Crashes | 2 | R27-052: Traffic Related WZ Crashes | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-09-15 | 2010-09-15 | ICT Project Management | 2013-04-09 | 2013-04-09 | 0 | TRUE | TRUE
58 | R27-054 Research Project Ends | R27-054 | Storm Water P. E.&S. | 35 | R27-054: Storm Water P. E.&S. | FY12-FY17 IGA |  | Nick York | 2012-12-31 | 2012-12-31 | ICT Project Management | 2013-04-01 | 2013-04-01 | 0 | TRUE | TRUE
59 | R27-055 Research Project Ends | R27-055 | Integral Abutment Bridges | 30 | R27-055: Integral Abutment Bridges | FY12-FY17 IGA |  | AKSHITI MODI | 2012-03-31 | 2012-03-31 | ICT Project Management | 2012-03-31 | 2012-03-31 | 0 | TRUE | TRUE
60 | R27-056 Research Project Ends | R27-056 | Prestressed SCC Girders | 3 | R27-056: Prestressed SCC Girders | FY09-FY11 IGA |  | Nick York | 2011-02-28 | 2011-02-28 | ICT Project Management [0.00 %] | 2011-09-01 | 2011-09-01 | 0 | TRUE | TRUE
61 | R27-057 Research Project Ends | R27-057 | Fibrous Additives | 26 | R27-057: Fibrous Additives | FY12-FY17 IGA |  | AKSHITI MODI | 2011-12-31 | 2011-12-31 | ICT Project Management | 2011-12-31 | 2011-12-31 | 0 | TRUE | TRUE
62 | R27-058 Research Project Ends | R27-058 | Wireless Detection Systems Eval | 3 | R27-058: Wireless Detection Systems Eval | FY09-FY11 IGA |  | Brian Lorbiecki | 2011-03-31 | 2011-03-31 | ICT Project Management | 2011-06-01 | 2011-06-01 | 0 | TRUE | TRUE
63 | R27-059 Research Project Ends | R27-059 | Solar Powered Flashing Beacons | 4 | R27-059: Solar Powered Flashing Beacons | FY09-FY11 IGA |  | Nick York | 2011-03-31 | 2011-03-31 | ICT Project Management [0.00 %] | 2011-06-01 | 2011-06-01 | 0 | TRUE | TRUE
64 | R27-060 Research Project Ends | R27-060 | Flexible Pavements (Mechanistic) | 40 | R27-060: Flexible Pavements (Mechanistic) | FY12-FY17 IGA |  | Brian Lorbiecki | 2014-06-30 | 2014-06-30 | ICT Project Management | 2014-05-27 | 2014-05-27 | 0 | TRUE | TRUE
65 | R27-061 Research Project Ends | R27-061 | Rigid Pavements | 41 | R27-061: Rigid Pavements | FY12-FY17 IGA |  | AKSHITI MODI | 2014-08-31 | 2014-08-31 | ICT Project Management | 2014-08-29 | 2014-08-29 | 0 | TRUE | TRUE
66 | R27-062 Research Project Ends | R27-062 | Material Quality Testing & Peer Exchange | 3 | R27-062: Material Quality Testing & Peer Exchange | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-12-31 | 2010-12-31 | ICT Project Management | 2011-03-01 | 2011-03-01 | 0 | TRUE | TRUE
67 | R27-063 Research Project Ends | R27-063 | Joints Cut Using Early-Entry Saws | 3 | R27-063: Joints Cut Using Early-Entry Saws | FY09-FY11 IGA |  | Nick York | 2010-09-30 | 2010-09-30 | ICT Project Management [0.00 %] | 2011-01-01 | 2011-01-01 | 0 | TRUE | TRUE
68 | R27-064 Research Project Ends | R27-064 | Incident Mgmt Operational/Training Guide | 2 | R27-064: Incident Mgmt Operational/Training Guide | FY09-FY11 IGA |  | Brian Lorbiecki | 2011-06-30 | 2011-06-30 | ICT Project Management | 2011-08-01 | 2011-08-01 | 0 | TRUE | TRUE
69 | R27-066 Research Project Ends | R27-066 | IL Speed Enforcement Techniques | 24 | R27-066: IL Speed Enforcement Techniques | FY12-FY17 IGA |  | AKSHITI MODI | 2012-10-31 | 2012-10-31 | ICT Project Management | 2012-10-31 | 2012-10-31 | 0 | TRUE | TRUE
70 | R27-067 Research Project Ends | R27-067 | National Safety Performance Summit | 2 | R27-067: National Safety Performance Summit | FY09-FY11 IGA |  | Nick York | 2009-12-31 | 2009-12-31 | ICT Project Management [0.00 %] | 2010-07-01 | 2010-07-01 | 0 | TRUE | TRUE
71 | R27-068 Research Project Ends | R27-068 | Midwest Air Quality Summit | 3 | R27-068: Midwest Air Quality Summit | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-12-31 | 2009-12-31 | ICT Project Management | 2009-12-31 | 2009-12-31 | 0 | TRUE | TRUE
72 | R27-069 Research Project Ends | R27-069 | Pile Load Test | 25 | R27-069: Pile Load Test | FY12-FY17 IGA |  | AKSHITI MODI | 2012-06-30 | 2012-06-30 | ICT Project Management | 2012-07-01 | 2012-07-01 | 0 | TRUE | TRUE
73 | R27-070 Research Project Ends | R27-070 | Earthquake Resisting System | 44 | R27-070: Earthquake Resisting System | FY12-FY17 IGA |  | AKSHITI MODI | 2012-12-31 | 2012-12-31 | ICT Project Management | 2012-12-01 | 2012-12-01 | 0 | TRUE | TRUE
74 | R27-071 Research Project Ends | R27-071 | Bridge Scour Sensor - Phase 2 | 5 | R27-071: Bridge Scour Sensor - Phase 2 | FY09-FY11 IGA |  | Nick York | 2010-06-30 | 2010-06-30 | ICT Project Management [0.00 %] | 2011-03-01 | 2011-03-01 | 0 | TRUE | TRUE
75 | R27-072 Research Project Ends | R27-072 | Rolling Lane Closures - Phase II | 2 | R27-072: Rolling Lane Closures - Phase II | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-01-31 | 2010-01-31 | ICT Project Management | 2010-08-01 | 2010-08-01 | 0 | TRUE | TRUE
76 | R27-073 Research Project Ends | R27-073 | Distance Technology Transfer | 35 | R27-073: Distance Technology Transfer | FY12-FY17 IGA |  | Nick York | 2013-03-31 | 2013-03-31 | ICT Project Management | 2013-06-01 | 2013-06-01 | 0 | TRUE | TRUE
77 | R27-074 Research Project Ends | R27-074 | Best Management Practices (BMP) for Interstate Rest Areas | 2 | R27-074: Best Management Practices (BMP) for Interstate Rest Areas | FY09-FY11 IGA |  | Nick York | 2010-12-31 | 2010-12-31 | ICT Project Management [0.00 %] | 2011-06-01 | 2011-06-01 | 0 | TRUE | TRUE
78 | R27-075 Research Project Ends | R27-075 | Traffic Signs | 2 | R27-075: Traffic Signs | FY12-FY17 IGA |  | AKSHITI MODI | 2012-03-31 | 2012-03-31 | ICT Project Management | 2013-04-08 | 2013-04-08 | 0 | TRUE | TRUE
79 | R27-076 Research Project Ends | R27-076 | LED Roadway Lighting | 26 | R27-076: LED Roadway Lighting | FY12-FY17 IGA |  | Brian Lorbiecki | 2012-03-31 | 2012-03-31 | ICT Project Management | 2012-03-31 | 2012-03-31 | 0 | TRUE | TRUE
80 | R27-077 Research Project Ends | R27-077 | Durable Pavement Markings on HMA Mixes | 33 | R27-077: Durable Pavement Markings on HMA Mixes | FY12-FY17 IGA |  | Nick York | 2013-11-30 | 2013-11-30 | ICT Project Management | 2013-12-01 | 2013-12-01 | 0 | TRUE | TRUE
81 | R27-078 Research Project Ends | R27-078 | Asphalt Binder Additives/Modifiers | 31 | R27-078: Asphalt Binder Additives/Modifiers | FY12-FY17 IGA |  | Brian Lorbiecki | 2013-12-31 | 2013-12-31 | ICT Project Management | 2014-01-31 | 2014-01-31 | 0 | TRUE | TRUE
82 | R27-079 Research Project Ends | R27-079 | Fine-Graded Hot Mix Asphalt | 36 | R27-079: Fine-Graded Hot Mix Asphalt | FY12-FY17 IGA |  | Nick York | 2013-12-31 | 2013-12-31 | ICT Project Management [0.00 %] | 2015-04-16 | 2015-04-16 | 0 | TRUE | TRUE
83 | R27-080 Research Project Ends | R27-080 | Fatigue Testing of Brass Breakaway Couplings | 3 | R27-080: Fatigue Testing of Brass Breakaway Couplings | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-12-31 | 2010-12-31 | ICT Project Management | 2013-04-16 | 2013-04-16 | 0 | TRUE | TRUE
84 | R27-081 Research Project Ends | R27-081 | Performance of IL Aggregates | 19 | R27-081: Performance of IL Aggregates | FY12-FY17 IGA |  | AKSHITI MODI | 2011-12-31 | 2011-12-31 | ICT Project Management | 2011-12-31 | 2011-12-31 | 0 | TRUE | TRUE
85 | R27-082 Research Project Ends | R27-082 | Bridge Wood Pilings Retrofits | 31 | R27-082: Bridge Wood Pilings Retrofits | FY12-FY17 IGA |  | Brian Lorbiecki | 2012-08-15 | 2012-08-15 | ICT Project Management | 2012-08-15 | 2012-08-15 | 0 | TRUE | TRUE
86 | R27-083 Research Project Ends | R27-083 | Good Movement Study in IL | 16 | R27-083: Good Movement Study in IL | FY12-FY17 IGA |  | AKSHITI MODI | 2011-08-15 | 2011-08-15 | ICT Project Management | 2011-08-15 | 2011-08-15 | 0 | TRUE | TRUE
87 | R27-084 Research Project Ends | R27-084 | Highway Networks | 3 | R27-084: Highway Networks | FY09-FY11 IGA |  | Nick York | 2011-06-30 | 2011-06-30 | ICT Project Management [0.00 %] | 2013-04-01 | 2013-04-01 | 0 | TRUE | TRUE
88 | R27-086 Research Project Ends | R27-086 | Hwy Construction Scheduling with Systems Approach | 2 | R27-086: Hwy Construction Scheduling with Systems Approach | FY09-FY11 IGA |  | Brian Lorbiecki | 2011-06-30 | 2011-06-30 | ICT Project Management | 2011-09-01 | 2011-09-01 | 0 | TRUE | TRUE
89 | R27-087 Research Project Ends | R27-087 | Pavement Management Systems | 20 | R27-087: Pavement Management Systems | FY12-FY17 IGA |  | AKSHITI MODI | 2011-08-31 | 2011-08-31 | ICT Project Management | 2011-08-31 | 2011-08-31 | 0 | TRUE | TRUE
90 | R27-088 Research Project Ends | R27-088 | Bridge Decks (Durability) | 32 | R27-088: Bridge Decks (Durability) | FY12-FY17 IGA |  | Nick York | 2013-06-15 | 2013-06-15 | ICT Project Management | 2013-07-01 | 2013-07-01 | 0 | TRUE | TRUE
91 | R27-089 Research Project Ends | R27-089 | Illinois Highway Safety Manual Workshop | 3 | R27-089: Illinois Highway Safety Manual Workshop | FY09-FY11 IGA |  | Nick York | 2011-06-30 | 2011-06-30 | Nick York [0.00 %] | 2012-10-01 | 2012-10-01 | 0 | TRUE | TRUE
92 | R27-090 Research Project Ends | R27-090 | Investigation Wrong-Way Driving | 42 | R27-090: Investigation Wrong-Way Driving | FY12-FY17 IGA |  | AKSHITI MODI | 2015-09-30 | 2015-09-30 | ICT Project Management | 2015-09-30 | 2015-09-30 | 0 | TRUE | TRUE
93 | R27-091 Research Project Ends | R27-091 | Traffic Flow Monitoring Technologies | 2 | R27-091: Traffic Flow Monitoring Technologies | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-12-31 | 2010-12-31 | ICT Project Management | 2013-06-01 | 2013-06-01 | 0 | TRUE | TRUE
94 | R27-093 Research Project Ends | R27-093 | Hot-Spot Air Quality Modeling | 31 | R27-093: Hot-Spot Air Quality Modeling | FY12-FY17 IGA |  | AKSHITI MODI | 2013-06-30 | 2013-06-30 | ICT Project Management | 2013-06-30 | 2013-06-30 | 0 | TRUE | TRUE
95 | R27-094 Research Project Ends | R27-094 | Snow & Ice Plows | 34 | R27-094: Snow & Ice Plows | FY12-FY17 IGA |  | AKSHITI MODI | 2015-11-30 | 2015-11-30 | ICT Project Management | 2015-11-20 | 2015-11-20 | 0 | TRUE | TRUE
96 | R27-095 Research Project Ends | R27-095 | RR Crossings | 39 | R27-095: RR Crossings | FY12-FY17 IGA |  | Nick York | 2014-12-31 | 2014-12-31 | ICT Project Management | 2015-01-27 | 2015-01-27 | 0 | TRUE | TRUE
97 | R27-096 Research Project Ends | R27-096 | Pedestrian/Bicyclist Warning Devices | 21 | R27-096: Pedestrian/Bicyclist Warning Devices | FY12-FY17 IGA |  | Nick York | 2012-12-31 | 2012-12-31 | ICT Project Management | 2013-04-01 | 2013-04-01 | 0 | TRUE | TRUE
98 | R27-097 Research Project Ends | R27-097 | Yellow Arrows | 42 | R27-097: Yellow Arrows | FY12-FY17 IGA |  | Nick York | 2016-03-31 | 2016-03-31 | ICT Project Management | 2016-03-02 | 2016-03-02 | 0 | TRUE | TRUE
99 | R27-098 Research Project Ends | R27-098 | Concrete Cylinder | 20 | R27-098: Concrete Cylinder | FY12-FY17 IGA |  | Brian Lorbiecki | 2012-06-30 | 2012-06-30 | ICT Project Management | 2012-06-30 | 2012-06-30 | 0 | TRUE | TRUE
100 | R27-099 Research Project Ends | R27-099 | Drilled Shafts | 17 | R27-099: Drilled Shafts | FY12-FY17 IGA |  | Nick York | 2013-04-30 | 2013-04-30 | ICT Project Management | 2013-05-01 | 2013-05-01 | 0 | TRUE | TRUE
101 | R27-100 Research Project Ends | R27-100 | Tack Coat Phase 2 | 24 | R27-100: Tack Coat Phase 2 | FY12-FY17 IGA |  | Nick York | 2013-03-15 | 2013-03-15 | ICT Project Management | 2012-07-01 | 2012-07-01 | 0 | TRUE | TRUE
102 | R27-101 Research Project Ends | R27-101 | BS/MS Student Scholarships | 4 | R27-101: BS/MS Student Scholarships | FY12-FY17 IGA |  | Brian Lorbiecki | 2017-06-30 | 2017-06-30 | ICT Project Management | 2017-06-30 | 2017-06-30 | 0 | TRUE | TRUE
103 | R27-102 Research Project Ends | R27-102 | Ditch Checks & Inlet Protection Structures | 41 | R27-102: Ditch Checks & Inlet Protection Structures | FY12-FY17 IGA |  | AKSHITI MODI | 2016-01-15 | 2016-01-15 | ICT Project Management | 2016-01-15 | 2016-01-15 | 0 | TRUE | TRUE
104 | R27-103 Research Project Ends | R27-103 | Interstate Rest Areas | 22 | R27-103: Interstate Rest Areas | FY12-FY17 IGA |  | AKSHITI MODI | 2013-06-30 | 2013-06-30 | ICT Project Management | 2013-06-30 | 2013-06-30 | 0 | TRUE | TRUE
105 | R27-104 Research Project Ends | R27-104 | Native Vegetation | 20 | R27-104: Native Vegetation | FY12-FY17 IGA |  | AKSHITI MODI | 2014-05-31 | 2014-05-31 | ICT Project Management | 2014-05-31 | 2014-05-31 | 0 | TRUE | TRUE
106 | R27-105 Research Project Ends | R27-105 | Bridge Scour Estimates w/ Sricos Phjase 2 | 19 | R27-105: Bridge Scour Estimates w/ Sricos Phjase 2 | FY12-FY17 IGA |  | Nick York | 2013-03-31 | 2013-03-31 | ICT Project Management | 2013-09-01 | 2013-09-01 | 0 | TRUE | TRUE
107 | R27-106 Research Project Ends | R27-106 | High Performance Grade 50 Structural Steel | 21 | R27-106: High Performance Grade 50 Structural Steel | FY12-FY17 IGA |  | Nick York | 2013-10-31 | 2013-10-31 | ICT Project Management | 2013-10-31 | 2013-10-31 | 0 | TRUE | TRUE
108 | R27-108 Research Project Ends | R27-108 | Night Traffic Warning Devices | 21 | R27-108: Night Traffic Warning Devices | FY12-FY17 IGA |  | Nick York | 2013-10-31 | 2013-10-31 | ICT Project Management | 2013-11-01 | 2013-11-01 | 0 | TRUE | TRUE
109 | R27-109 Research Project Ends | R27-109 | Flaggers & Spotters | 24 | R27-109: Flaggers & Spotters | FY12-FY17 IGA |  | Nick York | 2013-10-31 | 2013-10-31 | ICT Project Management | 2014-01-01 | 2014-01-01 | 0 | TRUE | TRUE
110 | R27-110 Research Project Ends | R27-110 | Highway Work Zones | 15 | R27-110: Highway Work Zones | FY12-FY17 IGA |  | Nick York | 2013-04-15 | 2013-04-15 | ICT Project Management | 2013-06-06 | 2013-06-06 | 0 | TRUE | TRUE
111 | R27-111 Research Project Ends | R27-111 | Right-Turn Lane Design | 36 | R27-111: Right-Turn Lane Design | FY12-FY17 IGA |  | Nick York | 2016-06-30 | 2016-06-30 | ICT Project Management | 2016-06-06 | 2016-06-06 | 0 | TRUE | TRUE
112 | R27-112 Research Project Ends | R27-112 | Testing of Portland Cement | 23 | R27-112: Testing of Portland Cement | FY12-FY17 IGA |  | AKSHITI MODI | 2013-12-31 | 2013-12-31 | ICT Project Management | 2013-12-31 | 2013-12-31 | 0 | TRUE | TRUE
113 | R27-113 Research Project Ends | R27-113 | Modeling Seniors Activity | 21 | R27-113: Modeling Seniors Activity | FY12-FY17 IGA |  | AKSHITI MODI | 2013-08-15 | 2013-08-15 | ICT Project Management | 2013-08-01 | 2013-08-01 | 0 | TRUE | TRUE
114 | R27-114 Research Project Ends | R27-114 | Restoration Progress at IDOT | 17 | R27-114: Restoration Progress at IDOT | FY12-FY17 IGA |  | AKSHITI MODI | 2013-03-31 | 2013-03-31 | ICT Project Management | 2013-03-31 | 2013-03-31 | 0 | TRUE | TRUE
115 | R27-115 Research Project Ends | R27-115 | Superstructures | 45 | R27-115: Superstructures | FY18-FY24 IGA |  | ICT Project Management | 2017-08-15 | 2017-08-15 | ICT Project Management | 2017-08-25 | 2017-08-25 | 0 | TRUE | TRUE
116 | R27-116 Research Project Ends | R27-116 | Highway Inventory Data | 17 | R27-116: Highway Inventory Data | FY12-FY17 IGA |  | Nick York | 2013-06-30 | 2013-06-30 | ICT Project Management | 2013-06-28 | 2013-06-28 | 0 | TRUE | TRUE
117 | R27-117 Research Project Ends | R27-117 | Engineers Peer to Peer Workshop | 14 | R27-117: Engineers Peer to Peer Workshop | FY12-FY17 IGA |  | Nick York | 2013-06-30 | 2013-06-30 | ICT Project Management | 2013-11-12 | 2013-11-12 | 0 | TRUE | TRUE
118 | R27-118 Research Project Ends | R27-118 | Traffic Incident Management | 31 | R27-118: Traffic Incident Management | FY12-FY17 IGA |  | Nick York | 2014-06-30 | 2014-06-30 | ICT Project Management | 2014-08-05 | 2014-08-05 | 0 | TRUE | TRUE
119 | R27-119 Research Project Ends | R27-119 | Real-Time Information Dissemination | 25 | R27-119: Real-Time Information Dissemination | FY12-FY17 IGA |  | Nick York | 2016-02-15 | 2016-02-15 | ICT Project Management | 2016-02-01 | 2016-02-01 | 0 | TRUE | TRUE
120 | R27-120 Research Project Ends | R27-120 | All Weather | 52 | R27-120: All Weather | FY18-FY24 IGA |  | ICT Project Management | 2019-06-30 | 2019-06-30 | Brian Lorbiecki | 2019-06-27 | 2019-06-27 | 0 | TRUE | TRUE
121 | R27-122 Research Project Ends | R27-122 | Driven Pile Installation | 22 | R27-122: Driven Pile Installation | FY12-FY17 IGA |  | Nick York | 2014-08-31 | 2014-08-31 | ICT Project Management | 2014-09-02 | 2014-09-02 | 0 | TRUE | TRUE
122 | R27-123 Research Project Ends | R27-123 | Street Lighting Technologies | 24 | R27-123: Street Lighting Technologies | FY12-FY17 IGA |  | Nick York | 2015-01-15 | 2015-01-15 | ICT Project Management | 2015-01-05 | 2015-01-05 | 337802 | TRUE | TRUE
123 | R27-124 Research Project Ends | R27-124 | Evaluation of Porous Materials | 27 | R27-124: Evaluation of Porous Materials | FY12-FY17 IGA |  | AKSHITI MODI | 2015-07-31 | 2015-07-31 | ICT Project Management | 2015-05-31 | 2015-05-31 | 0 | TRUE | TRUE
124 | R27-125 Research Project Ends | R27-125 | Sustainable Aggregates | 24 | R27-125: Sustainable Aggregates | FY12-FY17 IGA |  | AKSHITI MODI | 2015-05-31 | 2015-05-31 | ICT Project Management | 2015-05-31 | 2015-05-31 | 0 | TRUE | TRUE
125 | R27-126 Research Project Ends | R27-126 | Temporary Stabilization | 23 | R27-126: Temporary Stabilization | FY12-FY17 IGA |  | AKSHITI MODI | 2014-09-30 | 2014-09-30 | ICT Project Management | 2014-09-24 | 2014-09-24 | 0 | TRUE | TRUE
126 | R27-127 Research Project Ends | R27-127 | ASCT | 58 | R27-127: ASCT | FY18-FY24 IGA |  | ICT Project Management | 2019-06-30 | 2019-06-30 | Brian Lorbiecki | 2019-06-25 | 2019-06-25 | 0 | TRUE | TRUE
127 | R27-128 Research Project Ends | R27-128 | Binder Replacement | 26 | R27-128: Binder Replacement | FY12-FY17 IGA |  | Nick York | 2015-12-31 | 2015-12-31 | ICT Project Management | 2015-12-11 | 2015-12-11 | 0 | TRUE | TRUE
128 | R27-129 Research Project Ends | R27-129 | AIMS | 17 | R27-129: AIMS | FY12-FY17 IGA |  | Nick York | 2014-02-28 | 2014-02-28 | ICT Project Management | 2014-05-01 | 2014-05-01 | 0 | TRUE | TRUE
129 | R27-130 Research Project Ends | R27-130 | Overlay Thickness | 28 | R27-130: Overlay Thickness | FY12-FY17 IGA |  | Nick York | 2015-07-31 | 2015-07-31 | ICT Project Management | 2015-07-28 | 2015-07-28 | 0 | TRUE | TRUE
130 | R27-131 Research Project Ends | R27-131 | Urban Traffic | 21 | R27-131: Urban Traffic | FY12-FY17 IGA |  | Nick York | 2014-12-31 | 2014-12-31 | ICT Project Management | 2014-12-01 | 2014-12-01 | 0 | TRUE | TRUE
131 | R27-132 Research Project Ends | R27-132 | Incorporating NEPA into the IDOT and MPO Planning Process | 19 | R27-132: Incorporating NEPA into the IDOT and MPO Planning Process | FY12-FY17 IGA |  | Nick York | 2014-06-30 | 2014-06-30 | ICT Project Management | 2014-07-23 | 2014-07-23 | 0 | TRUE | TRUE
132 | R27-133 Research Project Ends | R27-133 | Earthquake Resisting System | 38 | R27-133: Earthquake Resisting System | FY18-FY24 IGA |  | ICT Project Management | 2018-08-31 | 2018-08-31 | ICT Project Management | 2018-08-31 | 2018-08-31 | 0 | TRUE | TRUE
133 | R27-134 Research Project Ends | R27-134 | Bridge Wood Pilings | 32 | R27-134: Bridge Wood Pilings | FY12-FY17 IGA |  | Nick York | 2016-05-15 | 2016-05-15 | ICT Project Management | 2016-05-09 | 2016-05-09 | 0 | TRUE | TRUE
134 | R27-135 Research Project Ends | R27-135 | Hwy Construction Mgmt 2 | 20 | R27-135: Hwy Construction Mgmt 2 | FY12-FY17 IGA |  | AKSHITI MODI | 2015-05-31 | 2015-05-31 | ICT Project Management | 2015-05-31 | 2015-05-31 | 0 | TRUE | TRUE
135 | R27-136 Research Project Ends | R27-136 | PROWAG | 25 | R27-136: PROWAG | FY12-FY17 IGA |  | AKSHITI MODI | 2016-01-31 | 2016-01-31 | ICT Project Management | 2015-01-31 | 2015-01-31 | 0 | TRUE | TRUE
136 | R27-137 Research Project Ends | R27-137 | Evaluation of PCC | 29 | R27-137: Evaluation of PCC | FY12-FY17 IGA |  | AKSHITI MODI | 2016-12-31 | 2016-12-31 | ICT Project Management | 2016-12-14 | 2016-12-14 | 0 | TRUE | TRUE
137 | R27-138 Research Project Ends | R27-138 | Material & Construction Inspection | 17 | R27-138: Material & Construction Inspection | FY12-FY17 IGA |  | Nick York | 2014-04-30 | 2014-04-30 | ICT Project Management | 2015-02-23 | 2015-02-23 | 0 | TRUE | TRUE
138 | R27-139 Research Project Ends | R27-139 | Bridge Decks 2 | 27 | R27-139: Bridge Decks 2 | FY12-FY17 IGA |  | Nick York | 2016-06-30 | 2016-06-30 | ICT Project Management | 2016-06-30 | 2016-06-30 | 0 | TRUE | TRUE |  | 367740 |  | James Krstulovich | 275805 |  | 160904 | 300000 | Paramita Mondal | PVMT
139 | R27-140 Research Project Ends | R27-140 | Exterior Beam | 23 | R27-140: Exterior Beam | FY12-FY17 IGA |  | Nick York | 2016-06-30 | 2016-06-30 | ICT Project Management | 2016-06-30 | 2016-06-30 | 0 | TRUE | TRUE
140 | R27-141 Research Project Ends | R27-141 | Storm Water Run | 32 | R27-141: Storm Water Run | FY12-FY17 IGA |  | Nick York | 2017-06-30 | 2017-06-30 | ICT Project Management | 2017-06-29 | 2017-06-29 | 0 | TRUE | TRUE
141 | R27-142 Research Project Ends | R27-142 | Road Weather Information System | 21 | R27-142: Road Weather Information System | FY12-FY17 IGA |  | Nick York | 2016-09-30 | 2016-09-30 | ICT Project Management | 2016-09-22 | 2016-09-22 | 0 | TRUE | TRUE
142 | R27-143 Research Project Ends | R27-143 | Tree Establishment | 14 | R27-143: Tree Establishment | FY12-FY17 IGA |  | Nick York | 2015-02-28 | 2015-02-28 | ICT Project Management | 2015-02-25 | 2015-02-25 | 0 | TRUE | TRUE
143 | R27-144 Research Project Ends | R27-144 | Urban Flood Frequency Equations | 28 | R27-144: Urban Flood Frequency Equations | FY12-FY17 IGA |  | ICT Project Management | 2016-06-30 | 2016-06-30 | ICT Project Management | 2016-06-29 | 2016-06-29 | 0 | TRUE | TRUE
144 | R27-145 Research Project Ends | R27-145 | Drill Shafts Weak Rocks | 35 | R27-145: Drill Shafts Weak Rocks | FY18-FY24 IGA |  | ICT Project Management | 2017-12-16 | 2017-12-16 | ICT Project Management | 2017-12-14 | 2017-12-14 | 0 | TRUE | TRUE
145 | R27-146 Research Project Ends | R27-146 | (MIRA) Ultrasonic Imaging for Concrete Infrastructures | 32 | R27-146: (MIRA) Ultrasonic Imaging for Concrete Infrastructures | FY12-FY17 IGA |  | ICT Project Management | 2017-04-30 | 2017-04-30 | ICT Project Management | 2017-04-25 | 2017-04-25 | 0 | TRUE | TRUE
146 | R27-147 Research Project Ends | R27-147 | Chloride Reduction | 12 | R27-147: Chloride Reduction | FY12-FY17 IGA |  | ICT Project Management | 2014-09-15 | 2014-09-15 | ICT Project Management | 2014-09-15 | 2014-09-15 | 0 | TRUE | TRUE
147 | R27-148 Research Project Ends | R27-148 | Low-Water Crossing Design for Very Low ADT | 23 | R27-148: Low-Water Crossing Design for Very Low ADT | FY12-FY17 IGA |  | ICT Project Management | 2016-12-31 | 2016-12-31 | ICT Project Management | 2016-11-21 | 2016-11-21 | 0 | TRUE | TRUE
148 | R27-149-1 Research Project Ends | R27-149-1 | M-E Design Flexible Pavements | 33 | R27-149-1: M-E Design Flexible Pavements | FY18-FY24 IGA |  | ICT Project Management | 2018-06-30 | 2018-06-30 | ICT Project Management | 2018-06-08 | 2018-06-08 | 0 | TRUE | TRUE
149 | R27-149-2 Research Project Ends | R27-149-2 | M-E Design Rigid Pavements | 35 | R27-149-2: M-E Design Rigid Pavements | FY18-FY24 IGA |  | ICT Project Management | 2018-08-31 | 2018-08-31 | ICT Project Management | 2018-08-31 | 2018-08-31 | 0 | TRUE | TRUE
150 | R27-150 Research Project Ends | R27-150 | Condition Rating Models | 31 | R27-150: Condition Rating Models | FY18-FY24 IGA |  | ICT Project Management | 2018-02-28 | 2018-02-28 | ICT Project Management | 2018-04-06 | 2018-04-06 | 0 | TRUE | TRUE
151 | R27-151 Research Project Ends | R27-151 | RPM | 41 | R27-151: RPM | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-11-30 | 2019-11-30 | Brian Lorbiecki | 2019-11-08 | 2019-11-08 | 0 | TRUE | TRUE
152 | R27-152 Research Project Ends | R27-152 | Fees Charged for Oversize/Overweight Vehicle Permits | 23 | R27-152: Fees Charged for Oversize/Overweight Vehicle Permits | FY12-FY17 IGA |  | ICT Project Management | 2017-02-28 | 2017-02-28 | ICT Project Management | 2017-06-29 | 2017-06-29 | 0 | TRUE | TRUE
153 | R27-153 Research Project Ends | R27-153 | Utility Relocation | 25 | R27-153: Utility Relocation | FY18-FY24 IGA |  | ICT Project Management | 2017-07-31 | 2017-07-31 | ICT Project Management | 2017-07-24 | 2017-07-24 | 0 | TRUE | TRUE
154 | R27-154 Research Project Ends | R27-154 | Early-Age Concrete | 29 | R27-154: Early-Age Concrete | FY18-FY24 IGA |  | ICT Project Management | 2017-12-15 | 2017-12-15 | ICT Project Management | 2017-12-14 | 2017-12-14 | 0 | TRUE | TRUE
155 | R27-155 Research Project Ends | R27-155 | Smart Work Zone | 20 | R27-155: Smart Work Zone | FY12-FY17 IGA |  | ICT Project Management | 2016-11-30 | 2016-11-30 | ICT Project Management | 2016-12-01 | 2016-12-01 | 0 | TRUE | TRUE
156 | R27-156 Research Project Ends | R27-156 | Prestressed Beams | 34 | R27-156: Prestressed Beams | FY18-FY24 IGA |  | ICT Project Management | 2018-01-31 | 2018-01-31 | ICT Project Management | 2018-02-16 | 2018-02-16 | 0 | TRUE | TRUE
157 | R27-157 Research Project Ends | R27-157 | Plasticity Index | 33 | R27-157: Plasticity Index | FY18-FY24 IGA |  | ICT Project Management | 2018-09-30 | 2018-09-30 | ICT Project Management | 2018-10-03 | 2018-10-03 | 0 | TRUE | TRUE
158 | R27-160 Research Project Ends | R27-160 | Sustainability Engineering | 2 | R27-160: Sustainability Engineering | FY12-FY17 IGA |  | ICT Project Management | 2017-06-30 | 2017-06-30 | ICT Project Management | 2017-07-18 | 2017-07-18 | 0 | TRUE | TRUE
159 | R27-161 Research Project Ends | R27-161 | Performance Monitoring | 42 | R27-161: Performance Monitoring | FY18-FY24 IGA |  | ICT Project Management | 2017-12-31 | 2017-12-31 | ICT Project Management | 2017-12-21 | 2017-12-21 | 0 | TRUE | TRUE
160 | R27-162 Research Project Ends | R27-162 | Chemical/BK Project | 22 | R27-162: Chemical/BK Project | FY12-FY17 IGA |  | ICT Project Management | 2017-01-31 | 2017-01-31 | ICT Project Management | 2017-02-01 | 2017-02-01 | 0 | TRUE | TRUE
161 | R27-163 Research Project Ends | R27-163 | Staking and Inspection | 26 | R27-163: Staking and Inspection | FY18-FY24 IGA |  | ICT Project Management | 2017-08-15 | 2017-08-15 |  | 2017-08-15 | 2017-08-15 | 0 | TRUE | TRUE
162 | R27-164 Research Project Ends | R27-164 | Living Snow Fences | 47 | R27-164: Living Snow Fences | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-12-15 | 2020-12-15 | Brian Lorbiecki | 2020-11-04 | 2020-11-04 | 0 | TRUE | TRUE
163 | R27-165 Research Project Ends | R27-165 | Determine whether a Deck with a Microsilica or Latex Concrete Overlay | 5 | R27-165: Determine whether a Deck with a Microsilica or Latex Concrete Overlay | FY12-FY17 IGA |  | ICT Project Management | 2016-02-08 | 2016-02-08 | ICT Project Management | 2016-02-08 | 2016-02-08 | 0 | TRUE | TRUE
164 | R27-167 Research Project Ends | R27-167 | Pedestrian Treatments | 25 | R27-167: Pedestrian Treatments | FY18-FY24 IGA |  | ICT Project Management | 2017-08-15 | 2017-08-15 | ICT Project Management | 2017-08-30 | 2017-08-30 | 0 | TRUE | TRUE
165 | R27-168 Research Project Ends | R27-168 | Sustainable Aggregates Ph. II | 31 | R27-168: Sustainable Aggregates Ph. II | FY18-FY24 IGA |  | ICT Project Management | 2018-09-30 | 2018-09-30 | ICT Project Management | 2018-10-03 | 2018-10-03 | 0 | TRUE | TRUE
166 | R27-169 Research Project Ends | R27-169 | Opportunistic Traffic Sensing | 42 | R27-169: Opportunistic Traffic Sensing | FY18-FY24 IGA |  | ICT Project Management | 2018-08-15 | 2018-08-15 | ICT Project Management | 2018-08-08 | 2018-08-08 | 0 | TRUE | TRUE
167 | R27-170 Research Project Ends | R27-170 | Rehab Course | 30 | R27-170: Rehab Course | FY18-FY24 IGA |  | Audrey Donoho | 2019-03-31 | 2019-03-31 | Audrey Donoho | 2019-03-29 | 2019-03-29 | 0 | TRUE | TRUE
168 | R27-171 Research Project Ends | R27-171 | Load Factors | 32 | R27-171: Load Factors | FY18-FY24 IGA |  | Audrey Donoho | 2019-02-28 | 2019-02-28 | Audrey Donoho | 2019-02-28 | 2019-02-28 | 0 | TRUE | TRUE
169 | R27-172 Research Project Ends | R27-172 | Soybean | 29 | R27-172: Soybean | FY18-FY24 IGA |  | ICT Project Management | 2018-06-30 | 2018-06-30 | ICT Project Management | 2018-06-27 | 2018-06-27 | 0 | TRUE | TRUE
170 | R27-174 Research Project Ends | R27-174 | Chip, Crack & Seal | 31 | R27-174: Chip, Crack & Seal | FY18-FY24 IGA |  | ICT Project Management | 2019-06-30 | 2019-06-30 | ICT Project Management | 2019-06-27 | 2019-06-27 | 0 | TRUE | TRUE
171 | R27-175 Research Project Ends | R27-175 | Long-Term Aging | 27 | R27-175: Long-Term Aging | FY18-FY24 IGA |  | ICT Project Management | 2019-08-31 | 2019-08-31 | ICT Project Management | 2019-08-02 | 2019-08-02 | 0 | TRUE | TRUE
172 | R27-176 Research Project Ends | R27-176 | Noise Barriers | 17 | R27-176: Noise Barriers | FY18-FY24 IGA |  | Audrey Donoho | 2018-11-30 | 2018-11-30 | Audrey Donoho | 2018-11-29 | 2018-11-29 | 0 | TRUE | TRUE
173 | R27-177 Research Project Ends | R27-177 | Dynamic Travel Time | 28 | R27-177: Dynamic Travel Time | FY18-FY24 IGA |  | Audrey Donoho | 2020-06-30 | 2020-06-30 | Audrey Donoho | 2020-06-29 | 2020-06-29 | 0 | TRUE | TRUE
174 | R27-178-1 Research Project Ends | R27-178-1 | Bridge Decks Phase III | 29 | R27-178-1: Bridge Decks Phase III | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-12-15 | 2020-12-15 | Brian Lorbiecki | 2020-12-10 | 2020-12-10 | 0 | TRUE | TRUE
175 | R27-178-2 Research Project Ends | R27-178-2 | Bridge Decks Phase III Hindi | 30 | R27-178-2: Bridge Decks Phase III Hindi | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-12-15 | 2020-12-15 | Brian Lorbiecki | 2020-12-10 | 2020-12-10 | 0 | TRUE | TRUE
176 | R27-179 Research Project Ends | R27-179 | Beam Rotation | 20 | R27-179: Beam Rotation | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-09-15 | 2019-09-15 | Audrey Donoho | 2019-09-11 | 2019-09-11 | 0 | TRUE | TRUE
177 | R27-180 Research Project Ends | R27-180 | SCM | 41 | R27-180: SCM | FY18-FY24 IGA |  | Audrey Donoho | 2021-09-30 | 2021-09-30 | Audrey Donoho | 2021-09-09 | 2021-09-09 | 0 | TRUE | TRUE
178 | R27-181 Research Project Ends | R27-181 | StreamStats | 59 | R27-181: StreamStats | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-12-31 | 2023-12-31 | Brian Lorbiecki | 2023-09-20 | 2023-09-20 | 0 | TRUE | TRUE
179 | R27-182 Research Project Ends | R27-182 | Riprap Phase I | 24 | R27-182: Riprap Phase I | FY18-FY24 IGA |  | Audrey Donoho | 2020-06-30 | 2020-06-30 | Audrey Donoho | 2020-01-16 | 2020-01-16 | 0 | TRUE | TRUE
180 | R27-183-HS Research Project Ends | R27-183-HS | Contaminated Soil | 46 | R27-183-HS: Contaminated Soil | FY18-FY24 IGA |  | Audrey Donoho | 2021-06-30 | 2021-06-30 | Audrey Donoho | 2021-06-21 | 2021-06-21 | 0 | TRUE | TRUE
181 | R27-186 Research Project Ends | R27-186 | Work Zone | 23 | R27-186: Work Zone | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-01-31 | 2020-01-31 | Brian Lorbiecki | 2020-01-15 | 2020-01-15 | 0 | TRUE | TRUE
182 | R27-187 Research Project Ends | R27-187 | Surface Treatments | 15 | R27-187: Surface Treatments | FY18-FY24 IGA |  | Audrey Donoho | 2018-12-31 | 2018-12-31 | Audrey Donoho | 2018-11-29 | 2018-11-29 | 0 | TRUE | TRUE
183 | R27-188 Research Project Ends | R27-188 | Drilled Shaft | 52 | R27-188: Drilled Shaft | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-11-30 | 2022-11-30 | Brian Lorbiecki | 2022-10-12 | 2022-10-12 | 0 | TRUE | TRUE
184 | R27-189 Research Project Ends | R27-189 | QCP/PFP | 28 | R27-189: QCP/PFP | FY18-FY24 IGA |  | Audrey Donoho | 2020-06-30 | 2020-06-30 | McCall Macomber | 2020-06-26 | 2020-06-26 | 0 | TRUE | TRUE
185 | R27-190 Research Project Ends | R27-190 | Perimeter Barriers | 32 | R27-190: Perimeter Barriers | FY18-FY24 IGA |  | Audrey Donoho | 2021-05-15 | 2021-05-15 | Audrey Donoho | 2021-05-03 | 2021-05-03 | 0 | TRUE | TRUE
186 | R27-191 Research Project Ends | R27-191 | Snow Fences | 24 | R27-191: Snow Fences | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-02-15 | 2021-02-15 | Brian Lorbiecki | 2020-11-06 | 2020-11-06 | 0 | TRUE | TRUE
187 | R27-192 Research Project Ends | R27-192 | Maritime Freight | 25 | R27-192: Maritime Freight | FY18-FY24 IGA |  | Audrey Donoho | 2020-12-15 | 2020-12-15 | Audrey Donoho | 2020-12-02 | 2020-12-02 | 0 | TRUE | TRUE
188 | R27-193-1 Research Project Ends | R27-193-1 | CIR and FDR | 27 | R27-193-1: CIR and FDR | FY18-FY24 IGA |  | Audrey Donoho | 2021-07-15 | 2021-07-15 | Audrey Donoho | 2021-07-06 | 2021-07-06 | 0 | TRUE | TRUE
189 | R27-193-2 Research Project Ends | R27-193-2 | Flexible Pavements (Rubblization) | 31 | R27-193-2: Flexible Pavements (Rubblization) | FY18-FY24 IGA |  | Audrey Donoho | 2021-07-15 | 2021-07-15 | Audrey Donoho | 2021-07-01 | 2021-07-01 | 0 | TRUE | TRUE
190 | R27-193-3 Research Project Ends | R27-193-3 | Geosynthetics | 28 | R27-193-3: Geosynthetics | FY18-FY24 IGA |  | Audrey Donoho | 2021-08-15 | 2021-08-15 | Audrey Donoho | 2021-08-05 | 2021-08-05 | 0 | TRUE | TRUE
191 | R27-193-4 Research Project Ends | R27-193-4 | JCPC | 27 | R27-193-4: JCPC | FY18-FY24 IGA |  | Audrey Donoho | 2021-01-15 | 2021-01-15 | Audrey Donoho | 2021-01-06 | 2021-01-06 | 0 | TRUE | TRUE
192 | R27-193-5 Research Project Ends | R27-193-5 | M-E Pavement Design | 22 | R27-193-5: M-E Pavement Design | FY18-FY24 IGA |  | Audrey Donoho | 2021-06-15 | 2021-06-15 | Audrey Donoho | 2021-05-28 | 2021-05-28 | 0 | TRUE | TRUE
193 | R27-193-6 Research Project Ends | R27-193-6 | Stabilized Support Layers | 26 | R27-193-6: Stabilized Support Layers | FY18-FY24 IGA |  | Audrey Donoho | 2022-02-28 | 2022-02-28 | Audrey Donoho | 2022-02-09 | 2022-02-09 | 0 | TRUE | TRUE
194 | R27-194 Research Project Ends | R27-194 | Steel Bridges | 77 | R27-194: Steel Bridges | Open |  | Brian Lorbiecki | 2026-06-30 | 2026-06-30 | Brian Lorbiecki |  |  | 0 | TRUE | FALSE
195 | R27-195 Research Project Ends | R27-195 | Reversible Lanes | 31 | R27-195: Reversible Lanes | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-10-31 | 2021-10-31 | Brian Lorbiecki | 2021-09-14 | 2021-09-14 | 0 | TRUE | TRUE
196 | R27-196-HS Research Project Ends | R27-196-HS | Rheology-Chemical | 31 | R27-196-HS: Rheology-Chemical | FY18-FY24 IGA |  | Audrey Donoho | 2021-06-30 | 2021-06-30 | Audrey Donoho | 2021-06-18 | 2021-06-18 | 0 | TRUE | TRUE
197 | R27-197 Research Project Ends | R27-197 | TEC Bars | 32 | R27-197: TEC Bars | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-01-15 | 2022-01-15 | Brian Lorbiecki | 2022-01-15 | 2022-01-15 | 0 | TRUE | TRUE
198 | R27-198 Research Project Ends | R27-198 | Horizontal Directional Drilling | 30 | R27-198: Horizontal Directional Drilling | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-09-15 | 2021-09-15 | Brian Lorbiecki | 2021-09-02 | 2021-09-02 | 0 | TRUE | TRUE
199 | R27-199 Research Project Ends | R27-199 | Smoother Roads | 26 | R27-199: Smoother Roads | FY18-FY24 IGA |  | Audrey Donoho | 2020-10-15 | 2020-10-15 | Audrey Donoho | 2020-09-11 | 2020-09-11 | 0 | TRUE | TRUE
200 | R27-200 Research Project Ends | R27-200 | Pedestrian Infrastructure | 27 | R27-200: Pedestrian Infrastructure | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-03-15 | 2021-03-15 | Brian Lorbiecki | 2021-03-01 | 2021-03-01 | 0 | TRUE | TRUE
201 | R27-201 Research Project Ends | R27-201 | Older Population | 24 | R27-201: Older Population | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-10-15 | 2020-10-15 | Brian Lorbiecki | 2020-10-13 | 2020-10-13 | 0 | TRUE | TRUE
202 | R27-202 Research Project Ends | R27-202 | Roadway Lighting | 34 | R27-202: Roadway Lighting | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-09-15 | 2021-09-15 | Brian Lorbiecki | 2021-08-07 | 2021-08-07 | 0 | TRUE | TRUE
203 | R27-203 Research Project Ends | R27-203 | Truck Platooning | 24 | R27-203: Truck Platooning | FY18-FY24 IGA |  | Audrey Donoho | 2021-05-31 | 2021-05-31 | Audrey Donoho | 2021-05-14 | 2021-05-14 | 0 | TRUE | TRUE
204 | R27-204 Research Project Ends | R27-204 | HMA | 39 | R27-204: HMA | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-05-31 | 2023-05-31 | Audrey Donoho | 2023-05-15 | 2023-05-15 | 0 | TRUE | TRUE
205 | R27-205 Research Project Ends | R27-205 | Bridge Load Testing | 48 | R27-205: Bridge Load Testing | Complete - IDOT-ICT |  | Brian Lorbiecki | 2024-12-15 | 2024-12-15 | Brian Lorbiecki | 2024-12-02 | 2024-12-02 | 0 | TRUE | TRUE
206 | R27-206 Research Project Ends | R27-206 | High Mast Towers | 43 | R27-206: High Mast Towers | FY18-FY24 IGA |  | Nick York | 2023-10-31 | 2023-10-31 | Nick York [0.00 %] | 2023-10-12 | 2023-10-12 | 0 | TRUE | TRUE
207 | R27-207 Research Project Ends | R27-207 | Solar Panels | 23 | R27-207: Solar Panels | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-08-15 | 2021-08-15 | Brian Lorbiecki | 2021-08-02 | 2021-08-02 | 0 | TRUE | TRUE
208 | R27-208 Research Project Ends | R27-208 | Resistivity | 47 | R27-208: Resistivity | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-08-15 | 2023-08-15 | Brian Lorbiecki [0.00 %] | 2023-08-04 | 2023-08-04 | 0 | TRUE | TRUE
209 | R27-210 Research Project Ends | R27-210 | CPT for Illinois Subsurface | 50 | R27-210: CPT for Illinois Subsurface | FY18-FY24 IGA |  | Brian Lorbiecki | 2024-05-31 | 2024-05-31 | Brian Lorbiecki | 2024-05-15 | 2024-05-15 | 0 | TRUE | TRUE
210 | R27-211 Research Project Ends | R27-211 | Policy and Design for CAV's | 35 | R27-211: Policy and Design for CAV's | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-08-15 | 2022-08-15 | Brian Lorbiecki | 2022-08-15 | 2022-08-15 | 0 | TRUE | TRUE
211 | R27-212 Research Project Ends | R27-212 | Dredge Material | 39 | R27-212: Dredge Material | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-11-30 | 2022-11-30 | Brian Lorbiecki | 2022-11-30 | 2022-11-30 | 0 | TRUE | TRUE
212 | R27-213 Research Project Ends | R27-213 | Concrete Cure Times | 35 | R27-213: Concrete Cure Times | FY18-FY24 IGA |  | Nick York | 2023-09-30 | 2023-09-30 | Nick York | 2023-09-18 | 2023-09-18 | 0 | TRUE | TRUE
213 | R27-214 Research Project Ends | R27-214 | RipRap Phase II | 38 | R27-214: RipRap Phase II | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-06-30 | 2023-06-30 | Brian Lorbiecki [0.00 %] | 2023-06-30 | 2023-06-30 | 0 | TRUE | TRUE
214 | R27-215 Research Project Ends | R27-215 | E-Scooters | 23 | R27-215: E-Scooters | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-05-15 | 2022-05-15 | Brian Lorbiecki | 2022-05-04 | 2022-05-04 | 0 | TRUE | TRUE
215 | R27-216 Research Project Ends | R27-216 | SMA | 53 | R27-216: SMA | Open |  | Brian Lorbiecki | 2026-04-30 | 2026-04-30 | Brian Lorbiecki [0.00 %] |  |  | 0 | TRUE | FALSE
216 | R27-217 Research Project Ends | R27-217 | Rideshare Taxation | 18 | R27-217: Rideshare Taxation | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-12-15 | 2021-12-15 | Brian Lorbiecki | 2021-12-06 | 2021-12-06 | 0 | TRUE | TRUE
217 | R27-218 Research Project Ends | R27-218 | Railroad-Highway Tool | 33 | R27-218: Railroad-Highway Tool | FY18-FY24 IGA |  | Nick York | 2023-06-30 | 2023-06-30 | Nick York | 2023-06-12 | 2023-06-12 | 0 | TRUE | TRUE
218 | R27-219 Research Project Ends | R27-219 | Field Curing | 44 | R27-219: Field Curing | FY18-FY24 IGA |  | Nick York | 2023-11-15 | 2023-11-15 | Nick York | 2023-10-27 | 2023-10-27 | 0 | TRUE | TRUE
219 | R27-220 Research Project Ends | R27-220 | Scour Depth Estimation | 63 | R27-220: Scour Depth Estimation | Open |  | Brian Lorbiecki | 2026-10-31 | 2026-10-31 | Brian Lorbiecki |  |  | 0 | TRUE | FALSE
220 | R27-221 Research Project Ends | R27-221 | Chip-Seal | 43 | R27-221: Chip-Seal | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-12-31 | 2023-12-31 | Brian Lorbiecki [0.00 %] | 2023-12-14 | 2023-12-14 | 0 | TRUE | TRUE
221 | R27-222 Research Project Ends | R27-222 | Community Impact | 26 | R27-222: Community Impact | FY18-FY24 IGA |  | Audrey Donoho | 2022-08-15 | 2022-08-15 | Audrey Donoho | 2022-08-04 | 2022-08-04 | 0 | TRUE | TRUE
222 | R27-223 Research Project Ends | R27-223 | CMFs for Contrast Pavement Markings | 28 | R27-223: CMFs for Contrast Pavement Markings | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-08-15 | 2022-08-15 | Brian Lorbiecki | 2022-08-01 | 2022-08-01 | 0 | TRUE | TRUE
223 | R27-224 Research Project Ends | R27-224 | Bridge Deck Crack-Sealing | 29 | R27-224: Bridge Deck Crack-Sealing | FY18-FY24 IGA |  | Audrey Donoho | 2022-06-30 | 2022-06-30 | Audrey Donoho | 2022-06-30 | 2022-06-30 | 0 | TRUE | TRUE
224 | R27-225 Research Project Ends | R27-225 | Damaged Steel Girders | 48 | R27-225: Damaged Steel Girders | Open |  | Brian Lorbiecki | 2026-06-30 | 2026-06-30 | Brian Lorbiecki |  |  | 0 | TRUE | FALSE
225 | R27-226 Research Project Ends | R27-226 | PPC Deck Beams with Transverse Cracks | 44 | R27-226: PPC Deck Beams with Transverse Cracks | Complete - IDOT-ICT |  | Brian Lorbiecki | 2025-05-15 | 2025-05-15 | Brian Lorbiecki | 2025-05-15 | 2025-05-15 | 0 | TRUE | TRUE
226 | R27-227 Research Project Ends | R27-227 | Cold Recycle Treatments | 25 | R27-227: Cold Recycle Treatments | FY18-FY24 IGA |  | Audrey Donoho | 2022-05-15 | 2022-05-15 | Audrey Donoho | 2022-05-06 | 2022-05-06 | 0 | TRUE | TRUE
227 | R27-228 Research Project Ends | R27-228 | Mobility | 25 | R27-228: Mobility | FY18-FY24 IGA |  | Nick York | 2023-06-15 | 2023-06-15 | Nick York [0.00 %] | 2023-06-05 | 2023-06-05 | 0 | TRUE | TRUE
228 | R27-229 Research Project Ends | R27-229 | Erosion Control Blankets | 28 | R27-229: Erosion Control Blankets | FY18-FY24 IGA |  | Nick York | 2023-12-15 | 2023-12-15 | Nick York | 2023-11-21 | 2023-11-21 | 0 | TRUE | TRUE
229 | R27-230 Research Project Ends | R27-230 | CRCP Performance and Design | 29 | R27-230: CRCP Performance and Design | FY18-FY24 IGA |  | Brian Lorbiecki | 2024-05-31 | 2024-05-31 | Brian Lorbiecki [0.00 %] | 2024-05-14 | 2024-05-14 | 0 | TRUE | TRUE
230 | R27-231 Research Project Ends | R27-231 | Airfield Pavements | 24 | R27-231: Airfield Pavements | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-08-15 | 2023-08-15 | Audrey Donoho | 2023-08-01 | 2023-08-01 | 0 | TRUE | TRUE
231 | R27-232 Research Project Ends | R27-232 | UHPC | 33 | R27-232: UHPC | Complete - IDOT-ICT |  | Brian Lorbiecki | 2024-09-30 | 2024-09-30 | Brian Lorbiecki | 2024-09-17 | 2024-09-17 | 0 | TRUE | TRUE
232 | R27-233 Research Project Ends | R27-233 | M-E Design Procedures | 31 | R27-233: M-E Design Procedures | FY18-FY24 IGA |  | Brian Lorbiecki | 2024-05-15 | 2024-05-15 | Brian Lorbiecki [0.00 %] | 2024-05-13 | 2024-05-13 | 0 | TRUE | TRUE
233 | R27-234 Research Project Ends | R27-234 | Bender Elements | 35 | R27-234: Bender Elements | Complete - IDOT-ICT |  | Brian Lorbiecki | 2025-06-30 | 2025-06-30 | Brian Lorbiecki [0.00 %] | 2025-06-30 | 2025-06-30 | 0 | TRUE | TRUE
234 | R27-235 Research Project Ends | R27-235 | Cement-treated Base Pavements | 28 | R27-235: Cement-treated Base Pavements | FY18-FY24 IGA |  | Brian Lorbiecki | 2024-06-30 | 2024-06-30 | Brian Lorbiecki [0.00 %] | 2024-06-10 | 2024-06-10 | 0 | TRUE | TRUE
235 | R27-236 Research Project Ends | R27-236 | EV Charging | 21 | R27-236: EV Charging | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-12-31 | 2022-12-31 | Brian Lorbiecki | 2022-12-15 | 2022-12-15 | 0 | TRUE | TRUE
236 | R27-238 Research Project Ends | R27-238 | Deterioration Curves | 29 | R27-238: Deterioration Curves | FY18-FY24 IGA |  | Brian Lorbiecki | 2024-02-29 | 2024-02-29 | Brian Lorbiecki | 2024-02-20 | 2024-02-20 | 0 | TRUE | TRUE
237 | R27-239 Research Project Ends | R27-239 | Commercial Vehicle Emission | 30 | R27-239: Commercial Vehicle Emission | FY18-FY24 IGA |  | Nick York | 2024-02-15 | 2024-02-15 | Nick York [0.00 %] | 2024-02-01 | 2024-02-01 | 0 | TRUE | TRUE
238 | R27-240 Research Project Ends | R27-240 | Low Traffic Volume Roadways | 28 | R27-240: Low Traffic Volume Roadways | FY18-FY24 IGA |  | Nick York | 2023-08-31 | 2023-08-31 | Nick York [0.00 %] | 2023-08-22 | 2023-08-22 | 0 | TRUE | TRUE | [8 empty] | Arudi Rajagopal
239 | R27-241 Research Project Ends | R27-241 | Air Mobility | 27 | R27-241: Air Mobility | FY18-FY24 IGA |  | Nick York | 2024-02-29 | 2024-02-29 | Nick York [0.00 %] | 2024-02-27 | 2024-02-27 | 0 | TRUE | TRUE
240 | R27-242 Research Project Ends | R27-242 | Accelerated Bridge Construction | 24 | R27-242: Accelerated Bridge Construction | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-08-15 | 2023-08-15 | Brian Lorbiecki | 2023-07-20 | 2023-07-20 | 0 | TRUE | TRUE
241 | R27-244 Research Project Ends | R27-244 | MWD | 48 | R27-244: MWD | Open |  | Brian Lorbiecki | 2027-03-31 | 2027-03-31 | Brian Lorbiecki |  |  | 0 | TRUE | FALSE
242 | R27-245-HS Research Project Ends | R27-245-HS | Rumble Strip Designs | 36 | R27-245-HS: Rumble Strip Designs | Complete - IDOT-ICT |  | Nick York | 2024-11-30 | 2024-11-30 | Nick York | 2024-11-13 | 2024-11-13 | 0 | TRUE | TRUE
243 | R27-246 Research Project Ends | R27-246 | Smart Work Zones | 21 | R27-246: Smart Work Zones | FY18-FY24 IGA |  | Nick York | 2024-01-31 | 2024-01-31 | Nick York [0.00 %] | 2024-01-11 | 2024-01-11 | 0 | TRUE | TRUE
244 | R27-247 Research Project Ends | R27-247 | Surface Friction | 44 | R27-247: Surface Friction | Open |  | Brian Lorbiecki | 2026-09-30 | 2026-09-30 | Brian Lorbiecki [0.00 %] |  |  | 0 | TRUE | FALSE
245 | R27-248 Research Project Ends | R27-248 | Dolomite Aggregate | 35 | R27-248: Dolomite Aggregate | Complete - IDOT-ICT |  | Brian Lorbiecki | 2025-12-31 | 2025-12-31 | Brian Lorbiecki [0.00 %] | 2025-12-12 | 2025-12-12 | 0 | TRUE | TRUE
246 | R27-249 Research Project Ends | R27-249 | Mobile RWIS Phase 2 | 33 | R27-249: Mobile RWIS Phase 2 | Open |  | Nick York | 2026-06-30 | 2026-06-30 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
247 | R27-250 Research Project Ends | R27-250 | Delta G | 35 | R27-250: Delta G | Published - IDOT-ICT |  | Brian Lorbiecki | 2025-10-31 | 2025-10-31 | Brian Lorbiecki [0.00 %] | 2025-10-22 | 2025-10-22 | 0 | TRUE | TRUE
248 | R27-251 Research Project Ends | R27-251 | Traffic Signals | 25 | R27-251: Traffic Signals | Complete - IDOT-ICT |  | Nick York | 2024-08-15 | 2024-08-15 | Nick York [0.00 %] | 2024-08-01 | 2024-08-01 | 0 | TRUE | TRUE
249 | R27-252 Research Project Ends | R27-252 | Increased Torque | 33 | R27-252: Increased Torque | Complete - IDOT-ICT |  | Brian Lorbiecki | 2025-05-15 | 2025-05-15 | Brian Lorbiecki [0.00 %] | 2025-05-15 | 2025-05-15 | 0 | TRUE | TRUE
250 | R27-254 Research Project Ends | R27-254 | Equipment Rental | 32 | R27-254: Equipment Rental | Complete - IDOT-ICT |  | Nick York | 2026-01-15 | 2026-01-15 | Nick York | 2026-01-15 | 2026-01-15 | 0 | TRUE | TRUE
251 | R27-255 Research Project Ends | R27-255 | Seeding Standards | 31 | R27-255: Seeding Standards | Complete - IDOT-ICT |  | Nick York | 2025-06-15 | 2025-06-15 | Nick York | 2025-05-21 | 2025-05-21 | 0 | TRUE | TRUE
252 | R27-256 Research Project Ends | R27-256 | Work Zone Training | 16 | R27-256: Work Zone Training | FY18-FY24 IGA |  | Nick York | 2023-11-30 | 2023-11-30 | Nick York | 2023-11-07 | 2023-11-07 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
253 | R27-257 Research Project Ends | R27-257 | Seismic Events | 29 | R27-257: Seismic Events | Open |  | Brian Lorbiecki | 2026-10-31 | 2026-10-31 | Brian Lorbiecki [0.00 %] |  |  | 0 | TRUE | FALSE
254 | R27-258 Research Project Ends | R27-258 | Digital Alert Systems | 36 | R27-258: Digital Alert Systems | Published - IDOT-ICT |  | Nick York | 2026-02-28 | 2026-02-28 | Nick York [0.00 %] | 2026-02-20 | 2026-02-20 | 0 | TRUE | TRUE
255 | R27-259 Research Project Ends | R27-259 | Transit Signal Priority | 22 | R27-259: Transit Signal Priority | Complete - IDOT-ICT |  | Nick York | 2025-06-30 | 2025-06-30 | Nick York [0.00 %] | 2025-06-03 | 2025-06-03 | 0 | TRUE | TRUE
256 | R27-260 Research Project Ends | R27-260 | TEC Rebars | 31 | R27-260: TEC Rebars | Open |  | Brian Lorbiecki | 2026-12-15 | 2026-12-15 | Brian Lorbiecki [0.00 %] |  |  | 0 | TRUE | FALSE
257 | R27-262 Research Project Ends | R27-262 | Geotech Asset Management | 35 | R27-262: Geotech Asset Management | Open |  | Brian Lorbiecki | 2026-08-15 | 2026-08-15 | Brian Lorbiecki [0.00 %] |  |  | 0 | TRUE | FALSE
258 | R27-263 Research Project Ends | R27-263 | Profiler Certification | 25 | R27-263: Profiler Certification | Open |  | Brian Lorbiecki | 2026-07-31 | 2026-07-31 | Brian Lorbiecki [0.00 %] |  |  | 0 | TRUE | FALSE
259 | R27-264 Research Project Ends | R27-264 | Friction Management | 35 | R27-264: Friction Management | Open |  | Brian Lorbiecki | 2026-05-31 | 2026-05-31 | Brian Lorbiecki [0.00 %] |  |  | 0 | TRUE | FALSE
260 | R27-265 Research Project Ends | R27-265 | Integral Abutment Testing | 28 | R27-265: Integral Abutment Testing | Open |  | Brian Lorbiecki | 2026-12-31 | 2026-12-31 | ICT Project Management |  |  | 0 | TRUE | FALSE
261 | R27-266 Research Project Ends | R27-266 | Energy Harvesting | 27 | R27-266: Energy Harvesting | Open |  | Brian Lorbiecki | 2026-12-15 | 2026-12-15 | ICT Project Management |  |  | 0 | TRUE | FALSE
262 | R27-267 Research Project Ends | R27-267 | Flexible Pavement | 30 | R27-267: Flexible Pavement | Open |  | Brian Lorbiecki | 2027-06-30 | 2027-06-30 | ICT Project Management |  |  | 0 | TRUE | FALSE
263 | R27-268 Research Project Ends | R27-268 | Quarry By-Product Fines | 24 | R27-268: Quarry By-Product Fines | Open |  | Brian Lorbiecki | 2026-08-15 | 2026-08-15 | ICT Project Management |  |  | 0 | TRUE | FALSE
264 | R27-269 Research Project Ends | R27-269 | Weigh-In-Motion | 30 | R27-269: Weigh-In-Motion | Open |  | Brian Lorbiecki | 2027-08-15 | 2027-08-15 | Brian Lorbiecki [0.00 %] |  |  | 0 | TRUE | FALSE
265 | R27-270 Research Project Ends | R27-270 | Traffic Control Devices | 29 | R27-270: Traffic Control Devices | Open |  | Nick York | 2026-12-31 | 2026-12-31 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
266 | R27-271 Research Project Ends | R27-271 | Air Quality Screening | 26 | R27-271: Air Quality Screening | Open |  | Nick York | 2027-02-15 | 2027-02-15 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
267 | R27-272 Research Project Ends | R27-272 | Gray Areas | 30 | R27-272: Gray Areas | Open |  | Nick York | 2027-08-15 | 2027-08-15 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
268 | R27-273 Research Project Ends | R27-273 | Emissions Transparency | 30 | R27-273: Emissions Transparency | Open |  | Nick York | 2027-08-15 | 2027-08-15 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
269 | R27-274 Research Project Ends | R27-274 | Free and Reduced Fares | 29 | R27-274: Free and Reduced Fares | Open |  | Nick York | 2026-12-31 | 2026-12-31 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
270 | R27-275 Research Project Ends | R27-275 | Seismic Ground Motions | 28 | R27-275: Seismic Ground Motions | Open |  | Brian Lorbiecki | 2028-08-15 | 2028-08-15 | ICT Project Management |  |  | 0 | TRUE | FALSE
271 | R27-276 Research Project Ends | R27-276 | TCE Alternatives | 30 | R27-276: TCE Alternatives | Open |  | Brian Lorbiecki | 2026-09-30 | 2026-09-30 | ICT Project Management |  |  | 0 | TRUE | FALSE
272 | R27-277 Research Project Ends | R27-277 | Traffic Factor Equations | 24 | R27-277: Traffic Factor Equations | Open |  | Brian Lorbiecki | 2027-06-30 | 2027-06-30 | ICT Project Management |  |  | 0 | TRUE | FALSE
273 | R27-278 Research Project Ends | R27-278 | Aggregate Materials Requirements | 28 | R27-278: Aggregate Materials Requirements | Open |  | Brian Lorbiecki | 2028-08-15 | 2028-08-15 | ICT Project Management |  |  | 0 | TRUE | FALSE
274 | R27-279 Research Project Ends | R27-279 | SER Phase II | 19 | R27-279: SER Phase II | Open |  | Nick York | 2027-06-30 | 2027-06-30 | ICT Project Management |  |  | 0 | TRUE | FALSE
275 | R27-280 Research Project Ends | R27-280 | EV Charging Network | 19 | R27-280: EV Charging Network | Open |  | Nick York | 2028-06-30 | 2028-06-30 | ICT Project Management |  |  | 0 | TRUE | FALSE
276 | R27-281 Research Project Ends | R27-281 | IL-Pave | 29 | R27-281: IL-Pave | Open |  | Brian Lorbiecki | 2028-08-15 | 2028-08-15 | ICT Project Management |  |  | 0 | TRUE | FALSE
277 | R27-282 Research Project Ends | R27-282 | Wearable Safety Lights | 23 | R27-282: Wearable Safety Lights | Open |  | Nick York | 2027-08-15 | 2027-08-15 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
278 | R27-283 Research Project Ends | R27-283 | Right Turn on Red | 21 | R27-283: Right Turn on Red | Open |  | Nick York | 2027-02-15 | 2027-02-15 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
279 | R27-284 Research Project Ends | R27-284 | MPO Performance Measures | 23 | R27-284: MPO Performance Measures | Open |  | Nick York | 2027-08-15 | 2027-08-15 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
280 | R27-285 Research Project Ends | R27-285 | Traffic Projection Tool | 23 | R27-285: Traffic Projection Tool | Open |  | Nick York | 2027-08-15 | 2027-08-15 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
281 | R27-286 Research Project Ends | R27-286 | ATV/UTV Ordinanaces | 21 | R27-286: ATV/UTV Ordinanaces | Open |  | Nick York | 2027-02-15 | 2027-02-15 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
282 | R27-287 Research Project Ends | R27-287 | UHPC Scalability and Implementation | 29 | R27-287: UHPC Scalability and Implementation | Open |  | Brian Lorbiecki | 2028-08-15 | 2028-08-15 | ICT Project Management |  |  | 0 | TRUE | FALSE
283 | R27-288 Research Project Ends | R27-288 | IL Pavement Feedback System | 22 | R27-288: IL Pavement Feedback System | Open |  | Brian Lorbiecki | 2028-02-29 | 2028-02-29 | ICT Project Management |  |  |  | TRUE | FALSE
284 | R27-289 Research Project Ends | R27-289 | Air Voids | 28 | R27-289: Air Voids | Pending - IDOT-ICT |  | Brian Lorbiecki | 2029-04-30 | 2029-04-30 | ICT Project Management |  |  |  | TRUE | FALSE
285 | R27-290 Research Project Ends | R27-290 | AI for Bridge Management | 22 | R27-290: AI for Bridge Management | Pending - IDOT-ICT |  | Brian Lorbiecki | 2028-05-15 | 2028-05-15 | ICT Project Management |  |  |  | TRUE | FALSE
286 | R27-291 Research Project Ends | R27-291 | CRS Calculation Models | 28 | R27-291: CRS Calculation Models | Pending - IDOT-ICT |  | Brian Lorbiecki | 2029-08-15 | 2029-08-15 | ICT Project Management |  |  |  | TRUE | FALSE
287 | R27-292 Research Project Ends | R27-292 | CRS for Pavement Treatments | 22 | R27-292: CRS for Pavement Treatments | Pending - IDOT-ICT |  | Brian Lorbiecki | 2028-05-15 | 2028-05-15 | ICT Project Management |  |  |  | TRUE | FALSE
288 | R27-293 Research Project Ends | R27-293 | LLM-STARS | 29 | R27-293: LLM-STARS | Pending - IDOT-ICT |  | Nick York | 2030-07-10 | 2030-07-10 | Nick York [0.00 %] |  |  |  | TRUE | FALSE
289 | R27-294 Research Project Ends | R27-294 | Congestion Pricing | 27 | R27-294: Congestion Pricing | Pending - IDOT-ICT |  | Nick York | 2028-08-16 | 2028-08-16 | Nick York [0.00 %] |  |  |  | TRUE | FALSE
290 | R27-295 Research Project Ends | R27-295 | Mussel Movement | 27 | R27-295: Mussel Movement | Pending - IDOT-ICT |  | Nick York | 2030-08-15 | 2030-08-15 | Nick York [0.00 %] |  |  |  | TRUE | FALSE
291 | R27-296 Research Project Ends | R27-296 | C1157 Hydraulic Cements | 28 | R27-296: C1157 Hydraulic Cements | Pending - IDOT-ICT |  | Brian Lorbiecki | 2029-08-15 | 2029-08-15 | ICT Project Management |  |  |  | TRUE | FALSE
292 | R27-ALS Research Project Ends | R27-ALS | ATLAS Repairs and Upgrades | 32 | R27-ALS: ATLAS Repairs and Upgrades | Complete - IDOT-ICT |  | Kristi Anderson | 2024-08-31 | 2024-08-31 | Kristi Anderson | 2024-08-31 | 2024-08-31 | 0 | TRUE | TRUE
293 | R27-ET2 (FY18-24 IGA) Research Project Ends | R27-ET2 (FY18-24 IGA) | R27-ET2 (FY18-24 IGA) | 31 | R27-ET2 (FY18-24 IGA): R27-ET2 (FY18-24 IGA) | FY18-FY24 IGA |  | Kristi Anderson | 2024-06-30 | 2024-06-30 | Kristi Anderson | 2024-06-30 | 2024-06-30 | 0 | TRUE | TRUE
294 | R27-ET2 (FY25-30 IGA) Research Project Ends | R27-ET2 (FY25-30 IGA) | R27-ET2 (FY25-30 IGA) | 27 | R27-ET2 (FY25-30 IGA): R27-ET2 (FY25-30 IGA) | Open |  | Nick York | 2030-06-30 | 2030-06-30 | Kristi Anderson [0.00 %] |  |  | 0 | TRUE | FALSE
295 | R27-PC (FY18-24 IGA) Research Project Ends | R27-PC (FY18-24 IGA) | R27-PC (FY18-24 IGA) | 31 | R27-PC (FY18-24 IGA): R27-PC (FY18-24 IGA) | FY18-FY24 IGA |  | Kristi Anderson | 2024-06-30 | 2024-06-30 | Kristi Anderson | 2024-06-30 | 2024-06-30 | 0 | TRUE | TRUE
296 | R27-PC (FY25-30 IGA) Research Project Ends | R27-PC (FY25-30 IGA) | R27-PC (FY25-30 IGA) | 27 | R27-PC (FY25-30 IGA): R27-PC (FY25-30 IGA) | Open |  | Nick York | 2030-06-30 | 2030-06-30 | Kristi Anderson [0.00 %] |  |  | 0 | TRUE | FALSE
297 | R27-RDI (FY18-24 IGA) Research Project Ends | R27-RDI (FY18-24 IGA) | R27-RDI (FY18-24 IGA) | 31 | R27-RDI (FY18-24 IGA): R27-RDI (FY18-24 IGA) | FY18-FY24 IGA |  | Kristi Anderson | 2024-06-30 | 2024-06-30 | Kristi Anderson | 2024-06-30 | 2024-06-30 | 0 | TRUE | TRUE
298 | R27-RDI (FY25-30 IGA) Research Project Ends | R27-RDI (FY25-30 IGA) | R27-RDI (FY25-30 IGA) | 27 | R27-RDI (FY25-30 IGA): R27-RDI (FY25-30 IGA) | Open |  | Nick York | 2030-06-30 | 2030-06-30 | Kristi Anderson [0.00 %] |  |  | 0 | TRUE | TRUE
299 | R27-SP# (FY06-08 IGA) Research Project Ends | R27-SP# (FY06-08 IGA) | R27-SP# (FY06-08 IGA) | 2 | R27-SP# (FY06-08 IGA): R27-SP# (FY06-08 IGA) | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management | 2008-06-30 | 2008-06-30 | 0 | TRUE | TRUE
300 | R27-SP# (FY09-11 IGA) Research Project Ends | R27-SP# (FY09-11 IGA) | R27-SP# (FY09-11 IGA) | 2 | R27-SP# (FY09-11 IGA): R27-SP# (FY09-11 IGA) | FY09-FY11 IGA |  | Brian Lorbiecki | 2011-06-30 | 2011-06-30 | ICT Project Management | 2011-06-30 | 2011-06-30 | 0 | TRUE | TRUE
301 | R27-SP01 Research Project Ends | R27-SP01 | Median Cable Scanning Tour | 2 | R27-SP01: Median Cable Scanning Tour | FY06-FY08 IGA |  | Nick York | 2006-01-31 | 2006-01-31 | ICT Project Management [0.00 %] | 2006-01-01 | 2006-01-01 | 0 | TRUE | TRUE
302 | R27-SP02 Research Project Ends | R27-SP02 | Chicago Bridge Columns | 2 | R27-SP02: Chicago Bridge Columns | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2006-03-05 | 2006-03-05 | 0 | TRUE | TRUE
303 | R27-SP03 Research Project Ends | R27-SP03 | Profile Equipment Verification FY06 | 2 | R27-SP03: Profile Equipment Verification FY06 | FY06-FY08 IGA |  | Nick York | 2006-06-30 | 2006-06-30 | ICT Project Management [0.00 %] | 2006-06-30 | 2006-06-30 | 0 | TRUE | TRUE
304 | R27-SP04 Research Project Ends | R27-SP04 | Highway Maintenance Manpower | 2 | R27-SP04: Highway Maintenance Manpower | FY06-FY08 IGA |  | Nick York | 2007-06-30 | 2007-06-30 | ICT Project Management [0.00 %] | 2007-06-30 | 2007-06-30 | 0 | TRUE | TRUE
305 | R27-SP05 Research Project Ends | R27-SP05 | Profile Equipment Verification FY07 | 2 | R27-SP05: Profile Equipment Verification FY07 | FY06-FY08 IGA |  | Nick York | 2007-06-30 | 2007-06-30 | ICT Project Management [0.00 %] | 2007-06-30 | 2007-06-30 | 0 | TRUE | TRUE
306 | R27-SP06 Research Project Ends | R27-SP06 | Cracking in Pavement | 2 | R27-SP06: Cracking in Pavement | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2008-06-30 | 2008-06-30 | 0 | TRUE | TRUE
307 | R27-SP07 Research Project Ends | R27-SP07 | Reinforced Concrete Structures | 2 | R27-SP07: Reinforced Concrete Structures | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2008-06-30 | 2008-06-30 | 0 | TRUE | TRUE
308 | R27-SP08 Research Project Ends | R27-SP08 | Wireless Internet Service on Trains | 2 | R27-SP08: Wireless Internet Service on Trains | FY06-FY08 IGA |  | Nick York | 2007-12-31 | 2007-12-31 | ICT Project Management [0.00 %] | 2007-12-31 | 2007-12-31 | 0 | TRUE | TRUE
309 | R27-SP09 Research Project Ends | R27-SP09 | Profile Equipment Verification 2008 | 2 | R27-SP09: Profile Equipment Verification 2008 | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2008-06-30 | 2008-06-30 | 0 | TRUE | TRUE
310 | R27-SP10 Research Project Ends | R27-SP10 | Online Training Course Prototype | 2 | R27-SP10: Online Training Course Prototype | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2008-08-31 | 2008-08-31 | 0 | TRUE | TRUE
311 | R27-SP11 Research Project Ends | R27-SP11 | Recycled CRCP Cores | 2 | R27-SP11: Recycled CRCP Cores | FY09-FY11 IGA |  | Nick York | 2008-09-30 | 2008-09-30 | ICT Project Management [0.00 %] | 2008-09-30 | 2008-09-30 | 0 | TRUE | TRUE
312 | R27-SP12 Research Project Ends | R27-SP12 | Bridge Collapse Investigation | 3 | R27-SP12: Bridge Collapse Investigation | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-05-15 | 2009-05-15 | ICT Project Management | 2009-04-01 | 2009-04-01 | 0 | TRUE | TRUE
313 | R27-SP13 Research Project Ends | R27-SP13 | Profile Equipment Verification 2009 | 3 | R27-SP13: Profile Equipment Verification 2009 | FY09-FY11 IGA |  | Nick York | 2010-06-30 | 2010-06-30 | ICT Project Management [0.00 %] | 2010-06-30 | 2010-06-30 | 0 | TRUE | TRUE
314 | R27-SP14 Research Project Ends | R27-SP14 | Retroreflective Sign Sheeting | 3 | R27-SP14: Retroreflective Sign Sheeting | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-09-30 | 2009-09-30 | ICT Project Management | 2010-03-01 | 2010-03-01 | 0 | TRUE | TRUE
315 | R27-SP15 Research Project Ends | R27-SP15 | Snowplow Simulator Training | 3 | R27-SP15: Snowplow Simulator Training | FY09-FY11 IGA |  | Nick York | 2010-09-30 | 2010-09-30 | ICT Project Management [0.00 %] | 2011-01-01 | 2011-01-01 | 0 | TRUE | TRUE
316 | R27-SP16 Research Project Ends | R27-SP16 | Horizontal Directional Drilling Eval | 3 | R27-SP16: Horizontal Directional Drilling Eval | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-08-15 | 2010-08-15 | ICT Project Management | 2011-11-01 | 2011-11-01 | 0 | TRUE | TRUE
317 | R27-SP17 Research Project Ends | R27-SP17 | Warm Mix Asphalt Study | 3 | R27-SP17: Warm Mix Asphalt Study | FY09-FY11 IGA |  | Nick York | 2010-07-31 | 2010-07-31 | ICT Project Management [0.00 %] | 2011-06-01 | 2011-06-01 | 0 | TRUE | TRUE
318 | R27-SP18 Research Project Ends | R27-SP18 | Bicycle Trail | 9 | R27-SP18: Bicycle Trail | FY12-FY17 IGA |  | AKSHITI MODI | 2012-06-30 | 2012-06-30 | ICT Project Management | 2012-06-30 | 2012-06-30 | 0 | TRUE | TRUE
319 | R27-SP19 Research Project Ends | R27-SP19 | Effect of RAS | 12 | R27-SP19: Effect of RAS | FY12-FY17 IGA |  | ICT Project Management | 2012-06-15 | 2012-06-15 | ICT Project Management | 2012-06-15 | 2012-06-15 | 0 | TRUE | TRUE
320 | R27-SP20 Research Project Ends | R27-SP20 | Signal Control Technologies | 12 | R27-SP20: Signal Control Technologies | FY12-FY17 IGA |  | AKSHITI MODI | 2012-12-15 | 2012-12-15 | ICT Project Management | 2012-12-15 | 2012-12-15 | 0 | TRUE | TRUE
321 | R27-SP21 Research Project Ends | R27-SP21 | COSIM | 14 | R27-SP21: COSIM | FY12-FY17 IGA |  | Nick York | 2013-04-30 | 2013-04-30 | ICT Project Management | 2013-06-01 | 2013-06-01 | 0 | TRUE | TRUE
322 | R27-SP22 Research Project Ends | R27-SP22 | HPMS Sample Counting | 19 | R27-SP22: HPMS Sample Counting | FY12-FY17 IGA |  | Nick York | 2014-04-30 | 2014-04-30 | ICT Project Management | 2014-04-30 | 2014-04-30 | 0 | TRUE | TRUE
323 | R27-SP23 Research Project Ends | R27-SP23 | Drainage Laws | 16 | R27-SP23: Drainage Laws | FY12-FY17 IGA |  | Nick York | 2014-07-31 | 2014-07-31 | ICT Project Management | 2014-07-31 | 2014-07-31 | 0 | TRUE | TRUE
324 | R27-SP24 Research Project Ends | R27-SP24 | TrafficTurk Evaluation | 12 | R27-SP24: TrafficTurk Evaluation | FY12-FY17 IGA |  | Nick York | 2014-02-15 | 2014-02-15 | ICT Project Management | 2014-04-01 | 2014-04-01 | 0 | TRUE | TRUE
325 | R27-SP25 Research Project Ends | R27-SP25 | Local Roadway Safety Assessments | 13 | R27-SP25: Local Roadway Safety Assessments | FY12-FY17 IGA |  | Nick York | 2014-04-30 | 2014-04-30 | ICT Project Management | 2015-02-26 | 2015-02-26 | 0 | TRUE | TRUE
326 | R27-SP26-C Research Project Ends | R27-SP26-C | Alternative Deicers | 15 | R27-SP26-C: Alternative Deicers | FY12-FY17 IGA |  | Nick York | 2014-11-30 | 2014-11-30 | ICT Project Management | 2016-01-25 | 2016-01-25 | 0 | TRUE | TRUE
327 | R27-SP27 Research Project Ends | R27-SP27 | AIMS Implementation | 15 | R27-SP27: AIMS Implementation | FY12-FY17 IGA |  | AKSHITI MODI | 2015-02-28 | 2015-02-28 | ICT Project Management | 2015-02-28 | 2015-02-28 | 0 | TRUE | TRUE
328 | R27-SP28 Research Project Ends | R27-SP28 | PG Asphalts ReOB | 13 | R27-SP28: PG Asphalts ReOB | FY12-FY17 IGA |  | AKSHITI MODI | 2016-02-15 | 2016-02-15 | ICT Project Management | 2016-02-15 | 2016-02-15 | 0 | TRUE | TRUE
329 | R27-SP29 Research Project Ends | R27-SP29 | Thermodynamics | 12 | R27-SP29: Thermodynamics | FY12-FY17 IGA |  | AKSHITI MODI | 2015-10-31 | 2015-10-31 | ICT Project Management | 2015-10-31 | 2015-10-31 | 0 | TRUE | TRUE
330 | R27-SP30 Research Project Ends | R27-SP30 | Speed Harmonization | 17 | R27-SP30: Speed Harmonization | FY12-FY17 IGA |  | AKSHITI MODI | 2016-10-15 | 2016-10-15 | ICT Project Management | 2016-10-25 | 2016-10-25 | 0 | TRUE | TRUE
331 | R27-SP31 Research Project Ends | R27-SP31 | Evaluation of I-FIT Results | 13 | R27-SP31: Evaluation of I-FIT Results | FY12-FY17 IGA |  | AKSHITI MODI | 2017-06-30 | 2017-06-30 | ICT Project Management | 2017-06-30 | 2017-06-30 | 0 | TRUE | TRUE
332 | R27-SP32 Research Project Ends | R27-SP32 | Red Light Running Cameras | 14 | R27-SP32: Red Light Running Cameras | FY12-FY17 IGA |  | AKSHITI MODI | 2017-04-15 | 2017-04-15 | ICT Project Management | 2017-04-15 | 2017-04-15 | 0 | TRUE | TRUE
333 | R27-SP33 Research Project Ends | R27-SP33 | Red Light Running Cameras | 12 | R27-SP33: Red Light Running Cameras | FY12-FY17 IGA |  | Nick York | 2017-04-15 | 2017-04-15 | ICT Project Management | 2018-01-26 | 2018-01-26 | 0 | TRUE | TRUE
334 | R27-SP34 Research Project Ends | R27-SP34 | Shear Tack | 14 | R27-SP34: Shear Tack | FY18-FY24 IGA |  | Brian Lorbiecki | 2017-12-31 | 2017-12-31 | Brian Lorbiecki | 2017-12-21 | 2017-12-21 | 0 | TRUE | TRUE
335 | R27-SP35 Research Project Ends | R27-SP35 | Textured Rebar | 18 | R27-SP35: Textured Rebar | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-04-30 | 2018-04-30 | Brian Lorbiecki | 2018-04-25 | 2018-04-25 | 0 | TRUE | TRUE
336 | R27-SP36 Research Project Ends | R27-SP36 | AIMS-MD | 13 | R27-SP36: AIMS-MD | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-05-31 | 2018-05-31 | Brian Lorbiecki | 2018-05-16 | 2018-05-16 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
337 | R27-SP37-C Research Project Ends | R27-SP37-C | Speed Limits | 17 | R27-SP37-C: Speed Limits | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-08-31 | 2018-08-31 | Audrey Donoho | 2018-08-16 | 2018-08-16 | 0 | TRUE | TRUE
338 | R27-SP38 Research Project Ends | R27-SP38 | QBP Durability | 14 | R27-SP38: QBP Durability | FY18-FY24 IGA |  | Audrey Donoho | 2019-10-31 | 2019-10-31 | Audrey Donoho | 2019-10-23 | 2019-10-23 | 0 | TRUE | TRUE
339 | R27-SP39 Research Project Ends | R27-SP39 | Hybrid Beacons | 13 | R27-SP39: Hybrid Beacons | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-09-15 | 2019-09-15 | Brian Lorbiecki | 2019-09-05 | 2019-09-05 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
340 | R27-SP40 Research Project Ends | R27-SP40 | Distracted Driving | 18 | R27-SP40: Distracted Driving | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-04-30 | 2020-04-30 | Brian Lorbiecki | 2020-04-13 | 2020-04-13 | 0 | TRUE | TRUE
341 | R27-SP41 Research Project Ends | R27-SP41 | Small Cells | 12 | R27-SP41: Small Cells | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-01-31 | 2020-01-31 | Brian Lorbiecki | 2020-01-27 | 2020-01-27 | 0 | TRUE | TRUE
342 | R27-SP42 Research Project Ends | R27-SP42 | Bridge Beams | 14 | R27-SP42: Bridge Beams | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-08-15 | 2020-08-15 | Brian Lorbiecki | 2020-08-03 | 2020-08-03 | 0 | TRUE | TRUE
343 | R27-SP43 Research Project Ends | R27-SP43 | Quarry By-products | 17 | R27-SP43: Quarry By-products | FY18-FY24 IGA |  | Audrey Donoho | 2021-06-30 | 2021-06-30 | Audrey Donoho | 2021-06-07 | 2021-06-07 | 0 | TRUE | TRUE
344 | R27-SP44 Research Project Ends | R27-SP44 | HMA Potholes | 17 | R27-SP44: HMA Potholes | FY18-FY24 IGA |  | Audrey Donoho | 2021-02-28 | 2021-02-28 | Audrey Donoho | 2021-02-22 | 2021-02-22 | 0 | TRUE | TRUE
345 | R27-SP45 Research Project Ends | R27-SP45 | Transit System Ridership | 16 | R27-SP45: Transit System Ridership | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-09-15 | 2021-09-15 | Brian Lorbiecki | 2021-09-15 | 2021-09-15 | 0 | TRUE | TRUE
346 | R27-SP46 Research Project Ends | R27-SP46 | Bridge Deterioration | 16 | R27-SP46: Bridge Deterioration | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-09-30 | 2021-09-30 | Brian Lorbiecki | 2021-09-09 | 2021-09-09 | 0 | TRUE | TRUE
347 | R27-SP47 Research Project Ends | R27-SP47 | Mobile Road Weather | 16 | R27-SP47: Mobile Road Weather | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-02-28 | 2022-02-28 | Brian Lorbiecki | 2022-02-28 | 2022-02-28 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
348 | R27-SP48 Research Project Ends | R27-SP48 | Longitudinal Cracking | 17 | R27-SP48: Longitudinal Cracking | FY18-FY24 IGA |  | Audrey Donoho | 2022-02-28 | 2022-02-28 | Audrey Donoho | 2022-02-04 | 2022-02-04 | 0 | TRUE | TRUE
349 | R27-SP49 Research Project Ends | R27-SP49 | Corrosion on Bridge Decks | 16 | R27-SP49: Corrosion on Bridge Decks | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-05-16 | 2022-05-16 | Brian Lorbiecki | 2022-05-16 | 2022-05-16 | 0 | TRUE | TRUE
350 | R27-SP50 Research Project Ends | R27-SP50 | Bridge Safety | 16 | R27-SP50: Bridge Safety | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-05-31 | 2022-05-31 | Brian Lorbiecki | 2022-05-17 | 2022-05-17 | 0 | TRUE | TRUE |  | 36000 |  |  | 27000 |  | 27000 | 36000
351 | R27-SP51-HS Research Project Ends | R27-SP51-HS | Transverse Rumble Strips | 17 | R27-SP51-HS: Transverse Rumble Strips | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-06-30 | 2022-06-30 | Brian Lorbiecki | 2022-06-15 | 2022-06-15 | 0 | TRUE | TRUE
352 | R27-SP52 Research Project Ends | R27-SP52 | Corrosion on Bridge Decks Phase II | 18 | R27-SP52: Corrosion on Bridge Decks Phase II | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-05-15 | 2023-05-15 | Brian Lorbiecki | 2023-05-02 | 2023-05-02 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
353 | R27-SP53 Research Project Ends | R27-SP53 | Transit Ridership Analysis | 16 | R27-SP53: Transit Ridership Analysis | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-04-15 | 2023-04-15 | Nick York | 2023-04-05 | 2023-04-05 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
354 | R27-SP55 Research Project Ends | R27-SP55 | Dynamic Messaging | 18 | R27-SP55: Dynamic Messaging | FY18-FY24 IGA |  | Nick York | 2024-05-31 | 2024-05-31 | Nick York [0.00 %] | 2024-05-22 | 2024-05-22 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
355 | R27-SP56 Research Project Ends | R27-SP56 | RAP in Pavement Preservation | 14 | R27-SP56: RAP in Pavement Preservation | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-10-31 | 2023-10-31 | Brian Lorbiecki [0.00 %] | 2023-10-31 | 2023-10-31 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
356 | R27-SP57 Research Project Ends | R27-SP57 | Transit Vehicle Technician Needs | 15 | R27-SP57: Transit Vehicle Technician Needs | FY18-FY24 IGA |  | Nick York | 2024-06-30 | 2024-06-30 | Nick York | 2024-06-18 | 2024-06-18 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
357 | R27-SP58 Research Project Ends | R27-SP58 | IDOT Maintenance Needs | 14 | R27-SP58: IDOT Maintenance Needs | FY18-FY24 IGA |  | Nick York | 2023-12-31 | 2023-12-31 | Nick York | 2023-12-13 | 2023-12-13 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
358 | R27-SP59 Research Project Ends | R27-SP59 | Asphalt Replacement Credits | 18 | R27-SP59: Asphalt Replacement Credits | FY18-FY24 IGA |  | Nick York | 2024-05-31 | 2024-05-31 | Nick York | 2024-05-14 | 2024-05-14 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
359 | R27-SP61 Research Project Ends | R27-SP61 | Wetland Mitigation | 14 | R27-SP61: Wetland Mitigation | FY18-FY24 IGA |  | Nick York | 2024-02-15 | 2024-02-15 | Nick York | 2024-02-05 | 2024-02-05 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
360 | R27-SP62 Research Project Ends | R27-SP62 | Bridge Deck Crack Sealing | 18 | R27-SP62: Bridge Deck Crack Sealing | FY18-FY24 IGA |  | Brian Lorbiecki | 2024-03-31 | 2024-03-31 | Brian Lorbiecki | 2024-03-01 | 2024-03-01 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
361 | R27-SP63 Research Project Ends | R27-SP63 | MSCR | 15 | R27-SP63: MSCR | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-12-31 | 2023-12-31 | Brian Lorbiecki [0.00 %] | 2023-12-11 | 2023-12-11 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
362 | R27-SP64 Research Project Ends | R27-SP64 | Endangered Species | 14 | R27-SP64: Endangered Species | FY18-FY24 IGA |  | Nick York | 2024-02-15 | 2024-02-15 | Nick York | 2024-02-01 | 2024-02-01 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
363 | R27-SP65 Research Project Ends | R27-SP65 | Low-Clearance Early Warning Devices | 17 | R27-SP65: Low-Clearance Early Warning Devices | Complete - IDOT-ICT |  | Nick York | 2024-07-31 | 2024-07-31 | Nick York | 2024-07-11 | 2024-07-11 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
364 | R27-SP66 Research Project Ends | R27-SP66 | Anti-Graffiti | 16 | R27-SP66: Anti-Graffiti | Complete - IDOT-ICT |  | Brian Lorbiecki | 2024-10-15 | 2024-10-15 | Brian Lorbiecki [0.00 %] | 2024-10-08 | 2024-10-08 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
365 | R27-SP67 Research Project Ends | R27-SP67 | Minimizing Impacts to Aquatic Resources | 17 | R27-SP67: Minimizing Impacts to Aquatic Resources | Complete - IDOT-ICT |  | Nick York | 2025-05-15 | 2025-05-15 | Nick York [0.00 %] | 2025-05-02 | 2025-05-02 | 0 | TRUE | TRUE
366 | R27-SP68 Research Project Ends | R27-SP68 | Rusty Patched Bumblebee | 21 | R27-SP68: Rusty Patched Bumblebee | Complete - IDOT-ICT |  | Nick York | 2025-11-30 | 2025-11-30 | Nick York [0.00 %] | 2025-11-17 | 2025-11-17 | 0 | TRUE | TRUE
367 | R27-SP69 Research Project Ends | R27-SP69 | Specialized Management Areas | 16 | R27-SP69: Specialized Management Areas | Complete - IDOT-ICT |  | Nick York | 2025-06-30 | 2025-06-30 | Nick York [0.00 %] | 2025-06-30 | 2025-06-30 | 0 | TRUE | TRUE
368 | R27-SP70 Research Project Ends | R27-SP70 | Wildlife Crossings | 15 | R27-SP70: Wildlife Crossings | Complete - IDOT-ICT |  | Nick York | 2025-06-30 | 2025-06-30 | Nick York [0.00 %] | 2025-06-05 | 2025-06-05 | 0 | TRUE | TRUE
369 | R27-SP71 Research Project Ends | R27-SP71 | Target Speeds | 17 | R27-SP71: Target Speeds | Complete - IDOT-ICT |  | Nick York | 2024-12-15 | 2024-12-15 | Nick York | 2024-12-03 | 2024-12-03 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
370 | R27-SP72 Research Project Ends | R27-SP72 | Roller Compacted Concrete | 20 | R27-SP72: Roller Compacted Concrete | Complete - IDOT-ICT |  | Brian Lorbiecki | 2025-10-31 | 2025-10-31 | Brian Lorbiecki [0.00 %] | 2025-10-10 | 2025-10-10 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | 0
371 | R27-SP74 Research Project Ends | R27-SP74 | Concrete Overlays | 16 | R27-SP74: Concrete Overlays | Complete - IDOT-ICT |  | Brian Lorbiecki | 2025-09-30 | 2025-09-30 | Brian Lorbiecki [0.00 %] | 2025-09-30 | 2025-09-30 | 0 | TRUE | TRUE
372 | R27-SP75 Research Project Ends | R27-SP75 | Pavement Temperature Measurement System | 18 | R27-SP75: Pavement Temperature Measurement System | Open |  | Brian Lorbiecki | 2026-08-31 | 2026-08-31 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE
373 | R27-SP76 Research Project Ends | R27-SP76 | Temporary Sign Support Systems | 16 | R27-SP76: Temporary Sign Support Systems | Open |  | Nick York | 2026-05-31 | 2026-05-31 | Nick York [0.00 %] |  |  | 0 | TRUE | FALSE
374 | R27-SP77 Research Project Ends | R27-SP77 | UAS 3D Bridge Inspection | 16 | R27-SP77: UAS 3D Bridge Inspection | Open |  | Brian Lorbiecki | 2026-09-15 | 2026-09-15 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE
375 | R27-SP78 Research Project Ends | R27-SP78 | Concrete Strength Sensing | 18 | R27-SP78: Concrete Strength Sensing | Open |  | Brian Lorbiecki | 2026-08-31 | 2026-08-31 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE
376 | R27-SP79 Research Project Ends | R27-SP79 | Aquatic Species Bridge PA | 15 | R27-SP79: Aquatic Species Bridge PA | Open |  | Nick York | 2026-07-15 | 2026-07-15 | Nick York [0.00 %] |  |  |  | TRUE | FALSE
377 | R27-SP80 Research Project Ends | R27-SP80 | Freeze-Thaw Chambers Data | 15 | R27-SP80: Freeze-Thaw Chambers Data | Pending - IDOT-ICT |  | Brian Lorbiecki | 2026-12-31 | 2026-12-31 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE
378 | R27-SP81 Research Project Ends | R27-SP81 | Audible Warnings | 15 | R27-SP81: Audible Warnings | Open |  | Nick York | 2026-11-30 | 2026-11-30 | Nick York [0.00 %] |  |  |  | TRUE | FALSE
379 | R27-SP82 Research Project Ends | R27-SP82 | Oxidation of Pavement Preservation | 15 | R27-SP82: Oxidation of Pavement Preservation | Pending - IDOT-ICT |  | Brian Lorbiecki | 2027-02-28 | 2027-02-28 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE
380 | R27-SP83 Research Project Ends | R27-SP83 | Ladle Slag | 15 | R27-SP83: Ladle Slag | Open |  | Brian Lorbiecki | 2026-11-30 | 2026-11-30 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE
381 | R28-001 Research Project Ends | R28-001 | Flexible Pavements (Ended 6/08) | 3 | R28-001: Flexible Pavements (Ended 6/08) | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2008-06-30 | 2008-06-30 | 0 | TRUE | TRUE
382 | R28-002 Research Project Ends | R28-002 | Binder / Mixture Testing & Analysis | 2 | R28-002: Binder / Mixture Testing & Analysis | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-08-31 | 2008-08-31 | ICT Project Management | 2008-08-31 | 2008-08-31 | 0 | TRUE | TRUE
383 | R39-001 Research Project Ends | R39-001 | Extended Life HMA Pavement Design | 3 | R39-001: Extended Life HMA Pavement Design | FY06-FY08 IGA |  | Nick York | 2006-12-31 | 2006-12-31 | ICT Project Management [0.00 %] | 2008-07-01 | 2008-07-01 | 0 | TRUE | TRUE
384 | R39-002 Research Project Ends | R39-002 | Nondestructive Pavement Evaluation | 3 | R39-002: Nondestructive Pavement Evaluation | FY09-FY11 IGA |  | Nick York | 2008-08-31 | 2008-08-31 | ICT Project Management [0.00 %] | 2008-09-01 | 2008-09-01 | 0 | TRUE | TRUE
385 | R43 Research Project Ends | R43 | Traffic Operations Lab | 2 | R43: Traffic Operations Lab | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2009-05-01 | 2009-05-01 | 0 | TRUE | TRUE
386 | R44 Research Project Ends | R44 | Self-Consolidating Concrete | 3 | R44: Self-Consolidating Concrete | FY06-FY08 IGA |  | Nick York | 2007-09-15 | 2007-09-15 | ICT Project Management [0.00 %] | 2008-07-01 | 2008-07-01 | 0 | TRUE | TRUE
387 | R53 Research Project Ends | R53 | Concrete Distress Identification | 3 | R53: Concrete Distress Identification | FY06-FY08 IGA |  | Nick York | 2006-06-30 | 2006-06-30 | ICT Project Management [0.00 %] | 2006-07-17 | 2006-07-17 | 0 | TRUE | TRUE
388 | R54 Research Project Ends | R54 | Lifting Loops in Shallow Precast Deck Beams | 3 | R54: Lifting Loops in Shallow Precast Deck Beams | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-09-30 | 2008-09-30 | ICT Project Management | 2009-08-01 | 2009-08-01 | 0 | TRUE | TRUE
389 | R55 Research Project Ends | R55 | Tack Coat Optimization | 4 | R55: Tack Coat Optimization | FY09-FY11 IGA |  | Nick York | 2008-12-31 | 2008-12-31 | ICT Project Management [0.00 %] | 2009-02-01 | 2009-02-01 | 0 | TRUE | TRUE
390 | R56 Research Project Ends | R56 | Speed Photo-Enforcement | 3 | R56: Speed Photo-Enforcement | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management [0.00 %] | 2010-01-01 | 2010-01-01 | 0 | TRUE | TRUE
391 | R57 Research Project Ends | R57 | CRCP and JPCP Design | 3 | R57: CRCP and JPCP Design | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-12-31 | 2008-12-31 | ICT Project Management | 2009-07-01 | 2009-07-01 | 0 | TRUE | TRUE
392 | R58 Research Project Ends | R58 | Reflective Crack Control | 5 | R58: Reflective Crack Control | FY09-FY11 IGA |  | Nick York | 2008-12-31 | 2008-12-31 | ICT Project Management [0.00 %] | 2009-05-01 | 2009-05-01 | 0 | TRUE | TRUE
393 | R59 Research Project Ends | R59 | Pavement Damage | 3 | R59: Pavement Damage | FY09-FY11 IGA |  | Nick York | 2008-12-31 | 2008-12-31 | ICT Project Management [0.00 %] | 2009-05-01 | 2009-05-01 | 0 | TRUE | TRUE
394 | R60-ADMIN (FY06-08 IGA) Research Project Ends | R60-ADMIN (FY06-08 IGA) | R60-ADMIN (FY06-08 IGA) | 2 | R60-ADMIN (FY06-08 IGA): R60-ADMIN (FY06-08 IGA) | FY06-FY08 IGA |  | Nick York | 2008-06-30 | 2008-06-30 | ICT Project Management | 2008-06-30 | 2008-06-30 | 0 | TRUE | TRUE
395 | R60-ADMIN (FY09-11 IGA) Research Project Ends | R60-ADMIN (FY09-11 IGA) | R60-ADMIN (FY09-11 IGA) | 2 | R60-ADMIN (FY09-11 IGA): R60-ADMIN (FY09-11 IGA) | FY09-FY11 IGA |  | Audrey Donoho | 2011-06-30 | 2011-06-30 | ICT Project Management | 2011-06-30 | 2011-06-30 | 0 | TRUE | TRUE
396 | R60-ADMIN (FY12-17 IGA) Research Project Ends | R60-ADMIN (FY12-17 IGA) | R60-ADMIN (FY12-17 IGA) | 23 | R60-ADMIN (FY12-17 IGA): R60-ADMIN (FY12-17 IGA) | FY12-FY17 IGA |  | Audrey Donoho | 2017-06-30 | 2017-06-30 | ICT Project Management | 2017-06-30 | 2017-06-30 | 0 | TRUE | TRUE
397 | R60-ADMIN (FY18-24 IGA) Research Project Ends | R60-ADMIN (FY18-24 IGA) | R60-ADMIN (FY18-24 IGA) | 42 | R60-ADMIN (FY18-24 IGA): R60-ADMIN (FY18-24 IGA) | FY18-FY24 IGA |  | Kristi Anderson | 2024-06-30 | 2024-06-30 | Kristi Anderson | 2024-06-30 | 2024-06-30 | 0 | TRUE | TRUE
398 | R60-ADMIN (FY25-30 IGA) Research Project Ends | R60-ADMIN (FY25-30 IGA) | R60-ADMIN (FY25-30 IGA) | 46 | R60-ADMIN (FY25-30 IGA): R60-ADMIN (FY25-30 IGA) | Open |  | Nick York | 2030-06-30 | 2030-06-30 | Kristi Anderson [0.00 %] |  |  | 0 | TRUE | FALSE

## PM.com Start lines
| Task Name | Project ID | Project Title | WBS | Project Name | Project Status | Customer | Project Manager | Planned Start Date | Planned Finish Date | Person | Actual Start Date | Actual Finish Date | Actual Cost | Milestone | Complete | Tags | Current Project Budget | Budgeted Engineering Hours | TRP Chair(s) | Current IDOT Budget | Research Conducted By | Original IDOT Budget | Original Project Budget | PI | TAG | Actual Engineering Hours
0 | R27-001 Research Project Start! | R27-001 | Char. IL Aggregates Subgrade/Subbase | 1 | R27-001: Char. IL Aggregates Subgrade/Subbase | FY09-FY11 IGA |  | Brian Lorbiecki | 2006-01-01 | 2006-01-01 | ICT Project Management | 2006-01-01 | 2006-01-01 | 430678 | TRUE | TRUE | PI Direct | 399101 |  | Riyad Wahab | 299329 |  | 258599 | 344799 | Erol Tutumluer | PVMT
1 | R27-002 Research Project Start! | R27-002 | Lighting Glare | 1 | R27-002: Lighting Glare | FY06-FY08 IGA |  | Nick York | 2006-01-01 | 2006-01-01 | ICT Project Management [0.00 %] | 2006-01-01 | 2006-01-01 | 186724 | TRUE | TRUE | PI Direct | 223573 |  | Dennis Huckaba | 141164 |  | 137498 | 218684 | Khaled El-Rayes | SAF
2 | R27-003 Research Project Start! | R27-003 | Ultra-Thin Whitetopping | 1 | R27-003: Ultra-Thin Whitetopping | FY06-FY08 IGA |  | Nick York | 2006-01-01 | 2006-01-01 | ICT Project Management [0.00 %] | 2006-01-01 | 2006-01-01 | 263052 | TRUE | TRUE | PI Direct | 247685 |  | James Krstulovich | 185764 |  | 173155 | 230872 | Jeffery Roesler | PVMT
3 | R27-004 Research Project Start! | R27-004 | Radiation Detection | 1 | R27-004: Radiation Detection | FY06-FY08 IGA |  | Nick York | 2006-01-01 | 2006-01-01 | ICT Project Management [0.00 %] | 2006-01-01 | 2006-01-01 | 37407 | TRUE | TRUE | PI Direct | 59789 |  | Joseph Hill | 44842 |  | 44842 | 59789 | William Dunn | OPS
4 | R27-005 Research Project Start! | R27-005 | Bus-Only Shoulder Riding | 1 | R27-005: Bus-Only Shoulder Riding | FY09-FY11 IGA |  | Nick York | 2007-08-16 | 2007-08-16 | ICT Project Management [0.00 %] | 2007-08-16 | 2007-08-16 | 96025 | TRUE | TRUE | PI Direct | 90603 |  | Charles Abraham | 67952 |  | 67952 | 90603 | Vonu Thakuriah | MFM
5 | R27-006 Research Project Start! | R27-006 | Illinois StreamStats | 1 | R27-006: Illinois StreamStats | FY06-FY08 IGA |  | Nick York | 2006-03-01 | 2006-03-01 | ICT Project Management [0.00 %] | 2006-03-01 | 2006-03-01 | 85160 | TRUE | TRUE | PI Direct | 120000 |  | Matthew O'Connor | 60000 |  | 45000 | 90000 | David Soong | BAF
6 | R27-007 Research Project Start! | R27-007 | Carbon Monoxide Screen | 1 | R27-007: Carbon Monoxide Screen | FY06-FY08 IGA |  | Nick York | 2007-02-01 | 2007-02-01 | ICT Project Management [0.00 %] | 2007-02-01 | 2007-02-01 | 17661 | TRUE | TRUE | PI Direct | 22181 |  | Walt Zyznieuski | 16635 |  | 16635 | 22181 | Scott Peters | ENV
7 | R27-008 Research Project Start! | R27-008 | Hot Mix Asphalt | 1 | R27-008: Hot Mix Asphalt | FY06-FY08 IGA |  | Nick York | 2006-06-01 | 2006-06-01 | ICT Project Management [0.00 %] | 2006-06-01 | 2006-06-01 | 15608 | TRUE | TRUE | PI Direct | 22100 |  | Jim Trepanier | 16550 |  | 16550 | 22100 | Mostafa Elseifi | PVMT
8 | R27-009 Research Project Start! | R27-009 | Kishwaukee Bridge Monitoring | 1 | R27-009: Kishwaukee Bridge Monitoring | FY06-FY08 IGA |  | Nick York | 2006-07-01 | 2006-07-01 | ICT Project Management [0.00 %] | 2006-07-01 | 2006-07-01 | 142801 | TRUE | TRUE | PI Direct | 133849 |  | Todd Ahrens | 101738 |  | 101738 | 133849 | Ming Wang | BAF
9 | R27-010 Research Project Start! | R27-010 | Mobile Source Air Toxics | 1 | R27-010: Mobile Source Air Toxics | FY06-FY08 IGA |  | Nick York | 2006-07-01 | 2006-07-01 | ICT Project Management [0.00 %] | 2006-07-01 | 2006-07-01 | 36329 | TRUE | TRUE | PI Direct | 50266 |  | Walt Zyznieuski | 37679 |  | 37679 | 50266 | Jane Lin | ENV
10 | R27-011 Research Project Start! | R27-011 | Residual Asphalt Binder in RAP | 1 | R27-011: Residual Asphalt Binder in RAP | FY06-FY08 IGA |  | Nick York | 2006-07-01 | 2006-07-01 | ICT Project Management [0.00 %] | 2006-07-01 | 2006-07-01 | 222235 | TRUE | TRUE | PI Direct | 210340 |  | Jim Trepanier | 157738 |  | 157738 | 133919 | Imad Al-Qadi | PVMT
11 | R27-012 Research Project Start! | R27-012 | CI & FDRwAP | 1 | R27-012: CI & FDRwAP | FY09-FY11 IGA |  | Brian Lorbiecki | 2006-07-01 | 2006-07-01 | ICT Project Management | 2006-07-01 | 2006-07-01 | 159675 | TRUE | TRUE | PI Direct | 150000 |  | Kevin Burke | 112500 |  | 112500 | 150000 | Marshall Thompson | PVMT
12 | R27-013 Research Project Start! | R27-013 | Calculation/Prediction Models | 1 | R27-013: Calculation/Prediction Models | FY06-FY08 IGA |  | Nick York | 2006-07-01 | 2006-07-01 | ICT Project Management [0.00 %] | 2006-07-01 | 2006-07-01 | 94853 | TRUE | TRUE | PI Direct | 139874 |  | David Felts | 104905 |  | 104905 | 139874 | Laura Heckel | PLAN
13 | R27-014 Research Project Start! | R27-014 | Commercial Vehicle Information Systems | 1 | R27-014: Commercial Vehicle Information Systems | FY06-FY08 IGA |  | Nick York | 2006-09-06 | 2006-09-06 | ICT Project Management [0.00 %] | 2006-09-06 | 2006-09-06 | 49070 | TRUE | TRUE | PI Direct | 69297 |  | Charles Sikaras | 51942 |  | 51942 | 69297 | Peter Nelson | PLAN
14 | R27-015 Research Project Start! | R27-015 | Regional Warehouse Trip Production | 1 | R27-015: Regional Warehouse Trip Production | FY09-FY11 IGA |  | Nick York | 2007-01-01 | 2007-01-01 | ICT Project Management [0.00 %] | 2007-01-01 | 2007-01-01 | 70853 | TRUE | TRUE | PI Direct | 66667 |  | Charles Abraham | 50000 |  | 50000 | 66667 | Jon Devries | MFM
15 | R27-016 Research Project Start! | R27-016 | Truck Parking Facilities | 1 | R27-016: Truck Parking Facilities | FY06-FY08 IGA |  | Nick York | 2007-01-01 | 2007-01-01 | ICT Project Management [0.00 %] | 2007-01-01 | 2007-01-01 | 27779 | TRUE | TRUE | PI Direct | 56132 |  | Charles Abraham | 40000 |  | 40000 | 56132 | Peter Beltemacchi | MFM
16 | R27-017 Research Project Start! | R27-017 | Traffic Strategies Targeting Elderly People | 1 | R27-017: Traffic Strategies Targeting Elderly People | FY09-FY11 IGA |  | Brian Lorbiecki | 2006-07-01 | 2006-07-01 | ICT Project Management | 2006-07-01 | 2006-07-01 | 82987 | TRUE | TRUE | PI Direct | 82500 |  | Charles Abraham | 61875 |  | 61875 | 82500 | Kouros Mohammadian | MFM
17 | R27-018 Research Project Start! | R27-018 | Crash Data Analysis | 1 | R27-018: Crash Data Analysis | FY09-FY11 IGA |  | Nick York | 2006-07-01 | 2006-07-01 | ICT Project Management [0.00 %] | 2006-07-01 | 2006-07-01 | 159675 | TRUE | TRUE | PI Direct | 165001 | 0 | Kevin Burke | 123751 |  | 112500 | 150000 | Yanfeng Ouyang | SAF | 0
18 | R27-019 Research Project Start! | R27-019 | Pier Scour Prediction | 1 | R27-019: Pier Scour Prediction | FY09-FY11 IGA |  | Brian Lorbiecki | 2006-08-01 | 2006-08-01 | ICT Project Management | 2006-08-01 | 2006-08-01 | 360851 | TRUE | TRUE | PI Direct | 352167 |  | Matthew O'Connor | 238000 |  | 233000 | 310667 | Tim Straub | BAF
19 | R27-020 Research Project Start! | R27-020 | Safety Performance Functions | 1 | R27-020: Safety Performance Functions | FY09-FY11 IGA |  | Nick York | 2007-01-01 | 2007-01-01 | ICT Project Management [0.00 %] | 2007-01-01 | 2007-01-01 | 154734 | TRUE | TRUE | PI Direct | 140000 |  | David Piper | 105001 |  | 105001 | 140000 | Yanfeng Ouyang | SAF
20 | R27-021 Research Project Start! | R27-021 | Alternative Intersections | 1 | R27-021: Alternative Intersections | FY09-FY11 IGA |  | Brian Lorbiecki | 2007-01-01 | 2007-01-01 | ICT Project Management | 2007-01-01 | 2007-01-01 | 56870 | TRUE | TRUE | PI Direct | 57824 |  | Sean Coyle | 43368 |  | 40247 | 53663 | Ray Benekohal | SAF
21 | R27-022 Research Project Start! | R27-022 | Regional Data Archiving | 1 | R27-022: Regional Data Archiving | FY09-FY11 IGA |  | Nick York | 2007-04-01 | 2007-04-01 | ICT Project Management [0.00 %] | 2007-04-01 | 2007-04-01 | 79836 | TRUE | TRUE | PI Direct | 150000 |  | John Benda | 56249 |  | 56249 | 150000 | Yanfeng Ouyang | OPS
22 | R27-023 Research Project Start! | R27-023 | HMA Overlays | 1 | R27-023: HMA Overlays | FY09-FY11 IGA |  | Brian Lorbiecki | 2007-07-01 | 2007-07-01 | ICT Project Management | 2007-07-01 | 2007-07-01 | 140855 | TRUE | TRUE | PI Direct | 134940 |  | Jeffrey South | 99240 |  | 99240 | 134940 | Angela Wolters | PLAN
23 | R27-024 Research Project Start! | R27-024 | Foundation Piling Design | 1 | R27-024: Foundation Piling Design | FY09-FY11 IGA |  | Nick York | 2007-01-01 | 2007-01-01 | ICT Project Management [0.00 %] | 2007-01-01 | 2007-01-01 | 161570 | TRUE | TRUE | PI Direct | 158045 |  | Bill Kramer | 118534 |  | 119250 | 159000 | Jim Long | BAF
24 | R27-025 Research Project Start! | R27-025 | Integral Abutment Design | 1 | R27-025: Integral Abutment Design | FY09-FY11 IGA |  | Brian Lorbiecki | 2007-01-01 | 2007-01-01 | ICT Project Management | 2007-01-01 | 2007-01-01 | 127990 | TRUE | TRUE | PI Direct | 119780 |  | Bill Kramer | 89835 |  | 89868 | 119825 | Scott Olson | BAF
25 | R27-026 Research Project Start! | R27-026 | Brass Breakaway Couplings | 1 | R27-026: Brass Breakaway Couplings | FY09-FY11 IGA |  | Nick York | 2007-04-01 | 2007-04-01 | ICT Project Management [0.00 %] | 2007-04-01 | 2007-04-01 | 125884 | TRUE | TRUE | PI Direct | 119647 |  | Chris Hahin | 89735 |  | 89735 | 119647 | Dan Kuchma | BAF
26 | R27-027 Research Project Start! | R27-027 | Reclaimed Asphalt | 1 | R27-027: Reclaimed Asphalt | FY09-FY11 IGA |  | Brian Lorbiecki | 2007-02-01 | 2007-02-01 | ICT Project Management | 2007-02-01 | 2007-02-01 | 79561 | TRUE | TRUE | PI Direct | 75000 |  | Sheila Beshears | 56250 |  | 56250 | 75000 | Erol Tutumluer | PVMT
27 | R27-028-T1 Research Project Start! | R27-028-T1 | Conference and Training Support | 1 | R27-028-T1: Conference and Training Support | FY09-FY11 IGA |  | Nick York | 2007-09-01 | 2007-09-01 | ICT Project Management [0.00 %] | 2007-09-01 | 2007-09-01 | 239813 | TRUE | TRUE | PI Direct | 194025 |  | David Lippert | 145518 |  | 145518 | 194025 | Imad Al-Qadi | Other / Department Wide
28 | R27-028-T2 Research Project Start! | R27-028-T2 | LTAP GIS Software | 1 | R27-028-T2: LTAP GIS Software | FY09-FY11 IGA |  | Brian Lorbiecki | 2007-11-01 | 2007-11-01 | ICT Project Management | 2007-11-01 | 2007-11-01 | 80013 | TRUE | TRUE | PI Direct | 75165 |  | David Lippert | 56374 |  | 56374 | 75165 | Imad Al-Qadi | Other / Department Wide
29 | R27-028-T3 Research Project Start! | R27-028-T3 | Bearing Capacity Conference | 1 | R27-028-T3: Bearing Capacity Conference | FY09-FY11 IGA |  | Nick York | 2009-05-01 | 2009-05-01 | ICT Project Management [0.00 %] | 2009-05-01 | 2009-05-01 | 11250 | TRUE | TRUE | PI Direct | 15000 |  | Amy Schutzbach | 11250 |  | 11250 | 15000 | Erol Tutumluer | PVMT
30 | R27-029 Research Project Start! | R27-029 | Particulate Matter 2.5 | 1 | R27-029: Particulate Matter 2.5 | FY06-FY08 IGA |  | Nick York | 2007-07-01 | 2007-07-01 | ICT Project Management [0.00 %] | 2007-07-01 | 2007-07-01 | 63870 | TRUE | TRUE | PI Direct | 60000 |  | Walt Zyznieuski | 45000 |  | 45000 | 60000 | Jane Lin | ENV
31 | R27-030 Research Project Start! | R27-030 | 3-D Laser Scanning for Constr. | 1 | R27-030: 3-D Laser Scanning for Constr. | FY09-FY11 IGA |  | Brian Lorbiecki | 2007-09-16 | 2007-09-16 | ICT Project Management | 2007-09-16 | 2007-09-16 | 197347 | TRUE | TRUE | PI Direct | 199246 |  | Ted Nemsky | 149452 |  | 150000 | 200000 | Dianne Slattery | CON
32 | R27-031 Research Project Start! | R27-031 | Wind Powered Electrical Systems | 1 | R27-031: Wind Powered Electrical Systems | FY09-FY11 IGA |  | Nick York | 2007-08-01 | 2007-08-01 | ICT Project Management [0.00 %] | 2007-08-01 | 2007-08-01 | 71058 | TRUE | TRUE | PI Direct | 70000 |  | Dave Johnson | 52500 |  | 52500 | 70000 | Patrick Chapman | OPS
33 | R27-032 Research Project Start! | R27-032 | Rolling Lane Closures | 1 | R27-032: Rolling Lane Closures | FY09-FY11 IGA |  | Brian Lorbiecki | 2007-09-01 | 2007-09-01 | ICT Project Management | 2007-09-01 | 2007-09-01 | 105549 | TRUE | TRUE | PI Direct | 103779 |  | Aaron Weatherholt | 75002 |  | 75002 | 100017 | Doug Steele | OPS
34 | R27-033 Research Project Start! | R27-033 | Cost in Highway Work Zones | 1 | R27-033: Cost in Highway Work Zones | FY09-FY11 IGA |  | Nick York | 2007-10-01 | 2007-10-01 | ICT Project Management [0.00 %] | 2007-10-01 | 2007-10-01 | 175363 | TRUE | TRUE | PI Direct | 160000 |  | Marshall Metcalf | 120000 |  | 120000 | 160000 | Ray Benekohal | OPS
35 | R27-034 Research Project Start! | R27-034 | Benefit-Cost Program Planning | 1 | R27-034: Benefit-Cost Program Planning | FY09-FY11 IGA |  | Brian Lorbiecki | 2007-10-01 | 2007-10-01 | ICT Project Management | 2007-10-01 | 2007-10-01 | 88430 | TRUE | TRUE | PI Direct | 80000 |  | Jeffrey South | 60000 |  | 60000 | 80000 | Yanfeng Ouyang | PLAN
36 | R27-035 Research Project Start! | R27-035 | Cost Effective Scour Sensor | 1 | R27-035: Cost Effective Scour Sensor | FY09-FY11 IGA |  | Nick York | 2007-08-01 | 2007-08-01 | ICT Project Management [0.00 %] | 2007-08-01 | 2007-08-01 | 74220 | TRUE | TRUE | PI Direct | 77617 |  | Dave Copenbarger | 52500 |  | 52500 | 77617 | Farhad Ansari | BAF
37 | R27-036 Research Project Start! | R27-036 | Tendons in SCC Girders | 1 | R27-036: Tendons in SCC Girders | FY09-FY11 IGA |  | Brian Lorbiecki | 2007-08-01 | 2007-08-01 | ICT Project Management | 2007-08-01 | 2007-08-01 | 53225 | TRUE | TRUE | PI Direct | 50000 |  | Tom Domagalski | 37500 |  | 37500 | 50000 | Bassem Andrawes | BAF
38 | R27-037 Research Project Start! | R27-037 | High RAP Content on Pavement | 2 | R27-037: High RAP Content on Pavement | FY12-FY17 IGA |  | Nick York | 2008-07-01 | 2008-07-01 | ICT Project Management | 2008-07-01 | 2008-07-01 | 361082 | TRUE | TRUE | PI Direct | 320937 |  | Jim Trepanier | 240702 |  | 225979 | 242411 | Imad Al-Qadi | PVMT
39 | R27-038 Research Project Start! | R27-038 | Concrete Temperatures | 1 | R27-038: Concrete Temperatures | FY09-FY11 IGA |  | Nick York | 2007-09-01 | 2007-09-01 | ICT Project Management [0.00 %] | 2007-09-01 | 2007-09-01 | 263195 | TRUE | TRUE | PI Direct | 247098 |  | Derek Parish | 185323 |  | 185323 | 247098 | John Popovics | PVMT
40 | R27-039 Research Project Start! | R27-039 | Context Sensitive Solns Training | 1 | R27-039: Context Sensitive Solns Training | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-02-16 | 2008-02-16 | ICT Project Management | 2008-02-16 | 2008-02-16 | 47724 | TRUE | TRUE | PI Direct | 50000 |  | Susan Stitt | 37500 |  | 37500 | 50000 | James Hall | PLAN
41 | R27-040 Research Project Start! | R27-040 | Highway Shoulder Attributes | 1 | R27-040: Highway Shoulder Attributes | FY09-FY11 IGA |  | Nick York | 2008-01-01 | 2008-01-01 | ICT Project Management [0.00 %] | 2008-01-01 | 2008-01-01 | 137586 | TRUE | TRUE | PI Direct | 140000 |  | David Piper | 105000 |  | 105000 | 140000 | Zongzhi Li | SAF
42 | R27-041 Research Project Start! | R27-041 | I-57 Recycled Concrete Pvmt. | 1 | R27-041: I-57 Recycled Concrete Pvmt. | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-01-01 | 2008-01-01 | ICT Project Management | 2008-01-01 | 2008-01-01 | 57483 | TRUE | TRUE | PI Direct | 54000 |  | Mark Gawedzinski | 40500 |  | 40500 | 54000 | Jeffery Roesler | PVMT
43 | R27-042 Research Project Start! | R27-042 | High Friction Surface Layer | 2 | R27-042: High Friction Surface Layer | FY12-FY17 IGA |  | Brian Lorbiecki | 2008-03-07 | 2008-03-07 | ICT Project Management | 2008-03-07 | 2008-03-07 | 782070 | TRUE | TRUE | PI Direct | 697405 |  | Tom Zehr | 523054 |  | 371168 | 494890 | Imad Al-Qadi | PVMT
44 | R27-043 Research Project Start! | R27-043 | Utah LTAP GIS Software Conversion | 1 | R27-043: Utah LTAP GIS Software Conversion | FY09-FY11 IGA |  | Nick York | 2007-11-01 | 2007-11-01 | ICT Project Management [0.00 %] | 2007-11-01 | 2007-11-01 | 19812 | TRUE | TRUE | PI Direct | 20000 |  | Kevin Burke | 15000 |  | 15000 | 20000 | Yanfeng Ouyang | Other / Department Wide
45 | R27-044 (FY09-11 IGA) Research Project Start! | R27-044 (FY09-11 IGA) | Tech Transfer (FY09-11 IGA) | 1 | R27-044 (FY09-11 IGA): Tech Transfer (FY09-11 IGA) | FY09-FY11 IGA |  | Audrey Donoho | 2008-07-01 | 2008-07-01 | ICT Project Management | 2008-07-01 | 2008-07-01 | 327880 | TRUE | TRUE | Admin Line Item | 455539 |  | Megan Swanson | 341654 |  | 341654 | 455539 | Imad Al-Qadi | Other / Department Wide
46 | R27-044 (FY12-17 IGA) Research Project Start! | R27-044 (FY12-17 IGA) | Tech Transfer (FY12-17 IGA) | 1 | R27-044 (FY12-17 IGA): Tech Transfer (FY12-17 IGA) | FY12-FY17 IGA |  | Audrey Donoho | 2011-07-01 | 2011-07-01 | ICT Project Management | 2011-07-01 | 2011-07-01 | 1663082 | TRUE | TRUE | Admin Line Item | 1650000 |  | Megan Swanson | 1237500 |  | 1237500 | 1650000 | Imad Al-Qadi | Other / Department Wide
47 | R27-044-T1 Research Project Start! | R27-044-T1 | Pavement Design Course | 2 | R27-044-T1: Pavement Design Course | FY12-FY17 IGA |  | Brian Lorbiecki | 2012-06-01 | 2012-06-01 | ICT Project Management | 2012-06-01 | 2012-06-01 | 143971 | TRUE | TRUE | PI Direct | 150000 |  | Charles Wienrank | 112500 |  | 112500 | 150000 | Hasan Ozer | PVMT
48 | R27-045 (FY09-11 IGA) Research Project Start! | R27-045 (FY09-11 IGA) | IT Support (FY09-11 IGA) | 1 | R27-045 (FY09-11 IGA): IT Support (FY09-11 IGA) | FY09-FY11 IGA |  | Audrey Donoho | 2008-07-01 | 2008-07-01 | ICT Project Management | 2008-07-01 | 2008-07-01 | 356113 | TRUE | TRUE | Admin Line Item | 447603 |  | Megan Swanson | 335702 |  | 335702 | 447603 | Imad Al-Qadi | Other / Department Wide
49 | R27-045 (FY12-17 IGA) Research Project Start! | R27-045 (FY12-17 IGA) | IT Support (FY12-17 IGA) | 1 | R27-045 (FY12-17 IGA): IT Support (FY12-17 IGA) | FY12-FY17 IGA |  | Audrey Donoho | 2011-07-01 | 2011-07-01 | ICT Project Management | 2011-07-01 | 2011-07-01 | 377742 | TRUE | TRUE | Admin Line Item | 1002720 |  | Megan Swanson | 752040 |  | 752040 | 1002720 | Imad Al-Qadi | Other / Department Wide
50 | R27-045-T1 Research Project Start! | R27-045-T1 | Laser Scanner | 2 | R27-045-T1: Laser Scanner | FY18-FY24 IGA |  | ICT Project Management | 2013-10-01 | 2013-10-01 | ICT Project Management | 2013-10-01 | 2013-10-01 | 226522 | TRUE | TRUE | PI Direct | 286102 |  | Ryan Culton | 215121 | In-State University | 147960 | 197280 | Greg Renshaw | CON
51 | R27-046 (FY09-11 IGA) Research Project Start! | R27-046 (FY09-11 IGA) | Special Projects Eng (FY09-11 IGA) | 1 | R27-046 (FY09-11 IGA): Special Projects Eng (FY09-11 IGA) | FY09-FY11 IGA |  | Audrey Donoho | 2008-07-01 | 2008-07-01 | ICT Project Management | 2008-07-01 | 2008-07-01 | 445401 | TRUE | TRUE | Admin Line Item | 480000 |  | Megan Swanson | 360000 |  | 360000 | 480000 | Imad Al-Qadi | Other / Department Wide
52 | R27-046 (FY12-17 IGA) Research Project Start! | R27-046 (FY12-17 IGA) | Special Projects Eng (FY12-17 IGA) | 1 | R27-046 (FY12-17 IGA): Special Projects Eng (FY12-17 IGA) | FY12-FY17 IGA |  | Audrey Donoho | 2011-07-01 | 2011-07-01 | ICT Project Management | 2011-07-01 | 2011-07-01 | 1527269 | TRUE | TRUE | Admin Line Item | 1600000 |  | Megan Swanson | 1200000 |  | 1200000 | 1600000 | Imad Al-Qadi | Other / Department Wide
53 | R27-047 Research Project Cancelled! | R27-047 | Illinois Tribunal Workshop | 2 | R27-047: Illinois Tribunal Workshop | Cancelled |  | Nick York | 2008-05-13 | 2008-05-13 | Nick York [0.00 %] | 2008-05-13 | 2008-05-13 | 0 | TRUE | TRUE | [9 empty] | ENV
54 | R27-048 Research Project Start! | R27-048 | Travel Demand Modeling for IL MPOs | 1 | R27-048: Travel Demand Modeling for IL MPOs | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-01-01 | 2009-01-01 | ICT Project Management | 2009-01-01 | 2009-01-01 | 159652 | TRUE | TRUE | PI Direct | 160000 |  | Susan Stitt | 120000 |  | 120000 | 160000 | Rita Morocoima-Black | PLAN
55 | R27-049 Research Project Start! | R27-049 | Documentation | 1 | R27-049: Documentation | FY09-FY11 IGA |  | Nick York | 2008-05-01 | 2008-05-01 | ICT Project Management [0.00 %] | 2008-05-01 | 2008-05-01 | 197298 | TRUE | TRUE | PI Direct | 200000 |  | Mike Renner | 150000 |  | 150000 | 300000 | Imad Al-Qadi | CON
56 | R27-050 Research Project Start! | R27-050 | Seniors' Trip Chaining Behavior | 1 | R27-050: Seniors' Trip Chaining Behavior | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-08-16 | 2008-08-16 | ICT Project Management | 2008-08-16 | 2008-08-16 | 110887 | TRUE | TRUE | PI Direct | 110887 |  | Charles Abraham | 77675 |  | 72047 | 96063 | Kouros Mohammadian | MFM
57 | R27-051 Research Project Start! | R27-051 | Truck Parking/Rest Facilities | 1 | R27-051: Truck Parking/Rest Facilities | FY09-FY11 IGA |  | Nick York | 2008-11-01 | 2008-11-01 | ICT Project Management [0.00 %] | 2008-11-01 | 2008-11-01 | 77154 | TRUE | TRUE | PI Direct | 80536 |  | Charles Abraham | 59560 |  | 59560 | 80536 | Peter Beltemacchi | MFM
58 | R27-052 Research Project Start! | R27-052 | Traffic Related WZ Crashes | 1 | R27-052: Traffic Related WZ Crashes | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-09-16 | 2008-09-16 | ICT Project Management | 2008-09-16 | 2008-09-16 | 241292 | TRUE | TRUE | PI Direct | 209999 |  | Marshall Metcalf | 157499 |  | 157499 | 209999 | Khaled El-Rayes | SAF
59 | R27-053 Research Project Cancelled! | R27-053 | Roadway Lighting Evaluation Tools | 2 | R27-053: Roadway Lighting Evaluation Tools | Cancelled |  | Nick York | 2008-09-04 | 2008-09-04 | Nick York [0.00 %] | 2008-09-04 | 2008-09-04 | 0 | TRUE | TRUE | [9 empty] | SAF
60 | R27-054 Research Project Start! | R27-054 | Storm Water P. E.&S. | 3 | R27-054: Storm Water P. E.&S. | FY12-FY17 IGA |  | Nick York | 2009-01-01 | 2009-01-01 | ICT Project Management | 2009-01-01 | 2009-01-01 | 532380 | TRUE | TRUE | RFP | 499229 |  | Joe Vespa | 374422 |  | 337500 | 450000 | Prasanta Kalita | ENV
61 | R27-055 Research Project Start! | R27-055 | Integral Abutment Bridges | 2 | R27-055: Integral Abutment Bridges | FY12-FY17 IGA |  | AKSHITI MODI | 2008-08-16 | 2008-08-16 | ICT Project Management | 2008-08-16 | 2008-08-16 | 285982 | TRUE | TRUE | PI Direct | 362999 |  | Bill Kramer | 272249 |  | 247499 | 330000 | Scott Olson | BAF
62 | R27-056 Research Project Start! | R27-056 | Prestressed SCC Girders | 1 | R27-056: Prestressed SCC Girders | FY09-FY11 IGA |  | Nick York | 2008-07-16 | 2008-07-16 | ICT Project Management [0.00 %] | 2008-07-16 | 2008-07-16 | 204324 | TRUE | TRUE | PI Direct | 190000 |  | Tom Domagalski | 142500 |  | 142500 | 190000 | Bassem Andrawes | BAF
63 | R27-057 Research Project Start! | R27-057 | Fibrous Additives | 3 | R27-057: Fibrous Additives | FY12-FY17 IGA |  | AKSHITI MODI | 2009-01-01 | 2009-01-01 | ICT Project Management | 2009-01-01 | 2009-01-01 | 165804 | TRUE | TRUE | RFP | 160000 |  | Gary Kowalski | 120000 |  | 120000 | 160000 | Mohammad Alhassan | BAF
64 | R27-058 Research Project Start! | R27-058 | Wireless Detection Systems Eval | 1 | R27-058: Wireless Detection Systems Eval | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-07-01 | 2008-07-01 | ICT Project Management | 2008-07-01 | 2008-07-01 | 256877 | TRUE | TRUE | PI Direct | 219624 |  | Yogesh Gautam | 164718 |  | 164718 | 219624 | Ray Benekohal | OPS
65 | R27-059 Research Project Start! | R27-059 | Solar Powered Flashing Beacons | 1 | R27-059: Solar Powered Flashing Beacons | FY09-FY11 IGA |  | Nick York | 2008-07-01 | 2008-07-01 | ICT Project Management [0.00 %] | 2008-07-01 | 2008-07-01 | 258061 | TRUE | TRUE | PI Direct | 218925 |  | Yogesh Gautam | 164194 |  | 164194 | 218925 | Ray Benekohal | OPS
66 | R27-060 Research Project Start! | R27-060 | Flexible Pavements (Mechanistic) | 2 | R27-060: Flexible Pavements (Mechanistic) | FY12-FY17 IGA |  | Brian Lorbiecki | 2008-07-01 | 2008-07-01 | ICT Project Management | 2008-07-01 | 2008-07-01 | 438622 | TRUE | TRUE | PI Direct | 484158 |  | Charles Wienrank | 363118 |  | 183118 | 207992 | Marshall Thompson | PVMT
67 | R27-061 Research Project Start! | R27-061 | Rigid Pavements | 2 | R27-061: Rigid Pavements | FY12-FY17 IGA |  | AKSHITI MODI | 2009-01-01 | 2009-01-01 | ICT Project Management | 2009-01-01 | 2009-01-01 | 517489 | TRUE | TRUE | PI Direct | 488675 |  | Charles Wienrank | 366506 |  | 347022 | 236260 | Jeffery Roesler | PVMT
68 | R27-062 Research Project Start! | R27-062 | Material Quality Testing & Peer Exchange | 1 | R27-062: Material Quality Testing & Peer Exchange | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-02-01 | 2009-02-01 | ICT Project Management | 2009-02-01 | 2009-02-01 | 93750 | TRUE | TRUE | PI Direct | 110934 |  | David Lippert | 83200 |  | 71201 | 94934 | Tim Murphy | PVMT
69 | R27-063 Research Project Start! | R27-063 | Joints Cut Using Early-Entry Saws | 1 | R27-063: Joints Cut Using Early-Entry Saws | FY09-FY11 IGA |  | Nick York | 2008-11-01 | 2008-11-01 | ICT Project Management [0.00 %] | 2008-11-01 | 2008-11-01 | 94730 | TRUE | TRUE | PI Direct | 94574 |  | Mark Gawedzinski | 70930 |  | 65123 | 86831 | Thomas Dam | PVMT
70 | R27-064 Research Project Start! | R27-064 | Incident Mgmt Operational/Training Guide | 1 | R27-064: Incident Mgmt Operational/Training Guide | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-07-01 | 2009-07-01 | ICT Project Management | 2009-07-01 | 2009-07-01 | 149318 | TRUE | TRUE | PI Direct | 136400 |  | Geno Koehler | 102011 |  | 102011 | 136400 | Huaguo Zhou | OPS
71 | R27-065 Research Project Cancelled! | R27-065 | Safety Analyst Study | 2 | R27-065: Safety Analyst Study | Cancelled |  | Nick York | 2009-09-11 | 2009-09-11 | Nick York [0.00 %] | 2009-09-11 | 2009-09-11 | 0 | TRUE | TRUE | [9 empty] | SAF
72 | R27-066 Research Project Start! | R27-066 | IL Speed Enforcement Techniques | 2 | R27-066: IL Speed Enforcement Techniques | FY12-FY17 IGA |  | AKSHITI MODI | 2009-11-01 | 2009-11-01 | ICT Project Management | 2009-11-01 | 2009-11-01 | 314232 | TRUE | TRUE | PI Direct | 300397 |  | Paul Lorton | 225000 |  | 224654 | 300397 | Hani Mahmassani | SAF
73 | R27-067 Research Project Start! | R27-067 | National Safety Performance Summit | 1 | R27-067: National Safety Performance Summit | FY09-FY11 IGA |  | Nick York | 2009-01-01 | 2009-01-01 | ICT Project Management [0.00 %] | 2009-01-01 | 2009-01-01 | 102474 | TRUE | TRUE | PI Direct | 100000 |  | Priscilla Tobias | 75000 |  | 75000 | 100000 | Yanfeng Ouyang | SAF
74 | R27-068 Research Project Start! | R27-068 | Midwest Air Quality Summit | 1 | R27-068: Midwest Air Quality Summit | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-03-16 | 2009-03-16 | ICT Project Management | 2009-03-16 | 2009-03-16 | 46467 | TRUE | TRUE | PI Direct | 45513 |  | Walt Zyznieuski | 34135 |  | 52500 | 70000 | Michael Koerber | ENV
75 | R27-069 Research Project Start! | R27-069 | Pile Load Test | 2 | R27-069: Pile Load Test | FY12-FY17 IGA |  | AKSHITI MODI | 2009-01-01 | 2009-01-01 | ICT Project Management | 2009-01-01 | 2009-01-01 | 405571 | TRUE | TRUE | PI Direct | 457091 |  | Bill Kramer | 342818 |  | 309999 | 413333 | Jim Long | BAF
76 | R27-070 Research Project Start! | R27-070 | Earthquake Resisting System | 2 | R27-070: Earthquake Resisting System | FY12-FY17 IGA |  | AKSHITI MODI | 2009-01-01 | 2009-01-01 | ICT Project Management | 2009-01-01 | 2009-01-01 | 786244 | TRUE | TRUE | PI Direct | 750080 |  | Dan Tobias | 562560 |  | 562560 | 625000 | James LaFave | BAF
77 | R27-071 Research Project Start! | R27-071 | Bridge Scour Sensor - Phase 2 | 1 | R27-071: Bridge Scour Sensor - Phase 2 | FY09-FY11 IGA |  | Nick York | 2009-02-01 | 2009-02-01 | ICT Project Management [0.00 %] | 2009-02-01 | 2009-02-01 | 190892 | TRUE | TRUE | PI Direct | 215267 |  | Dave Copenbarger | 161450 |  | 123000 | 164000 | Farhad Ansari | BAF
78 | R27-072 Research Project Start! | R27-072 | Rolling Lane Closures - Phase II | 1 | R27-072: Rolling Lane Closures - Phase II | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-01-16 | 2009-01-16 | ICT Project Management | 2009-01-16 | 2009-01-16 | 175000 | TRUE | TRUE | PI Direct | 175000 |  | Aaron Weatherholt | 131250 |  | 131250 | 175000 | Doug Steele | OPS
79 | R27-073 Research Project Start! | R27-073 | Distance Technology Transfer | 2 | R27-073: Distance Technology Transfer | FY12-FY17 IGA |  | Nick York | 2009-02-01 | 2009-02-01 | ICT Project Management | 2009-02-01 | 2009-02-01 | 204143 | TRUE | TRUE | PI Direct | 300000 |  | Kevin Burke | 225000 |  | 225000 | 300000 | James Hall | Other / Department Wide
80 | R27-074 Research Project Start! | R27-074 | Best Management Practices (BMP) for Interstate Rest Areas | 1 | R27-074: Best Management Practices (BMP) for Interstate Rest Areas | FY09-FY11 IGA |  | Nick York | 2010-01-01 | 2010-01-01 | ICT Project Management [0.00 %] | 2010-01-01 | 2010-01-01 | 117472 | TRUE | TRUE | PI Direct | 100000 |  | Craig Mitckes | 75000 |  | 75000 | 100000 | Khaled El-Rayes | ENV
81 | R27-075 Research Project Start! | R27-075 | Traffic Signs | 1 | R27-075: Traffic Signs | FY12-FY17 IGA |  | AKSHITI MODI | 2010-04-01 | 2010-04-01 | ICT Project Management | 2010-04-01 | 2010-04-01 | 233196 | TRUE | TRUE | RFP | 230000 |  | Julia Fox | 170665 |  | 170665 | 230000 | Hani Mahmassani | OPS
82 | R27-076 Research Project Start! | R27-076 | LED Roadway Lighting | 2 | R27-076: LED Roadway Lighting | FY12-FY17 IGA |  | Brian Lorbiecki | 2009-11-01 | 2009-11-01 | ICT Project Management | 2009-11-01 | 2009-11-01 | 318985 | TRUE | TRUE | PI Direct | 302599 |  | Mark Seppelt | 226950 |  | 226950 | 276200 | Ray Benekohal | OPS
83 | R27-077 Research Project Start! | R27-077 | Durable Pavement Markings on HMA Mixes | 3 | R27-077: Durable Pavement Markings on HMA Mixes | FY12-FY17 IGA |  | Nick York | 2009-12-01 | 2009-12-01 | ICT Project Management | 2009-12-01 | 2009-12-01 | 372866 | TRUE | TRUE | RFP | 369284 |  | Kelly Senger | 276963 |  | 225000 | 300000 | Carmine Dwyer | PVMT
84 | R27-078 Research Project Start! | R27-078 | Asphalt Binder Additives/Modifiers | 2 | R27-078: Asphalt Binder Additives/Modifiers | FY12-FY17 IGA |  | Brian Lorbiecki | 2010-02-16 | 2010-02-16 | ICT Project Management | 2010-02-16 | 2010-02-16 | 616728 | TRUE | TRUE | PI Direct | 546077 |  | Jim Trepanier | 409558 |  | 409558 | 546078 | Imad Al-Qadi | PVMT
85 | R27-079 Research Project Start! | R27-079 | Fine-Graded Hot Mix Asphalt | 2 | R27-079: Fine-Graded Hot Mix Asphalt | FY12-FY17 IGA |  | Nick York | 2009-08-16 | 2009-08-16 | ICT Project Management | 2009-08-16 | 2009-08-16 | 678509 | TRUE | TRUE | PI Direct | 692716 |  | Matt Mueller | 519537 |  | 519537 | 692716 | William Buttlar | PVMT
86 | R27-080 Research Project Start! | R27-080 | Fatigue Testing of Brass Breakaway Couplings | 1 | R27-080: Fatigue Testing of Brass Breakaway Couplings | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-07-01 | 2009-07-01 | ICT Project Management | 2009-07-01 | 2009-07-01 | 97836 | TRUE | TRUE | PI Direct | 85000 |  | Chris Hahin | 63750 |  | 63750 | 85000 | Greg Banas | BAF
87 | R27-081 Research Project Start! | R27-081 | Performance of IL Aggregates | 2 | R27-081: Performance of IL Aggregates | FY12-FY17 IGA |  | AKSHITI MODI | 2010-01-01 | 2010-01-01 | ICT Project Management | 2010-01-01 | 2010-01-01 | 346529 | TRUE | TRUE | PI Direct | 335017 |  | Greg Heckel | 251263 |  | 250451 | 335017 | Erol Tutumluer | BAF
88 | R27-082 Research Project Start! | R27-082 | Bridge Wood Pilings Retrofits | 2 | R27-082: Bridge Wood Pilings Retrofits | FY12-FY17 IGA |  | Brian Lorbiecki | 2009-08-16 | 2009-08-16 | ICT Project Management | 2009-08-16 | 2009-08-16 | 223345 | TRUE | TRUE | PI Direct | 200000 |  | Dan Tobias | 150000 |  | 135000 | 180000 | Bassem Andrawes | BAF
89 | R27-083 Research Project Start! | R27-083 | Good Movement Study in IL | 2 | R27-083: Good Movement Study in IL | FY12-FY17 IGA |  | AKSHITI MODI | 2010-01-01 | 2010-01-01 | ICT Project Management | 2010-01-01 | 2010-01-01 | 170852 | TRUE | TRUE | PI Direct | 159920 |  | Mike Garcia | 119940 |  | 119940 | 159920 | Kouros Mohammadian | PLAN
90 | R27-084 Research Project Start! | R27-084 | Highway Networks | 1 | R27-084: Highway Networks | FY09-FY11 IGA |  | Nick York | 2010-04-01 | 2010-04-01 | ICT Project Management [0.00 %] | 2010-04-01 | 2010-04-01 | 130317 | TRUE | TRUE | PI Direct | 125407 |  | Jeff Galas | 91672 |  | 91672 | 125407 | Marco Nie | PLAN
91 | R27-085 Research Project Cancelled! | R27-085 | Materials Management Training | 2 | R27-085: Materials Management Training | Cancelled |  | Nick York | 2010-03-03 | 2010-03-03 | Nick York [0.00 %] | 2010-03-03 | 2010-03-03 | 0 | TRUE | TRUE | [9 empty] | PVMT
92 | R27-086 Research Project Start! | R27-086 | Hwy Construction Scheduling with Systems Approach | 1 | R27-086: Hwy Construction Scheduling with Systems Approach | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-07-01 | 2010-07-01 | ICT Project Management | 2010-07-01 | 2010-07-01 | 81901 | TRUE | TRUE | PI Direct | 89113 |  | Mike Ripka | 66833 |  | 66833 | 89113 | Dianne Slattery | CON
93 | R27-087 Research Project Start! | R27-087 | Pavement Management Systems | 3 | R27-087: Pavement Management Systems | FY12-FY17 IGA |  | AKSHITI MODI | 2010-05-01 | 2010-05-01 | ICT Project Management | 2010-05-01 | 2010-05-01 | 109164 | TRUE | TRUE | RFP | 99851 |  | Kevin Burke | 74390 |  | 74324 | 99851 | Angela Wolters | PLAN
94 | R27-088 Research Project Start! | R27-088 | Bridge Decks (Durability) | 3 | R27-088: Bridge Decks (Durability) | FY12-FY17 IGA |  | Nick York | 2010-05-16 | 2010-05-16 | ICT Project Management | 2010-05-16 | 2010-05-16 | 364520 | TRUE | TRUE | RFP | 334372 |  | Dan Tobias | 250779 |  | 224987 | 299982 | Paramita Mondal | BAF
95 | R27-089 Research Project Start! | R27-089 | Illinois Highway Safety Manual Workshop | 1 | R27-089: Illinois Highway Safety Manual Workshop | FY09-FY11 IGA |  | Nick York | 2010-08-16 | 2010-08-16 | Nick York [0.00 %] | 2010-08-16 | 2010-08-16 | 169820 | TRUE | TRUE | PI Direct | 153333 |  | Priscilla Tobias | 115000 |  | 115000 | 153333 | Yanfeng Ouyang | SAF
96 | R27-090 Research Project Start! | R27-090 | Investigation Wrong-Way Driving | 3 | R27-090: Investigation Wrong-Way Driving | FY12-FY17 IGA |  | AKSHITI MODI | 2010-07-01 | 2010-07-01 | ICT Project Management | 2010-07-01 | 2010-07-01 | 484303 | TRUE | TRUE | RFP | 474421 |  | Richard Coakley / Priscilla Tobias | 355576 |  | 353511 | 230986 | Huaguo Zhou | SAF
97 | R27-091 Research Project Start! | R27-091 | Traffic Flow Monitoring Technologies | 1 | R27-091: Traffic Flow Monitoring Technologies | FY09-FY11 IGA |  | Brian Lorbiecki | 2010-01-01 | 2010-01-01 | ICT Project Management | 2010-01-01 | 2010-01-01 | 106124 | TRUE | TRUE | PI Direct | 99938 |  | Jeff Galas | 74954 |  | 74954 | 99938 | Jakob Eriksson | OPS
98 | R27-092 Research Project Cancelled! | R27-092 | Engineering Software Review | 2 | R27-092: Engineering Software Review | Cancelled |  | Nick York | 2009-11-13 | 2009-11-13 | Nick York [0.00 %] | 2009-11-13 | 2009-11-13 | 0 | TRUE | TRUE | [9 empty] | Other / Department Wide
99 | R27-093 Research Project Start! | R27-093 | Hot-Spot Air Quality Modeling | 4 | R27-093: Hot-Spot Air Quality Modeling | FY12-FY17 IGA |  | AKSHITI MODI | 2010-11-01 | 2010-11-01 | ICT Project Management | 2010-11-01 | 2010-11-01 | 108086 | TRUE | TRUE | RFP | 97749 |  | Walt Zyznieuski | 73305 |  | 72791 | 84430 | Jane Lin | ENV
100 | R27-094 Research Project Start! | R27-094 | Snow & Ice Plows | 3 | R27-094: Snow & Ice Plows | FY12-FY17 IGA |  | AKSHITI MODI | 2011-09-01 | 2011-09-01 | ICT Project Management | 2011-09-01 | 2011-09-01 | 355632 | TRUE | TRUE | RFP | 338708 |  | Tim Peters | 253523 |  | 252708 | 250000 | Souhail Elhouar | OPS
101 | R27-095 Research Project Start! | R27-095 | RR Crossings | 2 | R27-095: RR Crossings | FY12-FY17 IGA |  | Nick York | 2010-08-16 | 2010-08-16 | ICT Project Management | 2010-08-16 | 2010-08-16 | 334076 | TRUE | TRUE | PI Direct | 340887 |  | Yogesh Gautam | 255665 |  | 183814 | 245086 | Ray Benekohal | OPS
102 | R27-096 Research Project Start! | R27-096 | Pedestrian/Bicyclist Warning Devices | 3 | R27-096: Pedestrian/Bicyclist Warning Devices | FY12-FY17 IGA |  | Nick York | 2011-01-01 | 2011-01-01 | ICT Project Management | 2011-01-01 | 2011-01-01 | 185679 | TRUE | TRUE | RFP | 202658 |  | Kyle Armstrong | 150000 |  | 135813 | 200000 | Paul Metaxatos | OPS
103 | R27-097 Research Project Start! | R27-097 | Yellow Arrows | 3 | R27-097: Yellow Arrows | FY12-FY17 IGA |  | Nick York | 2010-11-01 | 2010-11-01 | ICT Project Management | 2010-11-01 | 2010-11-01 | 426681 | TRUE | TRUE | RFP | 399153 |  | Randy Laninga | 264649 |  | 181994 | 243854 | Kerrie Schattler | SAF
104 | R27-098 Research Project Start! | R27-098 | Concrete Cylinder | 2 | R27-098: Concrete Cylinder | FY12-FY17 IGA |  | Brian Lorbiecki | 2010-08-16 | 2010-08-16 | ICT Project Management | 2010-08-16 | 2010-08-16 | 232068 | TRUE | TRUE | PI Direct | 230000 |  | Douglas Dirks | 172500 |  | 166411 | 188778 | John Popovics | BAF
105 | R27-099 Research Project Start! | R27-099 | Drilled Shafts | 2 | R27-099: Drilled Shafts | FY12-FY17 IGA |  | Nick York | 2011-11-01 | 2011-11-01 | ICT Project Management | 2011-11-01 | 2011-11-01 | 143970 | TRUE | TRUE | PI Direct | 172500 |  | Bill Kramer | 129375 |  | 129375 | 172500 | Timothy Stark | BAF
106 | R27-100 Research Project Start! | R27-100 | Tack Coat Phase 2 | 2 | R27-100: Tack Coat Phase 2 | FY12-FY17 IGA |  | Nick York | 2010-09-16 | 2010-09-16 | ICT Project Management | 2010-09-16 | 2010-09-16 | 500001 | TRUE | TRUE | PI Direct | 529445 |  | Derek Parish | 396093 |  | 396093 | 529445 | Imad Al-Qadi | PVMT
107 | R27-101 Research Project Start! | R27-101 | BS/MS Student Scholarships | 1 | R27-101: BS/MS Student Scholarships | FY12-FY17 IGA |  | Brian Lorbiecki | 2011-01-01 | 2011-01-01 | ICT Project Management | 2011-01-01 | 2011-01-01 | 156542 | TRUE | TRUE | PI Direct | 275000 |  | Amy Schutzbach | 137500 |  | 137500 | 275000 | Imad Al-Qadi | Other / Department Wide
108 | R27-102 Research Project Start! | R27-102 | Ditch Checks & Inlet Protection Structures | 2 | R27-102: Ditch Checks & Inlet Protection Structures | FY12-FY17 IGA |  | AKSHITI MODI | 2011-08-16 | 2011-08-16 | ICT Project Management | 2011-08-16 | 2011-08-16 | 443056 | TRUE | TRUE | PI Direct | 411244 |  | Joe Vespa | 308433 |  | 308433 | 300000 | Prasanta Kalita | ENV
109 | R27-103 Research Project Start! | R27-103 | Interstate Rest Areas | 2 | R27-103: Interstate Rest Areas | FY12-FY17 IGA |  | AKSHITI MODI | 2011-01-01 | 2011-01-01 | ICT Project Management | 2011-01-01 | 2011-01-01 | 245434 | TRUE | TRUE | PI Direct | 220000 |  | Matt Sunderland | 165000 |  | 164721 | 220000 | Khaled El-Rayes | ENV
110 | R27-104 Research Project Start! | R27-104 | Native Vegetation | 2 | R27-104: Native Vegetation | FY12-FY17 IGA |  | AKSHITI MODI | 2012-01-01 | 2012-01-01 | ICT Project Management | 2012-01-01 | 2012-01-01 | 165257 | TRUE | TRUE | PI Direct | 192090 |  | Scott Marlow | 144068 |  | 144068 | 192091 | Heidi Howard | ENV
111 | R27-105 Research Project Start! | R27-105 | Bridge Scour Estimates w/ Sricos Phjase 2 | 2 | R27-105: Bridge Scour Estimates w/ Sricos Phjase 2 | FY12-FY17 IGA |  | Nick York | 2011-04-01 | 2011-04-01 | ICT Project Management | 2011-04-01 | 2011-04-01 | 156000 | TRUE | TRUE | PI Direct | 204000 |  | Neil VanBebber | 153000 |  | 153000 | 204000 | Tim Straub | BAF
112 | R27-106 Research Project Start! | R27-106 | High Performance Grade 50 Structural Steel | 3 | R27-106: High Performance Grade 50 Structural Steel | FY12-FY17 IGA |  | Nick York | 2011-12-01 | 2011-12-01 | ICT Project Management | 2011-12-01 | 2011-12-01 | 103501 | TRUE | TRUE | RFP | 103500 |  | Chris Hahin | 77626 |  | 67500 | 90000 | Semyon Vaynman | BAF
113 | R27-107 Research Project Cancelled! | R27-107 | Short-Span Plate & Tube Bridge | 2 | R27-107: Short-Span Plate & Tube Bridge | Cancelled |  | Nick York | 2013-07-02 | 2013-07-02 | Nick York [0.00 %] | 2013-07-02 | 2013-07-02 | 0 | TRUE | TRUE | [9 empty] | BAF
114 | R27-108 Research Project Start! | R27-108 | Night Traffic Warning Devices | 4 | R27-108: Night Traffic Warning Devices | FY12-FY17 IGA |  | Nick York | 2011-09-01 | 2011-09-01 | ICT Project Management | 2011-09-01 | 2011-09-01 | 230949 | TRUE | TRUE | RFP | 240000 |  | Tim Kell | 180000 |  | 120000 | 160000 | Doug Steele | OPS
115 | R27-109 Research Project Start! | R27-109 | Flaggers & Spotters | 3 | R27-109: Flaggers & Spotters | FY12-FY17 IGA |  | Nick York | 2011-11-01 | 2011-11-01 | ICT Project Management | 2011-11-01 | 2011-11-01 | 181106 | TRUE | TRUE | RFP | 167066 |  | Paul Lorton | 125299 |  | 125299 | 167066 | Khaled El-Rayes | SAF
116 | R27-110 Research Project Start! | R27-110 | Highway Work Zones | 2 | R27-110: Highway Work Zones | FY12-FY17 IGA |  | Nick York | 2012-04-16 | 2012-04-16 | ICT Project Management | 2012-04-16 | 2012-04-16 | 98409 | TRUE | TRUE | PI Direct | 85303 |  | Paul Lorton | 63977 |  | 63977 | 85303 | Ray Benekohal | SAF
117 | R27-111 Research Project Start! | R27-111 | Right-Turn Lane Design | 3 | R27-111: Right-Turn Lane Design | FY12-FY17 IGA |  | Nick York | 2011-09-01 | 2011-09-01 | ICT Project Management | 2011-09-01 | 2011-09-01 | 296065 | TRUE | TRUE | RFP | 255415 |  | Dan Mlacnik | 175000 |  | 103300 | 115800 | Kerrie Schattler | SAF
118 | R27-112 Research Project Start! | R27-112 | Testing of Portland Cement | 2 | R27-112: Testing of Portland Cement | FY12-FY17 IGA |  | AKSHITI MODI | 2011-05-01 | 2011-05-01 | ICT Project Management | 2011-05-01 | 2011-05-01 | 424697 | TRUE | TRUE | PI Direct | 399987 |  | John Huang | 299995 |  | 299780 | 400001 | Mohsen Issa | PVMT
119 | R27-113 Research Project Start! | R27-113 | Modeling Seniors Activity | 2 | R27-113: Modeling Seniors Activity | FY12-FY17 IGA |  | AKSHITI MODI | 2011-07-01 | 2011-07-01 | ICT Project Management | 2011-07-01 | 2011-07-01 | 136286 | TRUE | TRUE | PI Direct | 125063 |  | Amy Welk | 93793 |  | 93793 | 125063 | Kouros Mohammadian | MFM
120 | R27-114 Research Project Start! | R27-114 | Restoration Progress at IDOT | 2 | R27-114: Restoration Progress at IDOT | FY12-FY17 IGA |  | AKSHITI MODI | 2011-10-01 | 2011-10-01 | ICT Project Management | 2011-10-01 | 2011-10-01 | 64762 | TRUE | TRUE | PI Direct | 81214 |  | Tom Brooks | 60000 |  | 51155 | 81214 | Geoffrey Pociask | ENV
121 | R27-115 Research Project Start! | R27-115 | Superstructures | 3 | R27-115: Superstructures | FY18-FY24 IGA |  | ICT Project Management | 2012-03-01 | 2012-03-01 | ICT Project Management | 2012-03-01 | 2012-03-01 | 388957 | TRUE | TRUE | RFP | 345571 |  | Mark Shaffer | 259178 | In-State University | 225000 | 300000 | James LaFave | BAF
122 | R27-116 Research Project Start! | R27-116 | Highway Inventory Data | 3 | R27-116: Highway Inventory Data | FY12-FY17 IGA |  | Nick York | 2012-01-01 | 2012-01-01 | ICT Project Management | 2012-01-01 | 2012-01-01 | 217202 | TRUE | TRUE | RFP | 215000 |  | Rob Robinson | 161250 |  | 161250 | 215000 | Huaguo Zhou | SAF
123 | R27-117 Research Project Start! | R27-117 | Engineers Peer to Peer Workshop | 2 | R27-117: Engineers Peer to Peer Workshop | FY12-FY17 IGA |  | Nick York | 2012-08-01 | 2012-08-01 | ICT Project Management | 2012-08-01 | 2012-08-01 | 57375 | TRUE | TRUE | PI Direct | 50000 |  | Priscilla Tobias | 37500 |  | 37500 | 50000 | Yanfeng Ouyang | SAF
124 | R27-118 Research Project Start! | R27-118 | Traffic Incident Management | 2 | R27-118: Traffic Incident Management | FY12-FY17 IGA |  | Nick York | 2011-08-16 | 2011-08-16 | ICT Project Management | 2011-08-16 | 2011-08-16 | 374668 | TRUE | TRUE | PI Direct | 374668 |  | Geno Koehler | 280896 |  | 224896 | 300001 | Ryan Fries | OPS
125 | R27-119 Research Project Start! | R27-119 | Real-Time Information Dissemination | 3 | R27-119: Real-Time Information Dissemination | FY12-FY17 IGA |  | Nick York | 2013-08-16 | 2013-08-16 | ICT Project Management | 2013-08-16 | 2013-08-16 | 234997 | TRUE | TRUE | RFP | 235770 |  | Kevin Price / Bruce Carmitchel | 172645 |  | 120000 | 161256 | Ryan Fries | PLAN
126 | R27-120 Research Project Start! | R27-120 | All Weather | 3 | R27-120: All Weather | FY18-FY24 IGA |  | ICT Project Management | 2012-04-01 | 2012-04-01 | Brian Lorbiecki | 2012-04-01 | 2012-04-01 | 516044 | TRUE | TRUE | RFP | 500614 |  | Kelly Senger | 378585 | Out-of-State University | 300000 | 400000 | Neal Hawkins | OPS
127 | R27-121 Research Project Cancelled! | R27-121 | Polymer-Modified HMA & WMA Mixtures w/ RAP & RAS (Phase 1) | 2 | R27-121: Polymer-Modified HMA & WMA Mixtures w/ RAP & RAS (Phase 1) | Cancelled |  | Nick York | 2015-03-05 | 2015-03-05 | Nick York [0.00 %] | 2015-03-05 | 2015-03-05 | 0 | TRUE | TRUE | [9 empty] | PVMT
128 | R27-122 Research Project Start! | R27-122 | Driven Pile Installation | 2 | R27-122: Driven Pile Installation | FY12-FY17 IGA |  | Nick York | 2012-07-01 | 2012-07-01 | ICT Project Management | 2012-07-01 | 2012-07-01 | 303084 | TRUE | TRUE | PI Direct | 304792 |  | Bill Kramer | 228594 |  | 228594 | 304792 | Jim Long | BAF
129 | R27-123 Research Project Start! | R27-123 | Street Lighting Technologies | 2 | R27-123: Street Lighting Technologies | FY12-FY17 IGA |  | Nick York | 2012-10-16 | 2012-10-16 | ICT Project Management | 2012-10-16 | 2012-10-16 | 337802 | TRUE | TRUE | PI Direct | 282000 |  | Mark Seppelt | 211500 |  | 211500 | 282000 | Ray Benekohal | OPS
130 | R27-124 Research Project Start! | R27-124 | Evaluation of Porous Materials | 2 | R27-124: Evaluation of Porous Materials | FY12-FY17 IGA |  | AKSHITI MODI | 2012-08-16 | 2012-08-16 | ICT Project Management | 2012-08-16 | 2012-08-16 | 506080 | TRUE | TRUE | PI Direct | 486617 |  | Sheila Beshears | 364963 |  | 364958 | 460000 | Erol Tutumluer | PVMT
131 | R27-125 Research Project Start! | R27-125 | Sustainable Aggregates | 3 | R27-125: Sustainable Aggregates | FY12-FY17 IGA |  | AKSHITI MODI | 2013-02-01 | 2013-02-01 | ICT Project Management | 2013-02-01 | 2013-02-01 | 257562 | TRUE | TRUE | RFP | 220000 |  | Sheila Beshears | 165000 |  | 165000 | 220000 | Erol Tutumluer | PVMT
132 | R27-126 Research Project Start! | R27-126 | Temporary Stabilization | 3 | R27-126: Temporary Stabilization | FY12-FY17 IGA |  | AKSHITI MODI | 2012-08-01 | 2012-08-01 | ICT Project Management | 2012-08-01 | 2012-08-01 | 206779 | TRUE | TRUE | PI Direct | 249996 |  | Matt Sunderland | 187497 |  | 147360 | 249996 | Mark Grinter | ENV
133 | R27-127 Research Project Start! | R27-127 | ASCT | 3 | R27-127: ASCT | FY18-FY24 IGA |  | ICT Project Management | 2013-01-01 | 2013-01-01 | Brian Lorbiecki | 2013-01-01 | 2013-01-01 | 1075446 | TRUE | TRUE | RFP | 1019832 |  | Kyle Armstrong | 764874 | In-State University | 300000 | 400000 | Ray Benekohal | OPS
134 | R27-128 Research Project Start! | R27-128 | Binder Replacement | 2 | R27-128: Binder Replacement | FY12-FY17 IGA |  | Nick York | 2013-01-01 | 2013-01-01 | ICT Project Management | 2013-01-01 | 2013-01-01 | 831023 | TRUE | TRUE | PI Direct | 779997 |  | Matt Mueller | 584390 |  | 403784 | 585000 | Imad Al-Qadi | PVMT
135 | R27-129 Research Project Start! | R27-129 | AIMS | 3 | R27-129: AIMS | FY12-FY17 IGA |  | Nick York | 2012-12-01 | 2012-12-01 | ICT Project Management | 2012-12-01 | 2012-12-01 | 125035 | TRUE | TRUE | RFP | 125000 |  | Sheila Beshears | 93750 |  | 93750 | 125000 | Enad Mahmoud | PVMT
136 | R27-130 Research Project Start! | R27-130 | Overlay Thickness | 2 | R27-130: Overlay Thickness | FY12-FY17 IGA |  | Nick York | 2012-08-16 | 2012-08-16 | ICT Project Management | 2012-08-16 | 2012-08-16 | 143441 | TRUE | TRUE | PI Direct | 120000 |  | Thomas Winkelman / Scott Lackey | 90000 |  | 90000 | 120000 | Erol Tutumluer | PVMT
137 | R27-131 Research Project Start! | R27-131 | Urban Traffic | 2 | R27-131: Urban Traffic | FY12-FY17 IGA |  | Nick York | 2012-07-01 | 2012-07-01 | ICT Project Management | 2012-07-01 | 2012-07-01 | 231412 | TRUE | TRUE | PI Direct | 199980 |  | William Morgan | 149985 |  | 62812 | 100000 | Jakob Eriksson | PLAN
138 | R27-132 Research Project Start! | R27-132 | Incorporating NEPA into the IDOT and MPO Planning Process | 2 | R27-132: Incorporating NEPA into the IDOT and MPO Planning Process | FY12-FY17 IGA |  | Nick York | 2012-07-01 | 2012-07-01 | ICT Project Management | 2012-07-01 | 2012-07-01 | 205772 | TRUE | TRUE | PI Direct | 179703 |  | Bruce Carmitchel | 134777 |  | 134777 | 179703 | Nora El-Gohary | PLAN
139 | R27-133 Research Project Start! | R27-133 | Earthquake Resisting System | 2 | R27-133: Earthquake Resisting System | FY18-FY24 IGA |  | ICT Project Management | 2013-10-01 | 2013-10-01 | ICT Project Management | 2013-10-01 | 2013-10-01 | 358653 | TRUE | TRUE | PI Direct | 301129 |  | Mark Shaffer | 225847 | In-State University | 225000 | 300000 | James LaFave | BAF
140 | R27-134 Research Project Start! | R27-134 | Bridge Wood Pilings | 2 | R27-134: Bridge Wood Pilings | FY12-FY17 IGA |  | Nick York | 2012-11-16 | 2012-11-16 | ICT Project Management | 2012-11-16 | 2012-11-16 | 367383 | TRUE | TRUE | PI Direct | 350000 |  | Jeff Burke | 262500 |  | 262500 | 350000 | Bassem Andrawes | BAF
141 | R27-135 Research Project Start! | R27-135 | Hwy Construction Mgmt 2 | 2 | R27-135: Hwy Construction Mgmt 2 | FY12-FY17 IGA |  | AKSHITI MODI | 2013-05-01 | 2013-05-01 | ICT Project Management | 2013-05-01 | 2013-05-01 | 188165 | TRUE | TRUE | PI Direct | 180968 |  | Ted Nemsky | 133614 |  | 132183 | 180968 | Dianne Slattery | CON
142 | R27-136 Research Project Start! | R27-136 | PROWAG | 3 | R27-136: PROWAG | FY12-FY17 IGA |  | AKSHITI MODI | 2013-10-01 | 2013-10-01 | ICT Project Management | 2013-10-01 | 2013-10-01 | 253629 | TRUE | TRUE | RFP | 216665 |  | Juliet Shoultz | 162499 |  | 162485 | 216665 | Khaled El-Rayes | OPS
143 | R27-137 Research Project Start! | R27-137 | Evaluation of PCC | 2 | R27-137: Evaluation of PCC | FY12-FY17 IGA |  | AKSHITI MODI | 2013-07-01 | 2013-07-01 | ICT Project Management | 2013-07-01 | 2013-07-01 | 305865 | TRUE | TRUE | PI Direct | 287500 |  | Douglas Dirks | 215625 |  | 215625 | 250000 | John Popovics | BAF
144 | R27-138 Research Project Start! | R27-138 | Material & Construction Inspection | 2 | R27-138: Material & Construction Inspection | FY12-FY17 IGA |  | Nick York | 2013-09-01 | 2013-09-01 | ICT Project Management | 2013-09-01 | 2013-09-01 | 75129 | TRUE | TRUE | PI Direct | 80000 |  | Mark Neale | 60000 |  | 60000 | 80000 | Constance Kelly | CON
145 | R27-139 Research Project Start! | R27-139 | Bridge Decks 2 | 2 | R27-139: Bridge Decks 2 | FY12-FY17 IGA |  | Nick York | 2013-07-01 | 2013-07-01 | ICT Project Management | 2013-07-01 | 2013-07-01 | 418685 | TRUE | TRUE | PI Direct | 367739 |  | James Krstulovich | 275805 |  | 225000 | 300000 | Paramita Mondal | PVMT
146 | R27-140 Research Project Start! | R27-140 | Exterior Beam | 3 | R27-140: Exterior Beam | FY12-FY17 IGA |  | Nick York | 2014-01-01 | 2014-01-01 | ICT Project Management | 2014-01-01 | 2014-01-01 | 360552 | TRUE | TRUE | RFP | 300000 |  | Mark Thomson | 225000 |  | 225000 | 300000 | Riyadh Hindi | BAF
147 | R27-141 Research Project Start! | R27-141 | Storm Water Run | 3 | R27-141: Storm Water Run | FY12-FY17 IGA |  | Nick York | 2014-02-01 | 2014-02-01 | ICT Project Management | 2014-02-01 | 2014-02-01 | 347320 | TRUE | TRUE | RFP | 344303 |  | Scott Marlow | 256892 |  | 223623 | 299442 | Abdolreza Osouli | OPS
148 | R27-142 Research Project Start! | R27-142 | Road Weather Information System | 3 | R27-142: Road Weather Information System | FY12-FY17 IGA |  | Nick York | 2014-10-01 | 2014-10-01 | ICT Project Management | 2014-10-01 | 2014-10-01 | 283440 | TRUE | TRUE | RFP | 283440 |  | Derek Parish / Ruben Boehler | 212580 |  | 187500 | 250000 | Carmine Dwyer | OPS
149 | R27-143 Research Project Start! | R27-143 | Tree Establishment | 2 | R27-143: Tree Establishment | FY12-FY17 IGA |  | Nick York | 2013-09-01 | 2013-09-01 | ICT Project Management | 2013-09-01 | 2013-09-01 | 69194 | TRUE | TRUE | PI Direct | 79843 |  | Tom Brooks | 59882 |  | 59882 | 79843 | Jeffrey Matthews | ENV
150 | R27-144 Research Project Start! | R27-144 | Urban Flood Frequency Equations | 2 | R27-144: Urban Flood Frequency Equations | FY12-FY17 IGA |  | ICT Project Management | 2013-08-01 | 2013-08-01 | ICT Project Management | 2013-08-01 | 2013-08-01 | 466000 | TRUE | TRUE | PI Direct | 466000 |  | Matthew O'Connor | 349350 |  | 349350 | 426000 | Audrey Ishii | BAF
151 | R27-145 Research Project Start! | R27-145 | Drill Shafts Weak Rocks | 2 | R27-145: Drill Shafts Weak Rocks | FY18-FY24 IGA |  | ICT Project Management | 2014-01-01 | 2014-01-01 | ICT Project Management | 2014-01-01 | 2014-01-01 | 731350 | TRUE | TRUE | PI Direct | 736267 |  | Bill Kramer | 552200 | In-State University | 501984 | 669312 | Timothy Stark | BAF
152 | R27-146 Research Project Start! | R27-146 | (MIRA) Ultrasonic Imaging for Concrete Infrastructures | 2 | R27-146: (MIRA) Ultrasonic Imaging for Concrete Infrastructures | FY12-FY17 IGA |  | ICT Project Management | 2013-07-01 | 2013-07-01 | ICT Project Management | 2013-07-01 | 2013-07-01 | 547904 | TRUE | TRUE | PI Direct | 500000 |  | Douglas Dirks / Gary Kowalski | 375000 |  | 375000 | 500000 | John Popovics | CON
153 | R27-147 Research Project Start! | R27-147 | Chloride Reduction | 3 | R27-147: Chloride Reduction | FY12-FY17 IGA |  | ICT Project Management | 2014-03-17 | 2014-03-17 | ICT Project Management | 2014-03-17 | 2014-03-17 | 100000 | TRUE | TRUE | RFP | 100000 |  | Tim Peters | 75000 |  | 75000 | 100000 | Wilfrid Nixon | OPS
154 | R27-148 Research Project Start! | R27-148 | Low-Water Crossing Design for Very Low ADT | 3 | R27-148: Low-Water Crossing Design for Very Low ADT | FY12-FY17 IGA |  | ICT Project Management | 2015-01-01 | 2015-01-01 | ICT Project Management | 2015-01-01 | 2015-01-01 | 202837 | TRUE | TRUE | RFP | 200000 |  | Thomas Winkelman / Jayme Schiff | 150000 |  | 150000 | 200000 | Prasanta Kalita | BAF
155 | R27-149-1 Research Project Start! | R27-149-1 | M-E Design Flexible Pavements | 2 | R27-149-1: M-E Design Flexible Pavements | FY18-FY24 IGA |  | ICT Project Management | 2014-07-01 | 2014-07-01 | ICT Project Management | 2014-07-01 | 2014-07-01 | 252806 | TRUE | TRUE | PI Direct | 275863 |  | Charles Wienrank | 206897 | In-State University | 173017 | 230689 | Marshall Thompson | PVMT
156 | R27-149-2 Research Project Start! | R27-149-2 | M-E Design Rigid Pavements | 2 | R27-149-2: M-E Design Rigid Pavements | FY18-FY24 IGA |  | ICT Project Management | 2014-07-01 | 2014-07-01 | ICT Project Management | 2014-07-01 | 2014-07-01 | 432944 | TRUE | TRUE | PI Direct | 389592 |  | Charles Wienrank | 292194 | In-State University | 243750 | 324999 | Jeffery Roesler | PVMT
157 | R27-150 Research Project Start! | R27-150 | Condition Rating Models | 2 | R27-150: Condition Rating Models | FY18-FY24 IGA |  | ICT Project Management | 2015-01-01 | 2015-01-01 | ICT Project Management | 2015-01-01 | 2015-01-01 | 227930 | TRUE | TRUE | PI Direct | 203343 |  | Travis Lobmaster / Joe Vespa | 154195 | In-State University | 150000 | 200000 | Hasan Ozer | PLAN
158 | R27-151 Research Project Start! | R27-151 | RPM | 3 | R27-151: RPM | FY18-FY24 IGA |  | Brian Lorbiecki | 2014-10-01 | 2014-10-01 | Brian Lorbiecki | 2014-10-01 | 2014-10-01 | 468261 | TRUE | TRUE | RFP | 466640 |  | Kelly Senger / Kyle Armstrong | 353105 | Private Industry | 225000 | 300000 | Carmine Dwyer | OPS
159 | R27-152 Research Project Start! | R27-152 | Fees Charged for Oversize/Overweight Vehicle Permits | 4 | R27-152: Fees Charged for Oversize/Overweight Vehicle Permits | FY12-FY17 IGA |  | ICT Project Management | 2015-03-01 | 2015-03-01 | ICT Project Management | 2015-03-01 | 2015-03-01 | 246391 | TRUE | TRUE | RFP | 300000 |  | Justan Mann | 225001 |  | 225001 | 300000 | Imad Al-Qadi | OPS
160 | R27-153 Research Project Start! | R27-153 | Utility Relocation | 2 | R27-153: Utility Relocation | FY18-FY24 IGA |  | ICT Project Management | 2014-09-01 | 2014-09-01 | ICT Project Management | 2014-09-01 | 2014-09-01 | 257510 | TRUE | TRUE | PI Direct | 230000 |  | Tim Kell | 172500 | In-State University | 172500 | 230000 | Khaled El-Rayes | CON
161 | R27-154 Research Project Start! | R27-154 | Early-Age Concrete | 3 | R27-154: Early-Age Concrete | FY18-FY24 IGA |  | ICT Project Management | 2015-01-01 | 2015-01-01 | ICT Project Management | 2015-01-01 | 2015-01-01 | 388767 | TRUE | TRUE | RFP | 355313 |  | James Krstulovich | 266484 | In-State University | 224998 | 299998 | Mohsen Issa | PVMT
162 | R27-155 Research Project Start! | R27-155 | Smart Work Zone | 2 | R27-155: Smart Work Zone | FY12-FY17 IGA |  | ICT Project Management | 2014-10-15 | 2014-10-15 | ICT Project Management | 2014-10-15 | 2014-10-15 | 241781 | TRUE | TRUE | PI Direct | 225000 |  | Paul Lorton | 168750 |  | 168750 | 225000 | Daniel Work | SAF
163 | R27-156 Research Project Start! | R27-156 | Prestressed Beams | 3 | R27-156: Prestressed Beams | FY18-FY24 IGA |  | ICT Project Management | 2014-11-01 | 2014-11-01 | ICT Project Management | 2014-11-01 | 2014-11-01 | 337762 | TRUE | TRUE | RFP | 312165 |  | Victor Veliz | 234124 | In-State University | 225000 | 299999 | Bassem Andrawes | BAF
164 | R27-157 Research Project Start! | R27-157 | Plasticity Index | 3 | R27-157: Plasticity Index | FY18-FY24 IGA |  | ICT Project Management | 2015-01-01 | 2015-01-01 | ICT Project Management | 2015-01-01 | 2015-01-01 | 221361 | TRUE | TRUE | RFP | 210219 |  | Heather Shoup | 160788 | In-State University | 120710 | 160947 | Abdolreza Osouli | PVMT
165 | R27-158 Research Project Cancelled! | R27-158 | Crack Induction in Cement Stabalized Layers | 2 | R27-158: Crack Induction in Cement Stabalized Layers | Cancelled |  | Nick York | 2015-04-23 | 2015-04-23 | Nick York [0.00 %] | 2015-04-23 | 2015-04-23 | 0 | TRUE | TRUE | [9 empty] | PVMT
166 | R27-159 Research Project Cancelled! | R27-159 | Transportation Problems - Sustainability | 2 | R27-159: Transportation Problems - Sustainability | Cancelled |  | Nick York | 2013-12-09 | 2013-12-09 | Nick York [0.00 %] | 2013-12-09 | 2013-12-09 | 0 | TRUE | TRUE | [9 empty] | SUS
167 | R27-160 Research Project Start! | R27-160 | Sustainability Engineering | 1 | R27-160: Sustainability Engineering | FY12-FY17 IGA |  | ICT Project Management | 2013-12-09 | 2013-12-09 | ICT Project Management | 2013-12-09 | 2013-12-09 | 801388 | TRUE | TRUE | PI Direct | 1000000 |  | Kelly Senger | 750000 |  | 750000 | 1000000 | Imad Al-Qadi | SUS
168 | R27-161 Research Project Start! | R27-161 | Performance Monitoring | 2 | R27-161: Performance Monitoring | FY18-FY24 IGA |  | ICT Project Management | 2014-10-01 | 2014-10-01 | ICT Project Management | 2014-10-01 | 2014-10-01 | 980732 | TRUE | TRUE | PI Direct | 969729 |  | Jim Trepanier | 729097 | In-State University & Private Industry | 548207 | 674407 | Imad Al-Qadi | SUS
169 | R27-162 Research Project Start! | R27-162 | Chemical/BK Project | 2 | R27-162: Chemical/BK Project | FY12-FY17 IGA |  | ICT Project Management | 2015-01-01 | 2015-01-01 | ICT Project Management | 2015-01-01 | 2015-01-01 | 147923 | TRUE | TRUE | PI Direct | 144345 |  | Ronald Price | 108259 |  | 108259 | 144345 | B.K. Sharma | PVMT
170 | R27-163 Research Project Start! | R27-163 | Staking and Inspection | 3 | R27-163: Staking and Inspection | FY18-FY24 IGA |  | ICT Project Management | 2015-08-16 | 2015-08-16 | ICT Project Management | 2015-08-16 | 2015-08-16 | 249266 | TRUE | TRUE | RFP | 226651 |  | Tim Kell | 169988 | In-State University | 157500 | 210000 | Nora El-Gohary | CON
171 | R27-164 Research Project Start! | R27-164 | Living Snow Fences | 3 | R27-164: Living Snow Fences | FY18-FY24 IGA |  | Brian Lorbiecki | 2015-11-01 | 2015-11-01 | Brian Lorbiecki | 2015-11-01 | 2015-11-01 | 394210 | TRUE | TRUE | RFP | 373806 |  | Rodney Lashuay | 283480 | Out-of-State University | 225000 | 300000 | Xianming Shi | OPS
172 | R27-165 Research Project Start! | R27-165 | Determine whether a Deck with a Microsilica or Latex Concrete Overlay | 3 | R27-165: Determine whether a Deck with a Microsilica or Latex Concrete Overlay | FY12-FY17 IGA |  | ICT Project Management | 2016-01-01 | 2016-01-01 | ICT Project Management | 2016-01-01 | 2016-01-01 | 3551 | TRUE | TRUE | RFP | 3524 |  | Dave Copenbarger | 2643 |  | 2643 | 3524 | John Popovics | BAF
173 | R27-166 Research Project Cancelled! | R27-166 | Effectiveness of Waterproofing Systems for Bituminous Overlays on Bridge Decks | 2 | R27-166: Effectiveness of Waterproofing Systems for Bituminous Overlays on Bridge Decks | Cancelled |  | Nick York | 2015-06-29 | 2015-06-29 | Nick York [0.00 %] | 2015-06-29 | 2015-06-29 | 0 | TRUE | TRUE | [9 empty] | BAF
174 | R27-167 Research Project Start! | R27-167 | Pedestrian Treatments | 3 | R27-167: Pedestrian Treatments | FY18-FY24 IGA |  | ICT Project Management | 2015-08-16 | 2015-08-16 | ICT Project Management | 2015-08-16 | 2015-08-16 | 185542 | TRUE | TRUE | RFP | 176109 |  | Kyle Armstrong | 132297 | In-State University | 131250 | 175000 | Yan Qi | SAF
175 | R27-168 Research Project Start! | R27-168 | Sustainable Aggregates Ph. II | 2 | R27-168: Sustainable Aggregates Ph. II | FY18-FY24 IGA |  | ICT Project Management | 2015-09-01 | 2015-09-01 | ICT Project Management | 2015-09-01 | 2015-09-01 | 720399 | TRUE | TRUE | PI Direct | 696537 |  | Jim Trepanier | 522403 | In-State University | 375000 | 500000 | Erol Tutumluer | PVMT
176 | R27-169 Research Project Start! | R27-169 | Opportunistic Traffic Sensing | 2 | R27-169: Opportunistic Traffic Sensing | FY18-FY24 IGA |  | ICT Project Management | 2015-05-16 | 2015-05-16 | ICT Project Management | 2015-05-16 | 2015-05-16 | 244850 | TRUE | TRUE | PI Direct | 237117 |  | William Morgan | 177838 | In-State University | 177044 | 100000 | Jakob Eriksson | PLAN
177 | R27-170 Research Project Start! | R27-170 | Rehab Course | 3 | R27-170: Rehab Course | FY18-FY24 IGA |  | Audrey Donoho | 2016-01-01 | 2016-01-01 | Audrey Donoho | 2016-01-01 | 2016-01-01 | 580149 | TRUE | TRUE | RFP | 527045 |  | Charles Wienrank | 398152 | In-State University | 375000 | 449750 | Hasan Ozer | PVMT
178 | R27-171 Research Project Start! | R27-171 | Load Factors | 3 | R27-171: Load Factors | FY18-FY24 IGA |  | Audrey Donoho | 2015-12-01 | 2015-12-01 | Audrey Donoho | 2015-12-01 | 2015-12-01 | 363173 | TRUE | TRUE | RFP | 353343 |  | Timothy Armbrecht | 268132 | In-State University | 225000 | 300000 | Gongkang Fu | BAF
179 | R27-172 Research Project Start! | R27-172 | Soybean | 3 | R27-172: Soybean | FY18-FY24 IGA |  | ICT Project Management | 2016-01-01 | 2016-01-01 | ICT Project Management | 2016-01-01 | 2016-01-01 | 158431 | TRUE | TRUE | RFP | 156952 |  | Mark Seppelt | 120140 | Out-of-State University | 120140 | 100000 | Ronald Gibbons | ENV
180 | R27-173 Research Project Cancelled! | R27-173 | Thermodynamics of HMA Plant Production with ABR Mixes | 2 | R27-173: Thermodynamics of HMA Plant Production with ABR Mixes | Cancelled |  | Nick York | 2014-11-01 | 2014-11-01 | Nick York [0.00 %] | 2014-11-01 | 2014-11-01 | 0 | TRUE | TRUE | [9 empty] | PVMT
181 | R27-174 Research Project Start! | R27-174 | Chip, Crack & Seal | 2 | R27-174: Chip, Crack & Seal | FY18-FY24 IGA |  | ICT Project Management | 2016-01-01 | 2016-01-01 | ICT Project Management | 2016-01-01 | 2016-01-01 | 350625 | TRUE | TRUE | PI Direct | 337953 |  | Tim Peters | 256588 | In-State University | 225000 | 300000 | Mohammad Hossain | PVMT
182 | R27-175 Research Project Start! | R27-175 | Long-Term Aging | 2 | R27-175: Long-Term Aging | FY18-FY24 IGA |  | ICT Project Management | 2017-01-01 | 2017-01-01 | ICT Project Management | 2017-01-01 | 2017-01-01 | 916752 | TRUE | TRUE | PI Direct | 880546 | 2772.8 | Tom Zehr | 700675 | In-State University | 449976 | 599968 | Imad Al-Qadi | PVMT | 1603
183 | R27-176 Research Project Start! | R27-176 | Noise Barriers | 2 | R27-176: Noise Barriers | FY18-FY24 IGA |  | Audrey Donoho | 2017-09-01 | 2017-09-01 | Audrey Donoho | 2017-09-01 | 2017-09-01 | 96230 | TRUE | TRUE | PI Direct | 115384 |  | Scott Stitt | 86538 | In-State University | 86538 | 115384 | Khaled El-Rayes | ENV
184 | R27-177 Research Project Start! | R27-177 | Dynamic Travel Time | 2 | R27-177: Dynamic Travel Time | FY18-FY24 IGA |  | Audrey Donoho | 2017-09-01 | 2017-09-01 | Audrey Donoho | 2017-09-01 | 2017-09-01 | 286552 | TRUE | TRUE | PI Direct | 258892 |  | Kevin Price | 194170 | In-State University | 129807.75 | 173077 | Kouros Mohammadian | PLAN
185 | R27-178-1 Research Project Start! | R27-178-1 | Bridge Decks Phase III | 2 | R27-178-1: Bridge Decks Phase III | FY18-FY24 IGA |  | Brian Lorbiecki | 2017-09-15 | 2017-09-15 | Brian Lorbiecki | 2017-09-15 | 2017-09-15 | 216456 | TRUE | TRUE | PI Direct | 200000 |  | James Krstulovich | 153125 | In-State University & Out-of-State University | 146875.5 | 195834 | Paramita Mondal | BAF
186 | R27-178-2 Research Project Start! | R27-178-2 | Bridge Decks Phase III Hindi | 2 | R27-178-2: Bridge Decks Phase III Hindi | FY18-FY24 IGA |  | Brian Lorbiecki | 2017-09-15 | 2017-09-15 | Brian Lorbiecki | 2017-09-15 | 2017-09-15 | 232933 | TRUE | TRUE | PI Direct | 233700 |  | James Krstulovich | 178400 | Out-of-State University | 146875.5 | 195834 | Riyadh Hindi | BAF
187 | R27-179 Research Project Start! | R27-179 | Beam Rotation | 2 | R27-179: Beam Rotation | FY18-FY24 IGA |  | Brian Lorbiecki | 2017-09-15 | 2017-09-15 | Audrey Donoho | 2017-09-15 | 2017-09-15 | 216890 | TRUE | TRUE | PI Direct | 262500 |  | Douglas Dirks / Mark Thomson | 200000 | Out-of-State University | 200000 | 262500 | Riyadh Hindi | CON
188 | R27-180 Research Project Start! | R27-180 | SCM | 2 | R27-180: SCM | FY18-FY24 IGA |  | Audrey Donoho | 2017-10-01 | 2017-10-01 | Audrey Donoho | 2017-10-01 | 2017-10-01 | 773177 | TRUE | TRUE | PI Direct | 750000 | 346.6 | James Krstulovich | 565626 | In-State University & Out-of-State University | 302907 | 403846 | Jeffery Roesler | PVMT | 16
189 | R27-181 Research Project Start! | R27-181 | StreamStats | 2 | R27-181: StreamStats | FY18-FY24 IGA |  | Brian Lorbiecki | 2017-10-01 | 2017-10-01 | Brian Lorbiecki | 2017-10-01 | 2017-10-01 | 598450 | TRUE | TRUE | PI Direct | 596300 |  | Neil VanBebber | 402880 | Federal Organization | 372880 | 426300 | Thomas Over | BAF
190 | R27-182 Research Project Start! | R27-182 | Riprap Phase I | 2 | R27-182: Riprap Phase I | FY18-FY24 IGA |  | Audrey Donoho | 2018-01-01 | 2018-01-01 | Audrey Donoho | 2018-01-01 | 2018-01-01 | 428332 | TRUE | TRUE | PI Direct | 392716 | 1039.8 | Andrew Stolba | 294537 | In-State University | 294537 | 392716 | Erol Tutumluer | PVMT | 5
191 | R27-183-HS Research Project Start! | R27-183-HS | Contaminated Soil | 3 | R27-183-HS: Contaminated Soil | FY18-FY24 IGA |  | Audrey Donoho | 2018-02-01 | 2018-02-01 | Audrey Donoho | 2018-02-01 | 2018-02-01 | 550665 | TRUE | TRUE | RFP | 611898 |  | Douglas Dirks / James Curtis | 461826 | In-State University & Out-of-State University | 374778 | 512500 | Amanda Hohner | ENV
192 | R27-184 Research Project Cancelled! | R27-184 | Evaluating the Beneficial Effects of Winter Maintenance Best Practices | 2 | R27-184: Evaluating the Beneficial Effects of Winter Maintenance Best Practices | Cancelled |  | Nick York | 2017-10-31 | 2017-10-31 | Nick York [0.00 %] | 2017-10-31 | 2017-10-31 | 0 | TRUE | TRUE | [9 empty] | OPS
193 | R27-185 Research Project Cancelled! | R27-185 | Evaluation of the HMA Resurfacing Policy for State Maintained Highways | 2 | R27-185: Evaluation of the HMA Resurfacing Policy for State Maintained Highways | Cancelled |  | Nick York | 2017-11-17 | 2017-11-17 | Nick York [0.00 %] | 2017-11-17 | 2017-11-17 | 0 | TRUE | TRUE | [9 empty] | PVMT
194 | R27-186 Research Project Start! | R27-186 | Work Zone | 3 | R27-186: Work Zone | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-02-01 | 2018-02-01 | Brian Lorbiecki | 2018-02-01 | 2018-02-01 | 263956 | TRUE | TRUE | RFP | 262500 |  | Juan Pava | 198479 | In-State University | 198479 | 262500 | Kerrie Schattler | SAF
195 | R27-187 Research Project Start! | R27-187 | Surface Treatments | 3 | R27-187: Surface Treatments | FY18-FY24 IGA |  | Audrey Donoho | 2018-02-01 | 2018-02-01 | Audrey Donoho | 2018-02-01 | 2018-02-01 | 60511 | TRUE | TRUE | RFP | 209845 |  | Frank Sharpe | 159168 | Out-of-State University | 159168 | 260668 | Xianming Shi | SAF
196 | R27-188 Research Project Start! | R27-188 | Drilled Shaft | 3 | R27-188: Drilled Shaft | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-02-01 | 2018-02-01 | Brian Lorbiecki | 2018-02-01 | 2018-02-01 | 493820 | TRUE | TRUE | RFP | 537551 |  | Michael Short | 405289 | In-State University | 312616 | 448027 | Timothy Stark | BAF
197 | R27-189 Research Project Start! | R27-189 | QCP/PFP | 2 | R27-189: QCP/PFP | FY18-FY24 IGA |  | Audrey Donoho | 2018-01-01 | 2018-01-01 | Audrey Donoho | 2018-01-01 | 2018-01-01 | 606971 | TRUE | TRUE | PI Direct | 572397 | 433.25 | Jim Trepanier | 457917 | In-State University | 457917 | 521297 | Imad Al-Qadi | PVMT | 111
198 | R27-190 Research Project Start! | R27-190 | Perimeter Barriers | 2 | R27-190: Perimeter Barriers | FY18-FY24 IGA |  | Audrey Donoho | 2018-05-16 | 2018-05-16 | Audrey Donoho | 2018-05-16 | 2018-05-16 | 290219 | TRUE | TRUE | PI Direct | 299997 |  | Michael Brownlee | 224998 | In-State University | 224998 | 299997 | Rabin Bhattarai | ENV
199 | R27-191 Research Project Start! | R27-191 | Snow Fences | 2 | R27-191: Snow Fences | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-08-16 | 2018-08-16 | Brian Lorbiecki | 2018-08-16 | 2018-08-16 | 189649 | TRUE | TRUE | PI Direct | 187500 |  | Mark Bloome / Laura Shanley | 143750 | In-State University | 143750 | 187500 | Yan Qi | OPS
200 | R27-192 Research Project Start! | R27-192 | Maritime Freight | 2 | R27-192: Maritime Freight | FY18-FY24 IGA |  | Audrey Donoho | 2018-05-16 | 2018-05-16 | Audrey Donoho | 2018-05-16 | 2018-05-16 | 434138 | TRUE | TRUE | PI Direct | 375000 |  | B J Murray / Clayton Stambaugh | 281250 | In-State University | 281250 | 375000 | P.S. Sriraj | PLAN
201 | R27-193-1 Research Project Start! | R27-193-1 | CIR and FDR | 2 | R27-193-1: CIR and FDR | FY18-FY24 IGA |  | Audrey Donoho | 2018-07-16 | 2018-07-16 | Audrey Donoho | 2018-07-16 | 2018-07-16 | 110656 | TRUE | TRUE | PI Direct | 125220 | 0 | Charles Wienrank | 100176 | In-State University | 100176 | 125220 | Marshall Thompson | PVMT | 94
202 | R27-193-2 Research Project Start! | R27-193-2 | Flexible Pavements (Rubblization) | 2 | R27-193-2: Flexible Pavements (Rubblization) | FY18-FY24 IGA |  | Audrey Donoho | 2018-07-16 | 2018-07-16 | Audrey Donoho | 2018-07-16 | 2018-07-16 | 98628 | TRUE | TRUE | PI Direct | 125220 | 0 | Charles Wienrank | 100176 | In-State University | 100176 | 125220 | Marshall Thompson | PVMT | 261
203 | R27-193-3 Research Project Start! | R27-193-3 | Geosynthetics | 2 | R27-193-3: Geosynthetics | FY18-FY24 IGA |  | Audrey Donoho | 2018-08-16 | 2018-08-16 | Audrey Donoho | 2018-08-16 | 2018-08-16 | 216345 | TRUE | TRUE | PI Direct | 198520 |  | Heather Shoup / Veniecy Pearman-Green | 138964 | In-State University | 138964 | 198520 | Erol Tutumluer | PVMT
204 | R27-193-4 Research Project Start! | R27-193-4 | JCPC | 2 | R27-193-4: JCPC | FY18-FY24 IGA |  | Audrey Donoho | 2018-08-16 | 2018-08-16 | Audrey Donoho | 2018-08-16 | 2018-08-16 | 159109 | TRUE | TRUE | PI Direct | 152047 |  | Charles Wienrank | 106433 | In-State University | 106433 | 152047 | Jeffery Roesler | PVMT
205 | R27-193-5 Research Project Start! | R27-193-5 | M-E Pavement Design | 2 | R27-193-5: M-E Pavement Design | FY18-FY24 IGA |  | Audrey Donoho | 2019-06-16 | 2019-06-16 | Audrey Donoho | 2019-06-16 | 2019-06-16 | 81636 | TRUE | TRUE | PI Direct | 74497 |  | Heather Shoup | 55873 | In-State University | 55873 | 74497 | Erol Tutumluer | PVMT
206 | R27-193-6 Research Project Start! | R27-193-6 | Stabilized Support Layers | 2 | R27-193-6: Stabilized Support Layers | FY18-FY24 IGA |  | Audrey Donoho | 2019-10-16 | 2019-10-16 | Audrey Donoho | 2019-10-16 | 2019-10-16 | 98071 | TRUE | TRUE | PI Direct | 89322 | 86.65 | Charles Wienrank | 66992 | In-State University | 55873 | 74497 | Jeffery Roesler | PVMT | 5
207 | R27-194 Research Project Start! | R27-194 | Steel Bridges | 2 | R27-194: Steel Bridges | Open |  | Brian Lorbiecki | 2018-07-01 | 2018-07-01 | Brian Lorbiecki | 2018-07-01 | 2018-07-01 | 1446528 | TRUE | TRUE | PI Direct | 1238597 |  | Mark Shaffer | 928948 | In-State University | 450000 | 600000 | Larry Fahnestock | BAF
208 | R27-195 Research Project Start! | R27-195 | Reversible Lanes | 2 | R27-195: Reversible Lanes | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-10-16 | 2018-10-16 | Brian Lorbiecki | 2018-10-16 | 2018-10-16 | 356891 | TRUE | TRUE | PI Direct | 260777 |  | Matthew Daeda | 195581 | In-State University | 165000 | 220000 | Kouros Mohammadian | OPS
209 | R27-196-HS Research Project Start! | R27-196-HS | Rheology-Chemical | 2 | R27-196-HS: Rheology-Chemical | FY18-FY24 IGA |  | Audrey Donoho | 2018-07-01 | 2018-07-01 | Audrey Donoho | 2018-07-01 | 2018-07-01 | 394070 | TRUE | TRUE | PI Direct | 415873 | 173.3 | Kelly Senger | 311905 | In-State University | 262500 | 350000 | B.K. Sharma | PVMT | 283
210 | R27-197 Research Project Start! | R27-197 | TEC Bars | 2 | R27-197: TEC Bars | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-07-16 | 2018-07-16 | Brian Lorbiecki | 2018-07-16 | 2018-07-16 | 367709 | TRUE | TRUE | PI Direct | 357889 |  | Jayme Schiff / Dan Tobias | 268417 | In-State University | 225000 | 300000 | Bassem Andrawes | BAF
211 | R27-198 Research Project Start! | R27-198 | Horizontal Directional Drilling | 2 | R27-198: Horizontal Directional Drilling | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-07-16 | 2018-07-16 | Brian Lorbiecki | 2018-07-16 | 2018-07-16 | 406550 | TRUE | TRUE | PI Direct | 400000 |  | Heather Shoup / Joseph Angeli | 300000 | In-State University | 300000 | 400000 | Youssef Hashash | BAF
212 | R27-199 Research Project Start! | R27-199 | Smoother Roads | 3 | R27-199: Smoother Roads | FY18-FY24 IGA |  | Audrey Donoho | 2018-08-16 | 2018-08-16 | Audrey Donoho | 2018-08-16 | 2018-08-16 | 239650 | TRUE | TRUE | RFP | 237500 |  | John Senger / Douglas Dirks | 181250 | Private Industry | 181250 | 237500 | Hyung Lee | CON
213 | R27-200 Research Project Start! | R27-200 | Pedestrian Infrastructure | 3 | R27-200: Pedestrian Infrastructure | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-08-16 | 2018-08-16 | Brian Lorbiecki | 2018-08-16 | 2018-08-16 | 259497 | TRUE | TRUE | RFP | 248915 |  | Charles Abraham | 186686 | In-State University | 186686 | 248915 | Lindsay Braun | MFM
214 | R27-201 Research Project Start! | R27-201 | Older Population | 3 | R27-201: Older Population | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-08-16 | 2018-08-16 | Brian Lorbiecki | 2018-08-16 | 2018-08-16 | 110206 | TRUE | TRUE | RFP | 112500 |  | Cynthia Watters | 87500 | In-State University | 87500 | 112500 | Yan Qi | SAF
215 | R27-202 Research Project Start! | R27-202 | Roadway Lighting | 3 | R27-202: Roadway Lighting | FY18-FY24 IGA |  | Brian Lorbiecki | 2018-09-16 | 2018-09-16 | Brian Lorbiecki | 2018-09-16 | 2018-09-16 | 408370 | TRUE | TRUE | RFP | 406080 |  | Bernard Griffin / Marshall Metcalf | 307687 | Out-of-State University | 288679 | 384905 | Rajaram Bhagavathula | SAF
216 | R27-203 Research Project Start! | R27-203 | Truck Platooning | 2 | R27-203: Truck Platooning | FY18-FY24 IGA |  | Audrey Donoho | 2019-06-01 | 2019-06-01 | Audrey Donoho | 2019-06-01 | 2019-06-01 | 381964 | TRUE | TRUE | PI Direct | 380000 |  | Brian Hill / Charles Wienrank | 304000 | In-State University | 304000 | 380000 | Imad Al-Qadi | PVMT
217 | R27-204 Research Project Start! | R27-204 | HMA | 3 | R27-204: HMA | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-08-16 | 2019-08-16 | Audrey Donoho | 2019-08-16 | 2019-08-16 | 778862 | TRUE | TRUE | PI Direct | 767787 | 1473.05 | John Senger / Laura Heckel | 612048 | In-State University & Out-of-State University | 412500 | 550000 | Imad Al-Qadi | PVMT | 1631
218 | R27-205 Research Project Start! | R27-205 | Bridge Load Testing | 2 | R27-205: Bridge Load Testing | Complete - IDOT-ICT |  | Brian Lorbiecki | 2019-07-16 | 2019-07-16 | Brian Lorbiecki | 2019-07-16 | 2019-07-16 | 661083 | TRUE | TRUE | PI Direct | 741208 |  | Ruben Boehler | 555906 | In-State University | 337500 | 450000 | Bassem Andrawes | BAF
219 | R27-206 Research Project Start! | R27-206 | High Mast Towers | 3 | R27-206: High Mast Towers | FY18-FY24 IGA |  | Nick York | 2019-08-16 | 2019-08-16 | Brian Lorbiecki | 2019-08-16 | 2019-08-16 | 474245 | TRUE | TRUE | RFP | 447766 |  | Marshall Metcalf / Kyle Armstrong | 338950 | Out-of-State University | 275000 | 362500 | Ronald Gibbons | SAF
220 | R27-207 Research Project Start! | R27-207 | Solar Panels | 3 | R27-207: Solar Panels | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-08-16 | 2019-08-16 | Audrey Donoho | 2019-08-16 | 2019-08-16 | 354382 | TRUE | TRUE | RFP | 347500 |  | Christopher Schmidt | 263750 | In-State University | 263750 | 347500 | Brian Deal | PLAN
221 | R27-208 Research Project Start! | R27-208 | Resistivity | 3 | R27-208: Resistivity | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-08-16 | 2019-08-16 | Audrey Donoho | 2019-08-16 | 2019-08-16 | 355702 | TRUE | TRUE | RFP | 318276 |  | James Krstulovich | 244957 | Out-of-State University | 232457 | 322443 | Julie Hartell | PVMT
222 | R27-209 Research Project Cancelled! | R27-209 | Report Tracking of Public Maintenance Needs/Requests | 2 | R27-209: Report Tracking of Public Maintenance Needs/Requests | Cancelled |  | Nick York | 2019-05-16 | 2019-05-16 | Nick York [0.00 %] | 2019-05-16 | 2019-05-16 | 0 | TRUE | TRUE | [9 empty] | OPS
223 | R27-210 Research Project Start! | R27-210 | CPT for Illinois Subsurface | 3 | R27-210: CPT for Illinois Subsurface | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-08-16 | 2019-08-16 | Brian Lorbiecki [0.00 %] | 2019-08-16 | 2019-08-16 | 518944 | TRUE | TRUE | RFP | 512500 |  | Brian Laningham / Brad Hessing | 387500 | Out-of-State University | 387500 | 512500 | Jorge Macedo | BAF
224 | R27-211 Research Project Start! | R27-211 | Policy and Design for CAV's | 3 | R27-211: Policy and Design for CAV's | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-08-16 | 2019-08-16 | Audrey Donoho | 2019-08-16 | 2019-08-16 | 212076 | TRUE | TRUE | RFP | 215753 |  | Shawn Wilcockson | 161815 | In-State University | 135000 | 180000 | Arnab Chakraborty | PLAN
225 | R27-212 Research Project Start! | R27-212 | Dredge Material | 3 | R27-212: Dredge Material | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-09-01 | 2019-09-01 | Audrey Donoho | 2019-09-01 | 2019-09-01 | 68473 | TRUE | TRUE | RFP | 179998 |  | B J Murray / Heather Shoup | 134999 | In-State University | 112500 | 150000 | Timothy Stark | PLAN
226 | R27-213 Research Project Start! | R27-213 | Concrete Cure Times | 2 | R27-213: Concrete Cure Times | FY18-FY24 IGA |  | Nick York | 2020-08-16 | 2020-08-16 | Audrey Donoho | 2020-08-16 | 2020-08-16 | 239521 | TRUE | TRUE | PI Direct | 237856 | 103.98 | Douglas Dirks | 178392 | In-State University | 150000 | 200000 | Nishant Garg | CON | 9
227 | R27-214 Research Project Start! | R27-214 | RipRap Phase II | 2 | R27-214: RipRap Phase II | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-07-01 | 2020-07-01 | Audrey Donoho | 2020-07-01 | 2020-07-01 | 364578 | TRUE | TRUE | PI Direct | 390000 |  | Andrew Stolba | 292500 | In-State University | 292500 | 390000 | Erol Tutumluer | PVMT
228 | R27-215 Research Project Start! | R27-215 | E-Scooters | 2 | R27-215: E-Scooters | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-05-16 | 2020-05-16 | Brian Lorbiecki | 2020-05-16 | 2020-05-16 | 210769 | TRUE | TRUE | PI Direct | 200000 |  | Charles Abraham | 150000 | In-State University | 150000 | 200000 | Kouros Mohammadian | MFM
229 | R27-216 Research Project Start! | R27-216 | SMA | 2 | R27-216: SMA | Open |  | Brian Lorbiecki | 2020-08-16 | 2020-08-16 | Audrey Donoho | 2020-08-16 | 2020-08-16 | 1221299 | TRUE | TRUE | PI Direct | 1245362 | 1566.12 | Brian Hill | 996290 | In-State University | 560000 | 700000 | Imad Al-Qadi | PVMT | 2376.62
230 | R27-217 Research Project Start! | R27-217 | Rideshare Taxation | 2 | R27-217: Rideshare Taxation | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-08-16 | 2020-08-16 | Brian Lorbiecki | 2020-08-16 | 2020-08-16 | 142085 | TRUE | TRUE | PI Direct | 160000 |  | Charles Abraham | 120000 | In-State University | 120000 | 160000 | Lewis Lehe | MFM
231 | R27-218 Research Project Start! | R27-218 | Railroad-Highway Tool | 2 | R27-218: Railroad-Highway Tool | FY18-FY24 IGA |  | Nick York | 2020-05-16 | 2020-05-16 | Brian Lorbiecki | 2020-05-16 | 2020-05-16 | 393321 | TRUE | TRUE | PI Direct | 385000 |  | Bill Pearsall | 288750 | In-State University | 288750 | 385000 | P.S. Sriraj | SAF
232 | R27-219 Research Project Start! | R27-219 | Field Curing | 3 | R27-219: Field Curing | FY18-FY24 IGA |  | Nick York | 2020-08-16 | 2020-08-16 | Audrey Donoho | 2020-08-16 | 2020-08-16 | 265394 | TRUE | TRUE | RFP | 262497 |  | Douglas Dirks / James Krstulovich | 199998 | In-State University | 199998 | 262497 | Pranshoo Solanki | CON
233 | R27-220 Research Project Start! | R27-220 | Scour Depth Estimation | 3 | R27-220: Scour Depth Estimation | Open |  | Brian Lorbiecki | 2020-10-01 | 2020-10-01 | Brian Lorbiecki | 2020-10-01 | 2020-10-01 | 827578 | TRUE | TRUE | RFP | 963765 |  | Heather Shoup / Neil VanBebber | 728633 | In-State University | 350000 | 462500 | Abdolreza Osouli | BAF
234 | R27-221 Research Project Start! | R27-221 | Chip-Seal | 3 | R27-221: Chip-Seal | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-08-16 | 2020-08-16 | Audrey Donoho | 2020-08-16 | 2020-08-16 | 447586 | TRUE | TRUE | RFP | 445436 |  | John Senger | 337202 | Private Industry | 237500 | 312500 | Ahmad Alhasan | PVMT
235 | R27-222 Research Project Start! | R27-222 | Community Impact | 3 | R27-222: Community Impact | FY18-FY24 IGA |  | Audrey Donoho | 2020-08-16 | 2020-08-16 | Audrey Donoho | 2020-08-16 | 2020-08-16 | 198318 | TRUE | TRUE | RFP | 209128 |  | John Sherrill / Michael Vanderhoof | 161334 | In-State University & Out-of-State University | 161334 | 209128 | Lindsay Braun | ENV
236 | R27-223 Research Project Start! | R27-223 | CMFs for Contrast Pavement Markings | 3 | R27-223: CMFs for Contrast Pavement Markings | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-08-16 | 2020-08-16 | Brian Lorbiecki | 2020-08-16 | 2020-08-16 | 66362 | TRUE | TRUE | RFP | 91986 |  | Marshall Metcalf | 62005 | Out-of-State University | 62005 | 91986 | Michael Williamson | OPS
237 | R27-224 Research Project Start! | R27-224 | Bridge Deck Crack-Sealing | 3 | R27-224: Bridge Deck Crack-Sealing | FY18-FY24 IGA |  | Audrey Donoho | 2020-08-16 | 2020-08-16 | Audrey Donoho | 2020-08-16 | 2020-08-16 | 267650 | TRUE | TRUE | RFP | 313242 |  | Kelly Senger / Mark Shaffer | 234932 | In-State University | 299999 | 399998 | Nishant Garg | PVMT
238 | R27-225 Research Project Start! | R27-225 | Damaged Steel Girders | 3 | R27-225: Damaged Steel Girders | Open |  | Brian Lorbiecki | 2020-10-01 | 2020-10-01 | Brian Lorbiecki | 2020-10-01 | 2020-10-01 | 683244 | TRUE | TRUE | RFP | 931064 |  | Spencer Koehler | 698298 | In-State University | 375000 | 500000 | Larry Fahnestock | BAF
239 | R27-226 Research Project Start! | R27-226 | PPC Deck Beams with Transverse Cracks | 3 | R27-226: PPC Deck Beams with Transverse Cracks | Complete - IDOT-ICT |  | Brian Lorbiecki | 2020-08-16 | 2020-08-16 | Brian Lorbiecki | 2020-08-16 | 2020-08-16 | 350619 | TRUE | TRUE | RFP | 359704 |  | Robert Perkins | 269778 | In-State University | 225000 | 300000 | Bassem Andrawes | BAF
240 | R27-227 Research Project Start! | R27-227 | Cold Recycle Treatments | 2 | R27-227: Cold Recycle Treatments | FY18-FY24 IGA |  | Audrey Donoho | 2020-05-16 | 2020-05-16 | Audrey Donoho | 2020-05-16 | 2020-05-16 | 286389 | TRUE | TRUE | PI Direct | 295000 | 693.2 | John Senger | 236000 | In-State University | 236000 | 295000 | Imad Al-Qadi | PVMT | 683
241 | R27-228 Research Project Start! | R27-228 | Mobility | 2 | R27-228: Mobility | FY18-FY24 IGA |  | Nick York | 2021-04-16 | 2021-04-16 | Audrey Donoho | 2021-04-16 | 2021-04-16 | 400352 | TRUE | TRUE | PI Direct | 399745 |  | Michael Vanderhoof | 306059 | In-State University & Private Industry | 306059 | 399745 | Angeli Jayme | PLAN
242 | R27-229 Research Project Start! | R27-229 | Erosion Control Blankets | 2 | R27-229: Erosion Control Blankets | FY18-FY24 IGA |  | Nick York | 2021-05-16 | 2021-05-16 | Audrey Donoho | 2021-05-16 | 2021-05-16 | 224098 | TRUE | TRUE | PI Direct | 240000 |  | Scott Marlow | 180000 | In-State University | 180000 | 240000 | Rabin Bhattarai | ENV
243 | R27-230 Research Project Start! | R27-230 | CRCP Performance and Design | 2 | R27-230: CRCP Performance and Design | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-05-16 | 2021-05-16 | Audrey Donoho | 2021-05-16 | 2021-05-16 | 309387 | TRUE | TRUE | PI Direct | 285000 |  | Charles Wienrank | 213750 | In-State University | 213750 | 285000 | Jeffery Roesler | PVMT
244 | R27-231 Research Project Start! | R27-231 | Airfield Pavements | 2 | R27-231: Airfield Pavements | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-08-16 | 2021-08-16 | Audrey Donoho | 2021-08-16 | 2021-08-16 | 327724 | TRUE | TRUE | PI Direct | 368000 | 1386.4 | Bill Eves | 294400 | In-State University | 294400 | 368000 | Uthman Mohamed Ali | PVMT | 562
245 | R27-232 Research Project Start! | R27-232 | UHPC | 2 | R27-232: UHPC | Complete - IDOT-ICT |  | Brian Lorbiecki | 2021-07-01 | 2021-07-01 | Brian Lorbiecki | 2021-07-01 | 2021-07-01 | 337342 | TRUE | TRUE | PI Direct | 329680 |  | James Krstulovich / Mark Shaffer | 249355 | In-State University | 234375 | 309375 | Nishant Garg | BAF
246 | R27-233 Research Project Start! | R27-233 | M-E Design Procedures | 2 | R27-233: M-E Design Procedures | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-05-16 | 2021-05-16 | Audrey Donoho | 2021-05-16 | 2021-05-16 | 366737 | TRUE | TRUE | PI Direct | 350000 | 1386.4 | Charles Wienrank / Brian Hill | 262500 | In-State University | 262500 | 350000 | Ramez Hajj | PVMT | 490.7
247 | R27-234 Research Project Start! | R27-234 | Bender Elements | 2 | R27-234: Bender Elements | Complete - IDOT-ICT |  | Brian Lorbiecki | 2021-10-01 | 2021-10-01 | Audrey Donoho | 2021-10-01 | 2021-10-01 | 451093 | TRUE | TRUE | PI Direct | 436130 | 0 | Heather Shoup / Andrew Stolba | 327097 | In-State University | 256500 | 342000 | Erol Tutumluer | PVMT | 136.72
248 | R27-235 Research Project Start! | R27-235 | Cement-treated Base Pavements | 2 | R27-235: Cement-treated Base Pavements | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-07-01 | 2021-07-01 | Audrey Donoho | 2021-07-01 | 2021-07-01 | 103475 | TRUE | TRUE | PI Direct | 120000 |  | James Krstulovich / Tim Peters | 96000 | In-State University | 96000 | 120000 | Marshall Thompson | PVMT
249 | R27-236 Research Project Start! | R27-236 | EV Charging | 2 | R27-236: EV Charging | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-07-01 | 2021-07-01 | Brian Lorbiecki | 2021-07-01 | 2021-07-01 | 142008 | TRUE | TRUE | PI Direct | 238415 |  | Christopher Schmidt | 178812 | In-State University | 178812 | 238415 | Ria Kontou | PLAN
250 | R27-237 Research Project Cancelled! | R27-237 | 48-Volt Cabinets | 3 | R27-237: 48-Volt Cabinets | Cancelled |  | Brian Lorbiecki | 2021-07-09 | 2021-07-09 | Brian Lorbiecki [0.00 %] | 2021-07-09 | 2021-07-09 | 0 | TRUE | TRUE |  | 0 | 0 |  | 0 |  | 0 | 0 |  | OPS | 0
251 | R27-238 Research Project Start! | R27-238 | Deterioration Curves | 3 | R27-238: Deterioration Curves | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-08-01 | 2021-08-01 | Sree Venda | 2021-08-01 | 2021-08-01 | 214553 | TRUE | TRUE | RFP | 212497 |  | William Beisner | 162498 | In-State University | 162498 | 212497 | Gongkang Fu | BAF
252 | R27-239 Research Project Start! | R27-239 | Commercial Vehicle Emission | 3 | R27-239: Commercial Vehicle Emission | FY18-FY24 IGA |  | Nick York | 2021-08-16 | 2021-08-16 | Brian Lorbiecki | 2021-08-16 | 2021-08-16 | 487110 | TRUE | TRUE | RFP | 500000 |  | Christopher Schmidt | 375000 | In-State University | 375000 | 500000 | Jane Lin | PLAN
253 | R27-240 Research Project Start! | R27-240 | Low Traffic Volume Roadways | 3 | R27-240: Low Traffic Volume Roadways | FY18-FY24 IGA |  | Nick York | 2021-09-01 | 2021-09-01 | Brian Lorbiecki | 2021-09-01 | 2021-09-01 | 266026 | TRUE | TRUE | RFP | 261610 |  | Laura Shanley / Tim Peters | 199332 | Private Industry | 199332 | 261610 | Arudi Rajagopal | OPS
254 | R27-241 Research Project Start! | R27-241 | Air Mobility | 3 | R27-241: Air Mobility | FY18-FY24 IGA |  | Nick York | 2021-09-01 | 2021-09-01 | Brian Lorbiecki | 2021-09-01 | 2021-09-01 | 467510 | TRUE | TRUE | RFP | 462500 |  | William Viste | 350000 | In-State University | 350000 | 462500 | Hani Mahmassani | PLAN
255 | R27-242 Research Project Start! | R27-242 | Accelerated Bridge Construction | 3 | R27-242: Accelerated Bridge Construction | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-08-16 | 2021-08-16 | Sree Venda | 2021-08-16 | 2021-08-16 | 154334 | TRUE | TRUE | RFP | 149982 |  | Patrik Claussen | 112487 | In-State University | 112487 | 149982 | Khaled El-Rayes | BAF
256 | R27-243 Research Project Cancelled! | R27-243 | Pavement Friction | 2 | R27-243: Pavement Friction | Cancelled |  | Brian Lorbiecki | 2021-10-06 | 2021-10-06 | Audrey Donoho | 2021-10-06 | 2021-10-06 | 0 | TRUE | TRUE | [9 empty] | PVMT
257 | R27-244 Research Project Start! | R27-244 | MWD | 3 | R27-244: MWD | Open |  | Brian Lorbiecki | 2021-08-16 | 2021-08-16 | Sree Venda | 2021-08-16 | 2021-08-16 | 574167 | TRUE | TRUE | RFP | 662192 |  | Brad Hessing / Scott Kassel | 499769 | In-State University & Out-of-State University | 424998 | 562500 | Ann Christine Sychterz | BAF
258 | R27-245-HS Research Project Start! | R27-245-HS | Rumble Strip Designs | 3 | R27-245-HS: Rumble Strip Designs | Complete - IDOT-ICT |  | Nick York | 2021-11-01 | 2021-11-01 | Brian Lorbiecki | 2021-11-01 | 2021-11-01 | 695990 | TRUE | TRUE | RFP | 662478 |  | Benjamin Sperry | 529982 | In-State University | 150000 | 200000 | Khaled El-Rayes | SAF
259 | R27-246 Research Project Start! | R27-246 | Smart Work Zones | 2 | R27-246: Smart Work Zones | FY18-FY24 IGA |  | Nick York | 2022-01-01 | 2022-01-01 | Brian Lorbiecki | 2022-01-01 | 2022-01-01 | 215127 | TRUE | TRUE | PI Direct | 219912 |  | Juan Pava | 164934 | In-State University | 164934 | 219912 | Khaled El-Rayes | SAF
260 | R27-247 Research Project Start! | R27-247 | Surface Friction | 2 | R27-247: Surface Friction | Open |  | Brian Lorbiecki | 2022-07-01 | 2022-07-01 | Audrey Donoho | 2022-07-01 | 2022-07-01 | 559790 | TRUE | TRUE | PI Direct | 750000 | 2512.85 | John Senger | 600000 | In-State University | 600000 | 750000 | Imad Al-Qadi | PVMT | 130.25
261 | R27-248 Research Project Start! | R27-248 | Dolomite Aggregate | 2 | R27-248: Dolomite Aggregate | Complete - IDOT-ICT |  | Brian Lorbiecki | 2022-07-01 | 2022-07-01 | Audrey Donoho | 2022-07-01 | 2022-07-01 | 631770 | TRUE | TRUE | PI Direct | 645974 | 194.3 | Andrew Stolba | 484481 | In-State University | 292500 | 390000 | Erol Tutumluer | PVMT | 251.55
262 | R27-249 Research Project Start! | R27-249 | Mobile RWIS Phase 2 | 2 | R27-249: Mobile RWIS Phase 2 | Open |  | Nick York | 2022-07-01 | 2022-07-01 | Brian Lorbiecki [0.00 %] | 2022-07-01 | 2022-07-01 | 642060 | TRUE | TRUE | PI Direct | 836585 |  | Keith Donovan | 627439 | In-State University | 472748 | 630330 | Khaled El-Rayes | OPS
263 | R27-250 Research Project Start! | R27-250 | Delta G | 2 | R27-250: Delta G | Published - IDOT-ICT |  | Brian Lorbiecki | 2022-08-16 | 2022-08-16 | Audrey Donoho | 2022-08-16 | 2022-08-16 | 575818 | TRUE | TRUE | PI Direct | 540443 | 1386.4 | Kelly Senger / Brian Hill | 432354 | In-State University | 432354 | 540443 | Imad Al-Qadi | PVMT | 971.7
264 | R27-251 Research Project Start! | R27-251 | Traffic Signals | 3 | R27-251: Traffic Signals | Complete - IDOT-ICT |  | Nick York | 2022-08-16 | 2022-08-16 | Brian Lorbiecki | 2022-08-16 | 2022-08-16 | 173506 | TRUE | TRUE | RFP | 198243 |  | Kenneth Davis / Kyle Armstrong | 154493 | In-State University | 143750 | 187500 | Ryan Fries | OPS
265 | R27-252 Research Project Start! | R27-252 | Increased Torque | 3 | R27-252: Increased Torque | Complete - IDOT-ICT |  | Brian Lorbiecki | 2022-08-16 | 2022-08-16 | Audrey Donoho | 2022-08-16 | 2022-08-16 | 461132 | TRUE | TRUE | RFP | 418052 | 173.3 | John Senger | 332051 | In-State University & Out-of-State University | 326500 | 412500 | Angeli Jayme | PVMT | 7
266 | R27-253 Research Project Cancelled! | R27-253 | Bicycle Detection | 3 | R27-253: Bicycle Detection | Cancelled |  | Brian Lorbiecki | 2022-09-14 | 2022-09-14 | Brian Lorbiecki [0.00 %] | 2022-09-14 | 2022-09-14 |  | TRUE | TRUE | [9 empty] | MFM
267 | R27-254 Research Project Start! | R27-254 | Equipment Rental | 3 | R27-254: Equipment Rental | Complete - IDOT-ICT |  | Nick York | 2022-08-16 | 2022-08-16 | Audrey Donoho | 2022-08-16 | 2022-08-16 | 189444 | TRUE | TRUE | RFP | 273243 |  | Douglas Dirks / Tim Peters | 210742 | In-State University & Out-of-State University | 210742 | 273243 | Zheyong Bian | CON
268 | R27-255 Research Project Start! | R27-255 | Seeding Standards | 3 | R27-255: Seeding Standards | Complete - IDOT-ICT |  | Nick York | 2022-08-16 | 2022-08-16 | Audrey Donoho | 2022-08-16 | 2022-08-16 | 252137 | TRUE | TRUE | RFP | 269953 | 0 | Scott Hall | 202465 | In-State University | 202465 | 269953 | Jeffrey Matthews | ENV | 0
269 | R27-256 Research Project Start! | R27-256 | Work Zone Training | 2 | R27-256: Work Zone Training | FY18-FY24 IGA |  | Nick York | 2022-04-16 | 2022-04-16 | Brian Lorbiecki | 2022-04-16 | 2022-04-16 | 36741 | TRUE | TRUE | PI Direct | 52940 |  | Juan Pava | 39705 | In-State University | 39705 | 52940 | Ray Benekohal | SAF
270 | R27-257 Research Project Start! | R27-257 | Seismic Events | 2 | R27-257: Seismic Events | Open |  | Brian Lorbiecki | 2024-01-01 | 2024-01-01 | Brian Lorbiecki [0.00 %] | 2024-01-01 | 2024-01-01 | 80371 | TRUE | TRUE | PI Direct | 281586 |  | Mark Shaffer | 211189 | In-State University | 211189 | 281586 | James LaFave | BAF
271 | R27-258 Research Project Start! | R27-258 | Digital Alert Systems | 2 | R27-258: Digital Alert Systems | Published - IDOT-ICT |  | Nick York | 2023-03-01 | 2023-03-01 | Nick York [0.00 %] | 2023-03-01 | 2023-03-01 | 421229 | TRUE | TRUE | PI Direct | 444344 |  | Juan Pava | 333258 | In-State University | 187500 | 250000 | Alireza Talebpour | SAF
272 | R27-259 Research Project Start! | R27-259 | Transit Signal Priority | 2 | R27-259: Transit Signal Priority | Complete - IDOT-ICT |  | Nick York | 2023-07-01 | 2023-07-01 | Nick York [0.00 %] | 2023-07-01 | 2023-07-01 | 351226 | TRUE | TRUE | PI Direct | 321487 |  | Charles Abraham / Taqhi Mohammed | 246486 | In-State University | 225000 | 310744 | Kouros Mohammadian | MFM
273 | R27-260 Research Project Start! | R27-260 | TEC Rebars | 2 | R27-260: TEC Rebars | Open |  | Brian Lorbiecki | 2023-08-16 | 2023-08-16 | Brian Lorbiecki [0.00 %] | 2023-08-16 | 2023-08-16 | 673188 | TRUE | TRUE | PI Direct | 1093340 |  | Mark Shaffer | 820005 | In-State University | 562500 | 750000 | Bassem Andrawes | BAF | 2
274 | R27-261 Research Project Cancelled! | R27-261 | Urban Mobility | 2 | R27-261: Urban Mobility | Cancelled |  | Nick York | 2022-12-13 | 2022-12-13 | Nick York [0.00 %] | 2022-12-13 | 2022-12-13 | 0 | TRUE | TRUE | [9 empty] | MFM
275 | R27-262 Research Project Start! | R27-262 | Geotech Asset Management | 3 | R27-262: Geotech Asset Management | Open |  | Brian Lorbiecki | 2023-08-16 | 2023-08-16 | Brian Lorbiecki [0.00 %] | 2023-08-16 | 2023-08-16 | 364484 | TRUE | TRUE | RFP | 521486 |  | Heather Shoup / Laura Heckel | 396486 | Private Industry | 375000 | 510743 | Mike Prohaska | PVMT
276 | R27-263 Research Project Start! | R27-263 | Profiler Certification | 3 | R27-263: Profiler Certification | Open |  | Brian Lorbiecki | 2024-08-01 | 2024-08-01 | Brian Lorbiecki [0.00 %] | 2024-08-01 | 2024-08-01 | 581406 | TRUE | TRUE | RFP | 381981 |  | John Senger | 289172 | Private Industry | 278429 | 371238 | Steve Karamihas | PVMT
277 | R27-264 Research Project Start! | R27-264 | Friction Management | 4 | R27-264: Friction Management | Open |  | Brian Lorbiecki | 2023-09-01 | 2023-09-01 | Brian Lorbiecki [0.00 %] | 2023-09-01 | 2023-09-01 | 285737 | TRUE | TRUE | RFP | 360745 |  | John Senger | 273245 | In-State University | 273245 | 360745 | Yanfeng Ouyang | PVMT
278 | R27-265 Research Project Start! | R27-265 | Integral Abutment Testing | 2 | R27-265: Integral Abutment Testing | Open |  | Brian Lorbiecki | 2024-01-01 | 2024-01-01 | ICT Project Management | 2024-01-01 | 2024-01-01 | 254826 | TRUE | TRUE | PI Direct | 540254 |  | Mark Shaffer / Yazan Alshawabkeh | 406159 | In-State University | 406159 | 541546 | Mohsen Issa | BAF
279 | R27-266 Research Project Start! | R27-266 | Energy Harvesting | 2 | R27-266: Energy Harvesting | Open |  | Brian Lorbiecki | 2024-05-16 | 2024-05-16 | Brian Lorbiecki [0.00 %] | 2024-05-16 | 2024-05-16 | 353083 | TRUE | TRUE | PI Direct | 575225 | 640 | John Senger | 460180 | In-State University | 383779 | 479724 | Imad Al-Qadi | PVMT | 591.33
280 | R27-267 Research Project Start! | R27-267 | Flexible Pavement | 2 | R27-267: Flexible Pavement | Open |  | Brian Lorbiecki | 2024-07-01 | 2024-07-01 | Brian Lorbiecki [0.00 %] | 2024-07-01 | 2024-07-01 | 188119 | TRUE | TRUE | PI Direct | 400000 | 251 | Charles Wienrank / Brian Hill | 300000 | In-State University | 300000 | 400000 | Ramez Hajj | PVMT | 249.83
281 | R27-268 Research Project Start! | R27-268 | Quarry By-Product Fines | 4 | R27-268: Quarry By-Product Fines | Open |  | Brian Lorbiecki | 2024-08-16 | 2024-08-16 | Brian Lorbiecki [0.00 %] | 2024-08-16 | 2024-08-16 | 173645 | TRUE | TRUE | PI Direct | 367000 |  | John Senger / Andrew Stolba | 275250 | In-State University | 275250 | 367000 | Erol Tutumluer | PVMT | 16.75
282 | R27-269 Research Project Start! | R27-269 | Weigh-In-Motion | 3 | R27-269: Weigh-In-Motion | Open |  | Brian Lorbiecki | 2024-08-16 | 2024-08-16 | Brian Lorbiecki [0.00 %] | 2024-08-16 | 2024-08-16 | 85092 | TRUE | TRUE | RFP | 500000 | 0 | Mark Shaffer | 375000 | In-State University | 385743 | 500000 | Mohamad Alipour | BAF | 0
283 | R27-270 Research Project Start! | R27-270 | Traffic Control Devices | 3 | R27-270: Traffic Control Devices | Open |  | Nick York | 2024-08-16 | 2024-08-16 | Nick York [0.00 %] | 2024-08-16 | 2024-08-16 | 56938 | TRUE | TRUE | RFP | 299817 |  | Douglas Dirks | 224863 | In-State University | 235743 | 299817 | Khaled El-Rayes | CON
284 | R27-271 Research Project Start! | R27-271 | Air Quality Screening | 3 | R27-271: Air Quality Screening | Open |  | Nick York | 2024-08-16 | 2024-08-16 | Nick York [0.00 %] | 2024-08-16 | 2024-08-16 | 117747 | TRUE | TRUE | RFP | 300000 |  | Benjamin Sperry | 225000 | In-State University | 235743 | 300000 | Jane Lin | ENV
285 | R27-272 Research Project Start! | R27-272 | Gray Areas | 3 | R27-272: Gray Areas | Open |  | Nick York | 2024-08-16 | 2024-08-16 | Nick York [0.00 %] | 2024-08-16 | 2024-08-16 | 148254 | TRUE | TRUE | RFP | 299771 |  | Hannah Schmidt / Charles Abraham | 224828 | In-State University | 235743 | 299771 | Bumsoo Lee | MFM
286 | R27-273 Research Project Start! | R27-273 | Emissions Transparency | 3 | R27-273: Emissions Transparency | Open |  | Nick York | 2024-08-16 | 2024-08-16 | Nick York [0.00 %] | 2024-08-16 | 2024-08-16 | 114127 | TRUE | TRUE | RFP | 300000 |  | Christopher Schmidt | 225000 | In-State University | 225000 | 300000 | Sybil Derrible | PLAN
287 | R27-274 Research Project Start! | R27-274 | Free and Reduced Fares | 3 | R27-274: Free and Reduced Fares | Open |  | Nick York | 2024-08-16 | 2024-08-16 | Nick York [0.00 %] | 2024-08-16 | 2024-08-16 | 149204 | TRUE | TRUE | RFP | 400000 |  | Hannah Schmidt | 300000 | In-State University | 310743 | 400000 | Kouros Mohammadian | PLAN
288 | R27-275 Research Project Start! | R27-275 | Seismic Ground Motions | 3 | R27-275: Seismic Ground Motions | Open |  | Brian Lorbiecki | 2025-08-16 | 2025-08-16 | ICT Project Management | 2025-08-16 | 2025-08-16 | 21095 | TRUE | TRUE | PI Direct | 799999 |  | Heather Shoup / Mark Shaffer | 599999 | In-State University | 590821 | 799999 | Youssef Hashash | BAF
289 | R27-276 Research Project Start! | R27-276 | TCE Alternatives | 2 | R27-276: TCE Alternatives | Open |  | Brian Lorbiecki | 2024-10-01 | 2024-10-01 | ICT Project Management | 2024-10-01 | 2024-10-01 | 139089 | TRUE | TRUE | PI Direct | 481011 |  | Kelly Senger | 394957 | In-State University | 394957 | 481011 | Ramez Hajj | PVMT | 172.33
290 | R27-277 Research Project Start! | R27-277 | Traffic Factor Equations | 2 | R27-277: Traffic Factor Equations | Open |  | Brian Lorbiecki | 2025-01-01 | 2025-01-01 | ICT Project Management | 2025-01-01 | 2025-01-01 | 88319 | TRUE | TRUE | PI Direct | 488510 |  | Charles Wienrank | 390808 | In-State University | 390808 | 488510 | Imad Al-Qadi | PVMT | 0.5
291 | R27-278 Research Project Start! | R27-278 | Aggregate Materials Requirements | 2 | R27-278: Aggregate Materials Requirements | Open |  | Brian Lorbiecki | 2025-08-16 | 2025-08-16 | ICT Project Management | 2025-08-16 | 2025-08-16 | 0 | TRUE | TRUE | PI Direct | 970846 |  | Andrew Stolba / Heather Shoup | 733506 | In-State University | 733506 | 970846 | Erol Tutumluer | PVMT
292 | R27-279 Research Project Start! | R27-279 | SER Phase II | 2 | R27-279: SER Phase II | Open |  | Nick York | 2025-07-01 | 2025-07-01 | Nick York [0.00 %] | 2025-07-01 | 2025-07-01 | 36510 | TRUE | TRUE | PI Direct | 300000 |  | Stephane Seck-Birhame / Victoria Barrett | 225000 | In-State University | 225000 | 300000 | Alireza Talebpour | SAF
293 | R27-280 Research Project Start! | R27-280 | EV Charging Network | 2 | R27-280: EV Charging Network | Open |  | Nick York | 2025-07-01 | 2025-07-01 | Nick York [0.00 %] | 2025-07-01 | 2025-07-01 | 32554 | TRUE | TRUE | PI Direct | 280000 |  | Jason Lange | 210000 | In-State University | 210000 | 280000 | Ria Kontou | PLAN
294 | R27-281 Research Project Start! | R27-281 | IL-Pave | 2 | R27-281: IL-Pave | Open |  | Brian Lorbiecki | 2025-08-16 | 2025-08-16 | ICT Project Management | 2025-08-16 | 2025-08-16 | 104500 | TRUE | TRUE | PI Direct | 960000 |  | John Senger | 768000 | In-State University | 720000 | 960000 | Imad Al-Qadi | PVMT
295 | R27-282 Research Project Start! | R27-282 | Wearable Safety Lights | 3 | R27-282: Wearable Safety Lights | Open |  | Nick York | 2025-08-16 | 2025-08-16 | Nick York [0.00 %] | 2025-08-16 | 2025-08-16 | 0 | TRUE | TRUE | RFP | 196485 | 0 | Greg Gurski / Keith Donovan | 152735 | Out-of-State University | 152735 | 196485 | Ronald Gibbons | SAF | 0
296 | R27-283 Research Project Start! | R27-283 | Right Turn on Red | 3 | R27-283: Right Turn on Red | Open |  | Nick York | 2025-08-16 | 2025-08-16 | Nick York [0.00 %] | 2025-08-16 | 2025-08-16 | 33213 | TRUE | TRUE | RFP | 171485 | 0 | Meiwu An | 133985 | Out-of-State University | 133985 | 171485 | Christopher Day | OPS | 0
297 | R27-284 Research Project Start! | R27-284 | MPO Performance Measures | 3 | R27-284: MPO Performance Measures | Open |  | Nick York | 2025-08-16 | 2025-08-16 | Nick York [0.00 %] | 2025-08-16 | 2025-08-16 | 23433 | TRUE | TRUE | RFP | 421487 | 0 | Bob Innis | 321486 | Out-of-State University | 300000 | 421487 | Yazan Abukhalil | PLAN | 0
298 | R27-285 Research Project Start! | R27-285 | Traffic Projection Tool | 3 | R27-285: Traffic Projection Tool | Open |  | Nick York | 2025-08-16 | 2025-08-16 | Nick York [0.00 %] | 2025-08-16 | 2025-08-16 | 51239 | TRUE | TRUE | RFP | 421485 | 0 | Mike Miller / William Morgan | 321485 | Out-of-State University | 321485 | 421485 | L.D. White | PLAN | 0
299 | R27-286 Research Project Start! | R27-286 | ATV/UTV Ordinanaces | 3 | R27-286: ATV/UTV Ordinanaces | Open |  | Nick York | 2025-08-16 | 2025-08-16 | Nick York [0.00 %] | 2025-08-16 | 2025-08-16 | 839 | TRUE | TRUE | RFP | 199917 | 0 | John Senger | 149938 | In-State University | 149938 | 199917 | Timothy Stark | SAF | 0
300 | R27-287 Research Project Start! | R27-287 | UHPC Scalability and Implementation | 2 | R27-287: UHPC Scalability and Implementation | Open |  | Brian Lorbiecki | 2025-08-16 | 2025-08-16 | ICT Project Management | 2025-08-16 | 2025-08-16 | 16281 | TRUE | TRUE | PI Direct | 521484 |  | Mark Shaffer | 396484 | In-State University | 383058 | 521484 | Nishant Garg | BAF
301 | R27-288 Research Project Start! | R27-288 | IL Pavement Feedback System | 2 | R27-288: IL Pavement Feedback System | Open |  | Brian Lorbiecki | 2026-03-01 | 2026-03-01 | ICT Project Management | 2026-03-01 | 2026-03-01 |  | TRUE | TRUE | PI Direct | 653944 |  | John Senger | 523155 | In-State University | 523155 | 653944 | Hong Lang | PVMT
302 | R27-289 Research Project Start! | R27-289 | Air Voids | 2 | R27-289: Air Voids | Pending - IDOT-ICT |  | Brian Lorbiecki | 2026-05-01 | 2026-05-01 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE | PI Direct | 965318 |  | Brian Hill | 772254 | In-State University | 772254 | 965318 | Imad Al-Qadi | PVMT
303 | R27-290 Research Project Start! | R27-290 | AI for Bridge Management | 2 | R27-290: AI for Bridge Management | Pending - IDOT-ICT |  | Brian Lorbiecki | 2026-05-16 | 2026-05-16 | Nick York [0.00 %], ICT Project Management [0.00 %] |  |  |  | TRUE | FALSE | PI Direct | 220000 |  | Paul Van Metre / Mark Shaffer | 165000 | In-State University | 165000 | 220000 | Nora El-Gohary | BAF
304 | R27-291 Research Project Start! | R27-291 | CRS Calculation Models | 2 | R27-291: CRS Calculation Models | Pending - IDOT-ICT |  | Brian Lorbiecki | 2026-08-16 | 2026-08-16 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE | PI Direct | 930000 |  | John Senger / Travis Lobmaster | 697500 | In-State University | 697500 | 930000 | Yanfeng Ouyang | PVMT
305 | R27-292 Research Project Start! | R27-292 | CRS for Pavement Treatments | 2 | R27-292: CRS for Pavement Treatments | Pending - IDOT-ICT |  | Brian Lorbiecki | 2026-05-16 | 2026-05-16 | Nick York [0.00 %], ICT Project Management [0.00 %] |  |  |  | TRUE | FALSE | PI Direct | 373000 |  | Laura Heckel / John Senger | 279750 | In-State University | 279750 | 373000 | Ramez Hajj | PVMT
306 | R27-293 Research Project Start! | R27-293 | LLM-STARS | 2 | R27-293: LLM-STARS | Pending - IDOT-ICT |  | Nick York | 2026-05-16 | 2026-05-16 | Nick York [0.00 %] |  |  |  | TRUE | FALSE | PI Direct | 400000 |  | Sheng Chen | 300000 | In-State University | 300000 | 400000 | Sybil Derrible | PLAN
307 | R27-294 Research Project Start! | R27-294 | Congestion Pricing | 3 | R27-294: Congestion Pricing | Pending - IDOT-ICT |  | Nick York | 2026-08-16 | 2026-08-16 | Nick York [0.00 %] |  |  |  | TRUE | FALSE | RFP | 521485 |  | Chuck Abraham | 425000 |  | 425000 | 521485 |  | MFM
308 | R27-295 Research Project Start! | R27-295 | Mussel Movement | 3 | R27-295: Mussel Movement | Pending - IDOT-ICT |  | Nick York | 2026-08-16 | 2026-08-16 | Nick York [0.00 %] |  |  |  | TRUE | FALSE | RFP | 1021485 |  | Felecia Hurley | 0 |  | 0 | 1021485 |  | ENV
309 | R27-296 Research Project Start! | R27-296 | C1157 Hydraulic Cements | 2 | R27-296: C1157 Hydraulic Cements | Pending - IDOT-ICT |  | Brian Lorbiecki | 2026-08-16 | 2026-08-16 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE | PI Direct | 930000 |  | James Krstulovich | 697500 | In-State University | 697500 | 930000 | Nishant Garg | PVMT
310 | R27-ALS Research Project Start! | R27-ALS | ATLAS Repairs and Upgrades | 2 | R27-ALS: ATLAS Repairs and Upgrades | Complete - IDOT-ICT |  | Kristi Anderson | 2020-08-01 | 2020-08-01 | Kristi Anderson | 2020-08-01 | 2020-08-01 | 883382 | TRUE | TRUE | PI Direct | 951786 |  | John Senger | 761429 | In-State University | 400000 | 500000 | Imad Al-Qadi | Other / Department Wide
311 | R27-ET2 (FY18-24 IGA) Research Project Start! | R27-ET2 (FY18-24 IGA) | R27-ET2 (FY18-24 IGA) | 2 | R27-ET2 (FY18-24 IGA): R27-ET2 (FY18-24 IGA) | FY18-FY24 IGA |  | Kristi Anderson | 2017-07-01 | 2017-07-01 | Kristi Anderson | 2017-07-01 | 2017-07-01 | 689358 | TRUE | TRUE | Admin Line Item | 1135000 |  | John Senger | 1135000 | In-State University | 480000 | 480000 | Kristi Anderson | Other / Department Wide
312 | R27-ET2 (FY25-30 IGA) Research Project Start! | R27-ET2 (FY25-30 IGA) | R27-ET2 (FY25-30 IGA) | 2 | R27-ET2 (FY25-30 IGA): R27-ET2 (FY25-30 IGA) | Open |  | Nick York | 2024-07-01 | 2024-07-01 | Kristi Anderson [0.00 %], Abrielle Zinkl [0.00 %] | 2024-07-01 | 2024-07-01 | 211103 | TRUE | TRUE | Admin Line Item | 1095000 |  | John Senger | 1095000 | In-State University | 1095000 | 1095000 | Kristi Anderson | Other / Department Wide
313 | R27-PC (FY18-24 IGA) Research Project Start! | R27-PC (FY18-24 IGA) | R27-PC (FY18-24 IGA) | 2 | R27-PC (FY18-24 IGA): R27-PC (FY18-24 IGA) | FY18-FY24 IGA |  | Kristi Anderson | 2017-07-01 | 2017-07-01 | Kristi Anderson | 2017-07-01 | 2017-07-01 | 1617512 | TRUE | TRUE | Admin Line Item | 2321525 |  | John Senger | 2321525 | In-State University | 840000 | 840000 | Kristi Anderson | Other / Department Wide
314 | R27-PC (FY25-30 IGA) Research Project Start! | R27-PC (FY25-30 IGA) | R27-PC (FY25-30 IGA) | 2 | R27-PC (FY25-30 IGA): R27-PC (FY25-30 IGA) | Open |  | Nick York | 2024-07-01 | 2024-07-01 | Kristi Anderson [0.00 %], Abrielle Zinkl [0.00 %] | 2024-07-01 | 2024-07-01 | 440913 | TRUE | TRUE | Admin Line Item | 2600000 |  | John Senger | 2600000 | In-State University | 2600000 | 2600000 | Kristi Anderson | Other / Department Wide
315 | R27-RDI (FY18-24 IGA) Research Project Start! | R27-RDI (FY18-24 IGA) | R27-RDI (FY18-24 IGA) | 2 | R27-RDI (FY18-24 IGA): R27-RDI (FY18-24 IGA) | FY18-FY24 IGA |  | Kristi Anderson | 2017-07-01 | 2017-07-01 | Kristi Anderson | 2017-07-01 | 2017-07-01 | 296690 | TRUE | TRUE | Admin Line Item | 772000 |  | John Senger | 772000 | In-State University | 312000 | 312000 | Kristi Anderson | Other / Department Wide
316 | R27-RDI (FY25-30 IGA) Research Project Start! | R27-RDI (FY25-30 IGA) | R27-RDI (FY25-30 IGA) | 2 | R27-RDI (FY25-30 IGA): R27-RDI (FY25-30 IGA) | Open |  | Nick York | 2024-07-01 | 2024-07-01 | Kristi Anderson [0.00 %], Abrielle Zinkl [0.00 %] | 2024-07-01 | 2024-07-01 | 148289 | TRUE | TRUE | Admin Line Item | 660000 |  | John Senger | 660000 | In-State University | 660000 | 660000 | Kristi Anderson | Other / Department Wide
317 | R27-SP# (FY06-08 IGA) Research Project Start! | R27-SP# (FY06-08 IGA) | R27-SP# (FY06-08 IGA) | 1 | R27-SP# (FY06-08 IGA): R27-SP# (FY06-08 IGA) | FY06-FY08 IGA |  | Nick York | 2005-07-01 | 2005-07-01 | ICT Project Management | 2005-07-01 | 2005-07-01 | 0 | TRUE | TRUE | PI Direct | 225000 |  | Megan Swanson | 168750 |  | 168750 | 225000 | Imad Al-Qadi | Other / Department Wide
318 | R27-SP# (FY09-11 IGA) Research Project Start! | R27-SP# (FY09-11 IGA) | R27-SP# (FY09-11 IGA) | 1 | R27-SP# (FY09-11 IGA): R27-SP# (FY09-11 IGA) | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-07-01 | 2008-07-01 | ICT Project Management | 2008-07-01 | 2008-07-01 | 0 | TRUE | TRUE | PI Direct | 450000 |  | Megan Swanson | 337500 |  | 337000 | 450000 | Imad Al-Qadi | Other / Department Wide
319 | R27-SP01 Research Project Start! | R27-SP01 | Median Cable Scanning Tour | 1 | R27-SP01: Median Cable Scanning Tour | FY06-FY08 IGA |  | Nick York | 2005-08-22 | 2005-08-22 | ICT Project Management [0.00 %] | 2005-08-22 | 2005-08-22 | 10612 | TRUE | TRUE | PI Direct | 9969 |  | David Lippert | 7477 |  | 7477 | 9969 | Ray Benekohal | SAF
320 | R27-SP02 Research Project Start! | R27-SP02 | Chicago Bridge Columns | 1 | R27-SP02: Chicago Bridge Columns | FY06-FY08 IGA |  | Nick York | 2006-01-01 | 2006-01-01 | ICT Project Management [0.00 %] | 2006-01-01 | 2006-01-01 | 26265 | TRUE | TRUE | PI Direct | 24673 |  | David Lippert | 18506 |  | 18506 | 24673 | Imad Al-Qadi | BAF
321 | R27-SP03 Research Project Start! | R27-SP03 | Profile Equipment Verification FY06 | 1 | R27-SP03: Profile Equipment Verification FY06 | FY06-FY08 IGA |  | Nick York | 2006-04-17 | 2006-04-17 | ICT Project Management [0.00 %] | 2006-04-17 | 2006-04-17 | 5911 | TRUE | TRUE | PI Direct | 5567 |  | David Lippert | 4175 |  | 4175 | 5567 | Imad Al-Qadi | PVMT
322 | R27-SP04 Research Project Start! | R27-SP04 | Highway Maintenance Manpower | 1 | R27-SP04: Highway Maintenance Manpower | FY06-FY08 IGA |  | Nick York | 2007-01-01 | 2007-01-01 | ICT Project Management [0.00 %] | 2007-01-01 | 2007-01-01 | 48450 | TRUE | TRUE | PI Direct | 45515 |  | Joseph Hill | 34136 |  | 34136 | 45515 | Yanfeng Ouyang | OPS
323 | R27-SP05 Research Project Start! | R27-SP05 | Profile Equipment Verification FY07 | 1 | R27-SP05: Profile Equipment Verification FY07 | FY06-FY08 IGA |  | Nick York | 2007-04-01 | 2007-04-01 | ICT Project Management [0.00 %] | 2007-04-01 | 2007-04-01 | 8976 | TRUE | TRUE | PI Direct | 13231 |  | David Lippert | 9923 |  | 9923 | 13231 | Imad Al-Qadi | PVMT
324 | R27-SP06 Research Project Start! | R27-SP06 | Cracking in Pavement | 1 | R27-SP06: Cracking in Pavement | FY06-FY08 IGA |  | Nick York | 2006-07-01 | 2006-07-01 | ICT Project Management [0.00 %] | 2006-07-01 | 2006-07-01 | 21290 | TRUE | TRUE | PI Direct | 20000 |  | David Lippert | 15000 |  | 15000 | 20000 | Imad Al-Qadi | PVMT
325 | R27-SP07 Research Project Start! | R27-SP07 | Reinforced Concrete Structures | 1 | R27-SP07: Reinforced Concrete Structures | FY06-FY08 IGA |  | Nick York | 2007-09-12 | 2007-09-12 | ICT Project Management [0.00 %] | 2007-09-12 | 2007-09-12 | 28932 | TRUE | TRUE | PI Direct | 27333 |  | David Lippert | 20500 |  | 20500 | 27333 | Imad Al-Qadi | PVMT
326 | R27-SP08 Research Project Start! | R27-SP08 | Wireless Internet Service on Trains | 1 | R27-SP08: Wireless Internet Service on Trains | FY06-FY08 IGA |  | Nick York | 2007-10-01 | 2007-10-01 | ICT Project Management [0.00 %] | 2007-10-01 | 2007-10-01 | 66259 | TRUE | TRUE | PI Direct | 63115 |  | Mark Kinkaid | 47336 |  | 47336 | 63115 | R. Sreenivas | MFM
327 | R27-SP09 Research Project Start! | R27-SP09 | Profile Equipment Verification 2008 | 1 | R27-SP09: Profile Equipment Verification 2008 | FY06-FY08 IGA |  | Nick York | 2008-02-16 | 2008-02-16 | ICT Project Management [0.00 %] | 2008-02-16 | 2008-02-16 | 20344 | TRUE | TRUE | PI Direct | 21664 |  | David Lippert | 16248 |  | 16248 | 21664 | Imad Al-Qadi | PVMT
328 | R27-SP10 Research Project Start! | R27-SP10 | Online Training Course Prototype | 1 | R27-SP10: Online Training Course Prototype | FY06-FY08 IGA |  | Nick York | 2008-04-15 | 2008-04-15 | ICT Project Management [0.00 %] | 2008-04-15 | 2008-04-15 | 29383 | TRUE | TRUE | PI Direct | 32167 |  | Kevin Burke | 24125 |  | 24125 | 32167 | James Hall | OPS
329 | R27-SP11 Research Project Start! | R27-SP11 | Recycled CRCP Cores | 1 | R27-SP11: Recycled CRCP Cores | FY09-FY11 IGA |  | Nick York | 2008-07-01 | 2008-07-01 | ICT Project Management [0.00 %] | 2008-07-01 | 2008-07-01 | 13567 | TRUE | TRUE | PI Direct | 13333 |  | Mark Gawedzinski | 10000 |  | 10000 | 13333 | Jeffery Roesler | PVMT
330 | R27-SP12 Research Project Start! | R27-SP12 | Bridge Collapse Investigation | 1 | R27-SP12: Bridge Collapse Investigation | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-09-10 | 2008-09-10 | ICT Project Management | 2008-09-10 | 2008-09-10 | 19481 | TRUE | TRUE | PI Direct | 20280 |  | James Klein | 15210 |  | 15210 | 20280 | Bassem Andrawes | BAF
331 | R27-SP13 Research Project Start! | R27-SP13 | Profile Equipment Verification 2009 | 1 | R27-SP13: Profile Equipment Verification 2009 | FY09-FY11 IGA |  | Nick York | 2009-04-01 | 2009-04-01 | ICT Project Management [0.00 %] | 2009-04-01 | 2009-04-01 | 44578 | TRUE | TRUE | PI Direct | 45000 |  | LaDonna Rowden | 33750 |  | 33750 | 45000 | Imad Al-Qadi | PVMT
332 | R27-SP14 Research Project Start! | R27-SP14 | Retroreflective Sign Sheeting | 1 | R27-SP14: Retroreflective Sign Sheeting | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-05-01 | 2009-05-01 | ICT Project Management | 2009-05-01 | 2009-05-01 | 26912 | TRUE | TRUE | PI Direct | 27168 |  | Kelly Senger | 20376 |  | 20376 | 27168 | Liang Liu | PVMT
333 | R27-SP15 Research Project Start! | R27-SP15 | Snowplow Simulator Training | 1 | R27-SP15: Snowplow Simulator Training | FY09-FY11 IGA |  | Nick York | 2009-11-01 | 2009-11-01 | ICT Project Management [0.00 %] | 2009-11-01 | 2009-11-01 | 25402 | TRUE | TRUE | PI Direct | 27012 |  | Dave Johnson | 20259 |  | 20259 | 27012 | Thomas O'Rourke | OPS
334 | R27-SP16 Research Project Start! | R27-SP16 | Horizontal Directional Drilling Eval | 1 | R27-SP16: Horizontal Directional Drilling Eval | FY09-FY11 IGA |  | Brian Lorbiecki | 2009-07-16 | 2009-07-16 | ICT Project Management | 2009-07-16 | 2009-07-16 | 22361 | TRUE | TRUE | PI Direct | 19893 |  | Terri Peterson | 14920 |  | 14920 | 19893 | Youssef Hashash | Other / Department Wide
335 | R27-SP17 Research Project Start! | R27-SP17 | Warm Mix Asphalt Study | 1 | R27-SP17: Warm Mix Asphalt Study | FY09-FY11 IGA |  | Nick York | 2009-07-16 | 2009-07-16 | ICT Project Management [0.00 %] | 2009-07-16 | 2009-07-16 | 26471 | TRUE | TRUE | PI Direct | 23408 |  | Tom Zehr | 17556 |  | 17556 | 23408 | Imad Al-Qadi | PVMT
336 | R27-SP18 Research Project Start! | R27-SP18 | Bicycle Trail | 1.8.7 | R27-SP18: Bicycle Trail | FY12-FY17 IGA |  | AKSHITI MODI | 2011-08-16 | 2011-08-16 | ICT Project Management | 2011-08-16 | 2011-08-16 | 29148 | TRUE | TRUE | PI Direct | 30000 |  | Todd Hill | 22500 |  | 22500 | 30000 | Barry Dempsey | ENV
337 | R27-SP19 Research Project Start! | R27-SP19 | Effect of RAS | 2 | R27-SP19: Effect of RAS | FY12-FY17 IGA |  | ICT Project Management | 2011-12-16 | 2011-12-16 | ICT Project Management | 2011-12-16 | 2011-12-16 | 32790 | TRUE | TRUE | PI Direct | 30000 |  | David Lippert | 22500 |  | 22500 | 30000 | Hasan Ozer | PVMT
338 | R27-SP20 Research Project Start! | R27-SP20 | Signal Control Technologies | 2 | R27-SP20: Signal Control Technologies | FY12-FY17 IGA |  | AKSHITI MODI | 2012-04-16 | 2012-04-16 | ICT Project Management | 2012-04-16 | 2012-04-16 | 36524 | TRUE | TRUE | PI Direct | 30000 |  | Kyle Armstrong | 22500 |  | 22500 | 30000 | Ray Benekohal | OPS
339 | R27-SP21 Research Project Start! | R27-SP21 | COSIM | 2 | R27-SP21: COSIM | FY12-FY17 IGA |  | Nick York | 2012-06-01 | 2012-06-01 | ICT Project Management | 2012-06-01 | 2012-06-01 | 12680 | TRUE | TRUE | PI Direct | 25524 |  | Walt Zyznieuski | 19143 |  | 19143 | 25524 | Scott Peters | ENV
340 | R27-SP22 Research Project Start! | R27-SP22 | HPMS Sample Counting | 2 | R27-SP22: HPMS Sample Counting | FY12-FY17 IGA |  | Nick York | 2013-03-01 | 2013-03-01 | ICT Project Management | 2013-03-01 | 2013-03-01 | 25001 | TRUE | TRUE | PI Direct | 25400 |  | William Morgan | 19050 |  | 19050 | 25400 | James Hall | PLAN
341 | R27-SP23 Research Project Start! | R27-SP23 | Drainage Laws | 2 | R27-SP23: Drainage Laws | FY12-FY17 IGA |  | Nick York | 2013-09-16 | 2013-09-16 | ICT Project Management | 2013-09-16 | 2013-09-16 | 37048 | TRUE | TRUE | PI Direct | 30000 |  | Thomas Winkelman | 22500 |  | 22500 | 30000 | Art Schmidt | Other / Department Wide
342 | R27-SP24 Research Project Start! | R27-SP24 | TrafficTurk Evaluation | 2 | R27-SP24: TrafficTurk Evaluation | FY12-FY17 IGA |  | Nick York | 2013-08-16 | 2013-08-16 | ICT Project Management | 2013-08-16 | 2013-08-16 | 29181 | TRUE | TRUE | PI Direct | 30000 |  | Paul Lorton | 22500 |  | 22500 | 30000 | Daniel Work | SAF
343 | R27-SP25 Research Project Start! | R27-SP25 | Local Roadway Safety Assessments | 2 | R27-SP25: Local Roadway Safety Assessments | FY12-FY17 IGA |  | Nick York | 2013-11-01 | 2013-11-01 | ICT Project Management | 2013-11-01 | 2013-11-01 | 31385 | TRUE | TRUE | PI Direct | 30000 |  | Mike Gillette | 22500 |  | 22500 | 30000 | Yanfeng Ouyang | SAF
344 | R27-SP26-C Research Project Start! | R27-SP26-C | Alternative Deicers | 2 | R27-SP26-C: Alternative Deicers | FY12-FY17 IGA |  | Nick York | 2014-03-01 | 2014-03-01 | ICT Project Management | 2014-03-01 | 2014-03-01 | 35148 | TRUE | TRUE | PI Direct | 30000 |  | Tim Peters | 22500 |  | 22500 | 30000 | Jim Meister | OPS
345 | R27-SP27 Research Project Start! | R27-SP27 | AIMS Implementation | 2 | R27-SP27: AIMS Implementation | FY12-FY17 IGA |  | AKSHITI MODI | 2014-06-01 | 2014-06-01 | ICT Project Management | 2014-06-01 | 2014-06-01 | 30255 | TRUE | TRUE | PI Direct | 30000 |  | Sheila Beshears | 22500 |  | 22306 | 30000 | Enad Mahmoud | PVMT
346 | R27-SP28 Research Project Start! | R27-SP28 | PG Asphalts ReOB | 2 | R27-SP28: PG Asphalts ReOB | FY12-FY17 IGA |  | AKSHITI MODI | 2014-10-01 | 2014-10-01 | ICT Project Management | 2014-10-01 | 2014-10-01 | 34695 | TRUE | TRUE | PI Direct | 30000 |  | Ronald Price | 22500 |  | 22500 | 30000 | Hasan Ozer | SUS
347 | R27-SP29 Research Project Start! | R27-SP29 | Thermodynamics | 2 | R27-SP29: Thermodynamics | FY12-FY17 IGA |  | AKSHITI MODI | 2015-01-01 | 2015-01-01 | ICT Project Management | 2015-01-01 | 2015-01-01 | 30296 | TRUE | TRUE | PI Direct | 30000 |  | Matt Mueller | 22500 |  | 22500 | 30000 | Mohammad Hossain | PVMT
348 | R27-SP30 Research Project Start! | R27-SP30 | Speed Harmonization | 2 | R27-SP30: Speed Harmonization | FY12-FY17 IGA |  | AKSHITI MODI | 2015-09-16 | 2015-09-16 | ICT Project Management | 2015-09-16 | 2015-09-16 | 29180 | TRUE | TRUE | PI Direct | 30000 |  | Kyle Armstrong | 22500 |  | 22500 | 30000 | Yanfeng Ouyang | SAF
349 | R27-SP31 Research Project Start! | R27-SP31 | Evaluation of I-FIT Results | 2 | R27-SP31: Evaluation of I-FIT Results | FY12-FY17 IGA |  | AKSHITI MODI | 2016-08-16 | 2016-08-16 | ICT Project Management | 2016-08-16 | 2016-08-16 | 31395 | TRUE | TRUE | PI Direct | 30000 |  | Tom Zehr | 22500 |  | 19565 | 30000 | Hasan Ozer | PVMT
350 | R27-SP32 Research Project Start! | R27-SP32 | Red Light Running Cameras | 2 | R27-SP32: Red Light Running Cameras | FY12-FY17 IGA |  | AKSHITI MODI | 2016-08-16 | 2016-08-16 | ICT Project Management | 2016-08-16 | 2016-08-16 | 35519 | TRUE | TRUE | PI Direct | 30000 |  | Paul Lorton | 22350 |  | 22317 | 30000 | Kerrie Schattler | SAF
351 | R27-SP33 Research Project Start! | R27-SP33 | Red Light Running Cameras | 2 | R27-SP33: Red Light Running Cameras | FY12-FY17 IGA |  | Nick York | 2016-08-16 | 2016-08-16 | ICT Project Management | 2016-08-16 | 2016-08-16 | 34457 | TRUE | TRUE | PI Direct | 30000 |  | Paul Lorton | 22500 |  | 22500 | 30000 | Yanfeng Ouyang | SAF
352 | R27-SP34 Research Project Start! | R27-SP34 | Shear Tack | 2 | R27-SP34: Shear Tack | FY18-FY24 IGA |  | Brian Lorbiecki | 2017-05-01 | 2017-05-01 | Brian Lorbiecki | 2017-05-01 | 2017-05-01 | 35689 | TRUE | TRUE | PI Direct | 46029 |  | Jim Trepanier | 36813 | In-State University | 22500 | 30000 | Hasan Ozer | PVMT
353 | R27-SP35 Research Project Start! | R27-SP35 | Textured Rebar | 2 | R27-SP35: Textured Rebar | FY18-FY24 IGA |  | Brian Lorbiecki | 2017-05-15 | 2017-05-15 | Brian Lorbiecki | 2017-05-15 | 2017-05-15 | 37068 | TRUE | TRUE | PI Direct | 38930 |  | Jayme Schiff | 29198 | In-State University | 22500 | 30000 | Bassem Andrawes | PVMT
354 | R27-SP36 Research Project Start! | R27-SP36 | AIMS-MD | 2 | R27-SP36: AIMS-MD | FY18-FY24 IGA |  | Brian Lorbiecki | 2017-09-01 | 2017-09-01 | Brian Lorbiecki | 2017-09-01 | 2017-09-01 | 37548 | TRUE | TRUE | PI Direct | 36000 |  | John Senger | 27000 | Private Industry | 27000 | 36000 | Zina Eluri | PVMT
355 | R27-SP37-C Research Project Start! | R27-SP37-C | Speed Limits | 2 | R27-SP37-C: Speed Limits | FY18-FY24 IGA |  | Brian Lorbiecki | 2017-09-15 | 2017-09-15 | Audrey Donoho | 2017-09-15 | 2017-09-15 | 34145 | TRUE | TRUE | PI Direct | 35987 |  | Kyle Armstrong | 26990 | In-State University | 26990 | 35987 | Hadi Meidani | SAF
356 | R27-SP38 Research Project Start! | R27-SP38 | QBP Durability | 2 | R27-SP38: QBP Durability | FY18-FY24 IGA |  | Audrey Donoho | 2019-02-01 | 2019-02-01 | Audrey Donoho | 2019-02-01 | 2019-02-01 | 37106 | TRUE | TRUE | PI Direct | 36000 | 87 | Heather Shoup | 27000 | In-State University | 27000 | 36000 | Erol Tutumluer | PVMT | 29
357 | R27-SP39 Research Project Start! | R27-SP39 | Hybrid Beacons | 2 | R27-SP39: Hybrid Beacons | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-03-16 | 2019-03-16 | Brian Lorbiecki | 2019-03-16 | 2019-03-16 | 31917 | TRUE | TRUE | PI Direct | 36000 |  | Jon McCormick / Marshall Metcalf | 27000 | In-State University | 27000 | 36000 | Stacey DeLorenzo | SAF
358 | R27-SP40 Research Project Start! | R27-SP40 | Distracted Driving | 2 | R27-SP40: Distracted Driving | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-04-01 | 2019-04-01 | Brian Lorbiecki | 2019-04-01 | 2019-04-01 | 52188 | TRUE | TRUE | PI Direct | 48500 |  | Juan Pava / Adam Gabany | 39500 | In-State University | 39500 | 48500 | Yan Qi | SAF
359 | R27-SP41 Research Project Start! | R27-SP41 | Small Cells | 2 | R27-SP41: Small Cells | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-09-01 | 2019-09-01 | Brian Lorbiecki | 2019-09-01 | 2019-09-01 | 52426 | TRUE | TRUE | PI Direct | 48500 |  | Marshall Metcalf | 39500 | In-State University | 39500 | 48500 | Mohammad Hossain | OPS
360 | R27-SP42 Research Project Start! | R27-SP42 | Bridge Beams | 2 | R27-SP42: Bridge Beams | FY18-FY24 IGA |  | Brian Lorbiecki | 2019-11-16 | 2019-11-16 | Brian Lorbiecki | 2019-11-16 | 2019-11-16 | 35687 | TRUE | TRUE | PI Direct | 36000 |  | Robert Perkins | 27000 | In-State University | 27000 | 36000 | BF Spencer | BAF
361 | R27-SP43 Research Project Start! | R27-SP43 | Quarry By-products | 2 | R27-SP43: Quarry By-products | FY18-FY24 IGA |  | Audrey Donoho | 2020-05-16 | 2020-05-16 | Audrey Donoho | 2020-05-16 | 2020-05-16 | 33176 | TRUE | TRUE | PI Direct | 36000 | 0 | Michael Short | 27000 | In-State University | 27000 | 36000 | Erol Tutumluer | PVMT | 1
362 | R27-SP44 Research Project Start! | R27-SP44 | HMA Potholes | 2 | R27-SP44: HMA Potholes | FY18-FY24 IGA |  | Audrey Donoho | 2020-05-01 | 2020-05-01 | Audrey Donoho | 2020-05-01 | 2020-05-01 | 32250 | TRUE | TRUE | PI Direct | 36000 |  | Laura Shanley | 27000 | In-State University | 27000 | 36000 | Ramez Hajj | OPS
363 | R27-SP45 Research Project Start! | R27-SP45 | Transit System Ridership | 2 | R27-SP45: Transit System Ridership | FY18-FY24 IGA |  | Brian Lorbiecki | 2020-11-16 | 2020-11-16 | Brian Lorbiecki | 2020-11-16 | 2020-11-16 | 39029 | TRUE | TRUE | PI Direct | 36000 |  | Charles Abraham / Jessica Hector-Hsu | 27000 | In-State University | 27000 | 36000 | Yanfeng Ouyang | MFM
364 | R27-SP46 Research Project Start! | R27-SP46 | Bridge Deterioration | 2 | R27-SP46: Bridge Deterioration | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-01-01 | 2021-01-01 | Audrey Donoho | 2021-01-01 | 2021-01-01 | 50660 | TRUE | TRUE | PI Direct | 48500 |  | Travis Lobmaster / William Morgan | 39500 | In-State University | 39500 | 48500 | Gongkang Fu | PLAN
365 | R27-SP47 Research Project Start! | R27-SP47 | Mobile Road Weather | 2 | R27-SP47: Mobile Road Weather | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-04-16 | 2021-04-16 | Brian Lorbiecki | 2021-04-16 | 2021-04-16 | 27659 | TRUE | TRUE | PI Direct | 35997 |  | Laura Shanley | 26997 | In-State University | 26997 | 35997 | Khaled El-Rayes | OPS
366 | R27-SP48 Research Project Start! | R27-SP48 | Longitudinal Cracking | 3 | R27-SP48: Longitudinal Cracking | FY18-FY24 IGA |  | Audrey Donoho | 2021-05-01 | 2021-05-01 | Audrey Donoho | 2021-05-01 | 2021-05-01 | 34290 | TRUE | TRUE | PI Direct | 36000 |  | Charles Wienrank | 27000 | In-State University | 27000 | 36000 | Jeffery Roesler | PVMT
367 | R27-SP49 Research Project Start! | R27-SP49 | Corrosion on Bridge Decks | 2 | R27-SP49: Corrosion on Bridge Decks | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-08-16 | 2021-08-16 | Sree Venda | 2021-08-16 | 2021-08-16 | 50650 | TRUE | TRUE | PI Direct | 48500 |  | Jayme Schiff / Dan Tobias | 39500 | In-State University | 39500 | 48500 | Matthew Gombeda | BAF
368 | R27-SP50 Research Project Start! | R27-SP50 | Bridge Safety | 2 | R27-SP50: Bridge Safety | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-09-01 | 2021-09-01 | Sree Venda | 2021-09-01 | 2021-09-01 | 37615 | TRUE | TRUE | PI Direct | 36000 |  | Timothy Armbrecht / Dan Brydl | 27000 | In-State University | 27000 | 36000 | Marcelo Garcia | BAF
369 | R27-SP51-HS Research Project Start! | R27-SP51-HS | Transverse Rumble Strips | 2 | R27-SP51-HS: Transverse Rumble Strips | FY18-FY24 IGA |  | Brian Lorbiecki | 2021-09-01 | 2021-09-01 | Brian Lorbiecki | 2021-09-01 | 2021-09-01 | 5565 | TRUE | TRUE | PI Direct | 36000 | 43.33 | Issam Rayyan | 28800 | In-State University | 28800 | 36000 | Imad Al-Qadi | SAF | 5
370 | R27-SP52 Research Project Start! | R27-SP52 | Corrosion on Bridge Decks Phase II | 3 | R27-SP52: Corrosion on Bridge Decks Phase II | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-05-16 | 2022-05-16 | Brian Lorbiecki | 2022-05-16 | 2022-05-16 | 50650 | TRUE | TRUE | PI Direct | 48500 |  | Curt Evoy / Del Reeves | 39500 | In-State University | 39500 | 48500 | Matthew Gombeda | BAF
371 | R27-SP53 Research Project Start! | R27-SP53 | Transit Ridership Analysis | 3 | R27-SP53: Transit Ridership Analysis | FY18-FY24 IGA |  | Brian Lorbiecki | 2022-05-16 | 2022-05-16 | Brian Lorbiecki | 2022-05-16 | 2022-05-16 | 34487 | TRUE | TRUE | PI Direct | 36000 |  | Charles Abraham / Cemal Ayvalik | 27000 | In-State University | 27000 | 36000 | Yanfeng Ouyang | MFM
372 | R27-SP54 Research Project Cancelled! | R27-SP54 | Brine Rates | 2 | R27-SP54: Brine Rates | Cancelled |  | Nick York | 2023-01-11 | 2023-01-11 | Nick York [0.00 %] | 2023-01-11 | 2023-01-11 | 0 | TRUE | TRUE | [9 empty] | OPS
373 | R27-SP55 Research Project Start! | R27-SP55 | Dynamic Messaging | 2 | R27-SP55: Dynamic Messaging | FY18-FY24 IGA |  | Nick York | 2023-06-01 | 2023-06-01 | Nick York [0.00 %] | 2023-06-01 | 2023-06-01 | 34789 | TRUE | TRUE | PI Direct | 36000 |  | Sean Martschinke | 27000 | In-State University | 27000 | 36000 | Yanfeng Ouyang | OPS
374 | R27-SP56 Research Project Start! | R27-SP56 | RAP in Pavement Preservation | 3 | R27-SP56: RAP in Pavement Preservation | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-05-01 | 2023-05-01 | Audrey Donoho | 2023-05-01 | 2023-05-01 | 36287 | TRUE | TRUE | PI Direct | 36000 |  | John Senger | 28800 | In-State University | 28800 | 36000 | Imad Al-Qadi | PVMT
375 | R27-SP57 Research Project Start! | R27-SP57 | Transit Vehicle Technician Needs | 2 | R27-SP57: Transit Vehicle Technician Needs | FY18-FY24 IGA |  | Nick York | 2023-06-01 | 2023-06-01 | Nick York | 2023-06-01 | 2023-06-01 | 44438 | TRUE | TRUE | PI Direct | 46814 |  | Charles Abraham / Zoe Keller | 37814 | In-State University | 37814 | 46814 | Reggie Greenwood | MFM
376 | R27-SP58 Research Project Start! | R27-SP58 | IDOT Maintenance Needs | 3 | R27-SP58: IDOT Maintenance Needs | FY18-FY24 IGA |  | Nick York | 2023-04-01 | 2023-04-01 | Nick York | 2023-04-01 | 2023-04-01 | 29156 | TRUE | TRUE | PI Direct | 36000 |  | Charles Abraham / Zoe Keller | 27000 | In-State University | 27000 | 36000 | Yanfeng Ouyang | MFM
377 | R27-SP59 Research Project Start! | R27-SP59 | Asphalt Replacement Credits | 3 | R27-SP59: Asphalt Replacement Credits | FY18-FY24 IGA |  | Nick York | 2023-04-16 | 2023-04-16 | Nick York | 2023-04-16 | 2023-04-16 | 40981 | TRUE | TRUE | PI Direct | 36000 |  | Douglas Dirks | 27000 | In-State University | 27000 | 36000 | Ramez Hajj | CON
378 | R27-SP60 Research Project Cancelled! | R27-SP60 | E-Ticketing | 2 | R27-SP60: E-Ticketing | Cancelled |  | Nick York | 2023-01-19 | 2023-01-19 | Nick York [0.00 %] | 2023-01-19 | 2023-01-19 | 0 | TRUE | TRUE | [9 empty] | CON
379 | R27-SP61 Research Project Start! | R27-SP61 | Wetland Mitigation | 2 | R27-SP61: Wetland Mitigation | FY18-FY24 IGA |  | Nick York | 2023-05-16 | 2023-05-16 | Nick York | 2023-05-16 | 2023-05-16 | 31521 | TRUE | TRUE | PI Direct | 36000 |  | Kimberly Burkwald / Shawn Wilcockson | 27000 | In-State University | 27000 | 36000 | Geoffrey Pociask | ENV
380 | R27-SP62 Research Project Start! | R27-SP62 | Bridge Deck Crack Sealing | 3 | R27-SP62: Bridge Deck Crack Sealing | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-07-01 | 2023-07-01 | Brian Lorbiecki [0.00 %] | 2023-07-01 | 2023-07-01 | 36397 | TRUE | TRUE | PI Direct | 36000 |  | Mark Shaffer | 27000 | In-State University | 27000 | 36000 | Mohsen Issa | BAF
381 | R27-SP63 Research Project Start! | R27-SP63 | MSCR | 3 | R27-SP63: MSCR | FY18-FY24 IGA |  | Brian Lorbiecki | 2023-04-01 | 2023-04-01 | Audrey Donoho | 2023-04-01 | 2023-04-01 | 38801 | TRUE | TRUE | PI Direct | 36000 |  | Kelly Senger | 27000 | In-State University | 27000 | 36000 | Ramez Hajj | PVMT
382 | R27-SP64 Research Project Start! | R27-SP64 | Endangered Species | 2 | R27-SP64: Endangered Species | FY18-FY24 IGA |  | Nick York | 2023-05-16 | 2023-05-16 | Nick York | 2023-05-16 | 2023-05-16 | 33826 | TRUE | TRUE | PI Direct | 36000 |  | Kimberly Burkwald / Shawn Wilcockson | 27000 | In-State University | 27000 | 36000 | Wendy Schelsky | ENV
383 | R27-SP65 Research Project Start! | R27-SP65 | Low-Clearance Early Warning Devices | 3 | R27-SP65: Low-Clearance Early Warning Devices | Complete - IDOT-ICT |  | Nick York | 2023-11-01 | 2023-11-01 | Nick York | 2023-11-01 | 2023-11-01 | 32962 | TRUE | TRUE | PI Direct | 36000 |  | Kyle Armstrong | 27000 | In-State University | 27000 | 36000 | Yanfeng Ouyang | OPS
384 | R27-SP66 Research Project Start! | R27-SP66 | Anti-Graffiti | 2 | R27-SP66: Anti-Graffiti | Complete - IDOT-ICT |  | Brian Lorbiecki | 2024-01-16 | 2024-01-16 | Brian Lorbiecki [0.00 %] | 2024-01-16 | 2024-01-16 | 98656 | TRUE | TRUE | PI Direct | 83286 |  | Mark Shaffer | 67036 | In-State University | 59494 | 75743 | Yasser Khodair | BAF
385 | R27-SP67 Research Project Start! | R27-SP67 | Minimizing Impacts to Aquatic Resources | 4 | R27-SP67: Minimizing Impacts to Aquatic Resources | Complete - IDOT-ICT |  | Nick York | 2024-08-16 | 2024-08-16 | Nick York [0.00 %] | 2024-08-16 | 2024-08-16 | 42536 | TRUE | TRUE | PI Direct | 64977 |  | Vincent Hamer | 48733 | In-State University | 48733 | 64977 | Dusty Swedberg | ENV
386 | R27-SP68 Research Project Start! | R27-SP68 | Rusty Patched Bumblebee | 4 | R27-SP68: Rusty Patched Bumblebee | Complete - IDOT-ICT |  | Nick York | 2024-09-01 | 2024-09-01 | Nick York [0.00 %] | 2024-09-01 | 2024-09-01 | 65398 | TRUE | TRUE | PI Direct | 65000 |  | Kimberly Burkwald | 48750 | In-State University | 48750 | 65000 | Jason Robinson | ENV
387 | R27-SP69 Research Project Start! | R27-SP69 | Specialized Management Areas | 4 | R27-SP69: Specialized Management Areas | Complete - IDOT-ICT |  | Nick York | 2024-10-01 | 2024-10-01 | Nick York [0.00 %] | 2024-10-01 | 2024-10-01 | 65302 | TRUE | TRUE | PI Direct | 65000 |  | Jake Vancil | 48750 | In-State University | 48750 | 65000 | David Zaya | ENV
388 | R27-SP70 Research Project Start! | R27-SP70 | Wildlife Crossings | 4 | R27-SP70: Wildlife Crossings | Complete - IDOT-ICT |  | Nick York | 2024-10-01 | 2024-10-01 | Nick York [0.00 %] | 2024-10-01 | 2024-10-01 | 42633 | TRUE | TRUE | PI Direct | 57867 |  | Bradley Daugherty | 43400 | In-State University | 43400 | 57867 | Kirk Stodola | ENV
389 | R27-SP71 Research Project Start! | R27-SP71 | Target Speeds | 3 | R27-SP71: Target Speeds | Complete - IDOT-ICT |  | Nick York | 2024-02-16 | 2024-02-16 | Nick York | 2024-02-16 | 2024-02-16 | 72873 | TRUE | TRUE | PI Direct | 65000 |  | Stephane Seck-Birhame / Victoria Barrett | 48750 | In-State University | 48750 | 65000 | Alireza Talebpour | SAF
390 | R27-SP72 Research Project Start! | R27-SP72 | Roller Compacted Concrete | 2 | R27-SP72: Roller Compacted Concrete | Complete - IDOT-ICT |  | Brian Lorbiecki | 2024-04-16 | 2024-04-16 | Brian Lorbiecki [0.00 %] | 2024-04-16 | 2024-04-16 | 64703 | TRUE | TRUE | PI Direct | 65000 | 0 | John Senger | 48750 | In-State University | 48750 | 65000 | Jeffery Roesler | PVMT
391 | R27-SP73 Research Project Cancelled! | R27-SP73 | Mussel Relocation | 2 | R27-SP73: Mussel Relocation | Cancelled |  | Nick York | 2025-01-23 | 2025-01-23 | Nick York [0.00 %] | 2025-01-23 | 2025-01-23 | 0 | TRUE | TRUE | PI Direct | 0 |  | Felecia Hurley / Shawn Wilcockson | 0 | Out-of-State University | 0 | 0 | Kevin Roe | ENV
392 | R27-SP74 Research Project Start! | R27-SP74 | Concrete Overlays | 2 | R27-SP74: Concrete Overlays | Complete - IDOT-ICT |  | Brian Lorbiecki | 2024-11-16 | 2024-11-16 | Brian Lorbiecki [0.00 %] | 2024-11-16 | 2024-11-16 | 65213 | TRUE | TRUE | PI Direct | 65000 |  | Charles Wienrank | 48750 | In-State University | 48750 | 65000 | Jeffery Roesler | PVMT
393 | R27-SP75 Research Project Start! | R27-SP75 | Pavement Temperature Measurement System | 2 | R27-SP75: Pavement Temperature Measurement System | Open |  | Brian Lorbiecki | 2025-06-01 | 2025-06-01 | Brian Lorbiecki [0.00 %] | 2025-06-01 | 2025-06-01 | 16597 | TRUE | TRUE | PI Direct | 65000 |  | John Senger | 48750 | In-State University | 48750 | 65000 | Ramez Hajj | PVMT
394 | R27-SP76 Research Project Start! | R27-SP76 | Temporary Sign Support Systems | 2 | R27-SP76: Temporary Sign Support Systems | Open |  | Nick York | 2025-06-01 | 2025-06-01 | Nick York [0.00 %] | 2025-06-01 | 2025-06-01 | 7325 | TRUE | TRUE | PI Direct | 65000 |  | Juan Pava | 48750 | In-State University | 48750 | 65000 | Yanfeng Ouyang | SAF | 8
395 | R27-SP77 Research Project Start! | R27-SP77 | UAS 3D Bridge Inspection | 2 | R27-SP77: UAS 3D Bridge Inspection | Open |  | Brian Lorbiecki | 2025-09-16 | 2025-09-16 | Brian Lorbiecki [0.00 %] | 2025-09-16 | 2025-09-16 | 7336 | TRUE | TRUE | PI Direct | 64997 |  | Mark Shaffer | 48748 | In-State University | 48748 | 64997 | Mohamad Alipour | BAF
396 | R27-SP78 Research Project Start! | R27-SP78 | Concrete Strength Sensing | 2 | R27-SP78: Concrete Strength Sensing | Open |  | Brian Lorbiecki | 2025-09-01 | 2025-09-01 | Brian Lorbiecki [0.00 %] | 2025-09-01 | 2025-09-01 |  | TRUE | TRUE | PI Direct | 85948 |  | Charles Wienrank / Xinyu Sun | 69698 | In-State University | 69698 | 85948 | Mohammad Hossain | PVMT
397 | R27-SP79 Research Project Start! | R27-SP79 | Aquatic Species Bridge PA | 2 | R27-SP79: Aquatic Species Bridge PA | Open |  | Nick York | 2025-10-16 | 2025-10-16 | Nick York [0.00 %] | 2025-10-16 | 2025-10-16 | 13636 | TRUE | TRUE | PI Direct | 65000 |  | Kimberly Burkwald | 48750 | In-State University | 48750 | 65000 | Dan Salas | ENV
398 | R27-SP80 Research Project Start! | R27-SP80 | Freeze-Thaw Chambers Data | 2 | R27-SP80: Freeze-Thaw Chambers Data | Pending - IDOT-ICT |  | Brian Lorbiecki | 2026-04-01 | 2026-04-01 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE | PI Direct | 65000 |  | Andrew Stolba | 48750 | In-State University | 48750 | 65000 | Nishant Garg | PVMT
399 | R27-SP81 Research Project Start! | R27-SP81 | Audible Warnings | 2 | R27-SP81: Audible Warnings | Open |  | Nick York | 2026-03-01 | 2026-03-01 | Nick York [0.00 %] | 2026-03-01 | 2026-03-01 |  | TRUE | TRUE | PI Direct | 65000 |  | Meiwu An / Greg Gurski | 48750 | In-State University | 48750 | 65000 | Yanfeng Ouyang | OPS | 8
400 | R27-SP82 Research Project Start! | R27-SP82 | Oxidation of Pavement Preservation | 2 | R27-SP82: Oxidation of Pavement Preservation | Pending - IDOT-ICT |  | Brian Lorbiecki | 2026-05-01 | 2026-05-01 | Brian Lorbiecki [0.00 %] |  |  |  | TRUE | FALSE | PI Direct | 65000 |  | Kelly Senger | 48750 | In-State University | 48750 | 65000 | Ramez Hajj | PVMT
401 | R27-SP83 Research Project Start! | R27-SP83 | Ladle Slag | 2 | R27-SP83: Ladle Slag | Open |  | Brian Lorbiecki | 2026-03-01 | 2026-03-01 | Brian Lorbiecki [0.00 %] | 2026-03-01 | 2026-03-01 |  | TRUE | TRUE | PI Direct | 65000 |  | Andrew Stolba | 48750 | In-State University | 48750 | 65000 | Erol Tutumluer | PVMT
402 | R28-001 Research Project Start! | R28-001 | Flexible Pavements (Ended 6/08) | 1 | R28-001: Flexible Pavements (Ended 6/08) | FY06-FY08 IGA |  | Nick York | 2005-07-01 | 2005-07-01 | ICT Project Management [0.00 %] | 2005-07-01 | 2005-07-01 | 132720 | TRUE | TRUE | PI Direct | 126846 |  | David Lippert | 95135 |  | 31500 | 42000 | Marshall Thompson | PVMT
403 | R28-002 Research Project Start! | R28-002 | Binder / Mixture Testing & Analysis | 1 | R28-002: Binder / Mixture Testing & Analysis | FY09-FY11 IGA |  | Brian Lorbiecki | 2008-01-01 | 2008-01-01 | ICT Project Management | 2008-01-01 | 2008-01-01 | 47016 | TRUE | TRUE | PI Direct | 42000 |  | Amy Schutzbach | 31500 |  | 31500 | 42000 | Samuel Carpenter | PVMT
404 | R39-001 Research Project Start! | R39-001 | Extended Life HMA Pavement Design | 1 | R39-001: Extended Life HMA Pavement Design | FY06-FY08 IGA |  | Nick York | 2002-07-01 | 2002-07-01 | ICT Project Management [0.00 %] | 2002-07-01 | 2002-07-01 | 184480 | TRUE | TRUE | PI Direct | 170020 |  | Amy Schutzbach | 127514 |  | 90014 | 120018 | Samuel Carpenter | PVMT
405 | R39-002 Research Project Start! | R39-002 | Nondestructive Pavement Evaluation | 1 | R39-002: Nondestructive Pavement Evaluation | FY09-FY11 IGA |  | Nick York | 2004-08-01 | 2004-08-01 | ICT Project Management [0.00 %] | 2004-08-01 | 2004-08-01 | 86795 | TRUE | TRUE | PI Direct | 84818 |  | Charles Wienrank | 63614 |  | 63614 | 84818 | Erol Tutumluer | PVMT
406 | R43 Research Project Start! | R43 | Traffic Operations Lab | 1 | R43: Traffic Operations Lab | FY06-FY08 IGA |  | Nick York | 2005-07-01 | 2005-07-01 | ICT Project Management [0.00 %] | 2005-07-01 | 2005-07-01 | 454367 | TRUE | TRUE | PI Direct | 444631 |  | Yogesh Gautam | 333473 |  | 333473 | 444631 | Ray Benekohal | OPS
407 | R44 Research Project Start! | R44 | Self-Consolidating Concrete | 1 | R44: Self-Consolidating Concrete | FY06-FY08 IGA |  | Nick York | 2003-07-01 | 2003-07-01 | ICT Project Management [0.00 %] | 2003-07-01 | 2003-07-01 | 202464 | TRUE | TRUE | PI Direct | 190196 |  | James Krstulovich | 142646 |  | 113561 | 151414 | David Lange | PVMT
408 | R53 Research Project Start! | R53 | Concrete Distress Identification | 1 | R53: Concrete Distress Identification | FY06-FY08 IGA |  | Nick York | 2005-07-01 | 2005-07-01 | ICT Project Management [0.00 %] | 2005-07-01 | 2005-07-01 | 83983 | TRUE | TRUE | PI Direct | 78902 |  | Patricia Broers | 59176 |  | 53797 | 71729 | Leslie Struble | PVMT
409 | R54 Research Project Start! | R54 | Lifting Loops in Shallow Precast Deck Beams | 1 | R54: Lifting Loops in Shallow Precast Deck Beams | FY09-FY11 IGA |  | Brian Lorbiecki | 2005-07-01 | 2005-07-01 | ICT Project Management | 2005-07-01 | 2005-07-01 | 296818 | TRUE | TRUE | PI Direct | 278832 |  | Kevin Riechers | 209124 |  | 194125 | 258833 | Dan Kuchma | BAF
410 | R55 Research Project Start! | R55 | Tack Coat Optimization | 1 | R55: Tack Coat Optimization | FY09-FY11 IGA |  | Nick York | 2005-07-01 | 2005-07-01 | ICT Project Management [0.00 %] | 2005-07-01 | 2005-07-01 | 745278 | TRUE | TRUE | PI Direct | 694590 |  | Jim Trepanier | 520942 |  | 326776 | 435702 | Imad Al-Qadi | PVMT
411 | R56 Research Project Start! | R56 | Speed Photo-Enforcement | 1 | R56: Speed Photo-Enforcement | FY06-FY08 IGA |  | Nick York | 2005-07-01 | 2005-07-01 | ICT Project Management [0.00 %] | 2005-07-01 | 2005-07-01 | 329031 | TRUE | TRUE | PI Direct | 309095 |  | Priscilla Tobias | 231821 |  | 231821 | 289438 | Ray Benekohal | SAF
412 | R57 Research Project Start! | R57 | CRCP and JPCP Design | 1 | R57: CRCP and JPCP Design | FY09-FY11 IGA |  | Brian Lorbiecki | 2005-09-01 | 2005-09-01 | ICT Project Management | 2005-09-01 | 2005-09-01 | 321183 | TRUE | TRUE | PI Direct | 301814 |  | Amy Schutzbach | 226361 |  | 187087 | 249449 | Jeffery Roesler | PVMT
413 | R58 Research Project Start! | R58 | Reflective Crack Control | 1 | R58: Reflective Crack Control | FY09-FY11 IGA |  | Nick York | 2005-07-01 | 2005-07-01 | ICT Project Management [0.00 %] | 2005-07-01 | 2005-07-01 | 329558 | TRUE | TRUE | PI Direct | 309589 |  | Joe Vespa | 232192 |  | 220901 | 294535 | William Buttlar | PVMT
414 | R59 Research Project Start! | R59 | Pavement Damage | 1 | R59: Pavement Damage | FY09-FY11 IGA |  | Nick York | 2006-01-01 | 2006-01-01 | ICT Project Management [0.00 %] | 2006-01-01 | 2006-01-01 | 317494 | TRUE | TRUE | PI Direct | 293893 |  | Mark Gawedzinski | 220420 |  | 233700 | 311599 | Imad Al-Qadi | PVMT
415 | R60-ADMIN (FY06-08 IGA) Research Project Start! | R60-ADMIN (FY06-08 IGA) | R60-ADMIN (FY06-08 IGA) | 1 | R60-ADMIN (FY06-08 IGA): R60-ADMIN (FY06-08 IGA) | FY06-FY08 IGA |  | Nick York | 2005-07-01 | 2005-07-01 | ICT Project Management | 2005-07-01 | 2005-07-01 | 779998 | TRUE | TRUE | Admin Line Item | 1040000 |  | Megan Swanson | 780000 |  | 780000 | 1040000 | Kristi Anderson | Other / Department Wide
416 | R60-ADMIN (FY09-11 IGA) Research Project Start! | R60-ADMIN (FY09-11 IGA) | R60-ADMIN (FY09-11 IGA) | 1 | R60-ADMIN (FY09-11 IGA): R60-ADMIN (FY09-11 IGA) | FY09-FY11 IGA |  | Audrey Donoho | 2008-07-01 | 2008-07-01 | ICT Project Management | 2008-07-01 | 2008-07-01 | 892939 | TRUE | TRUE | Admin Line Item | 995000 |  | Megan Swanson | 995000 |  | 995000 | 995000 | Kristi Anderson | Other / Department Wide
417 | R60-ADMIN (FY12-17 IGA) Research Project Start! | R60-ADMIN (FY12-17 IGA) | R60-ADMIN (FY12-17 IGA) | 1 | R60-ADMIN (FY12-17 IGA): R60-ADMIN (FY12-17 IGA) | FY12-FY17 IGA |  | Audrey Donoho | 2011-07-01 | 2011-07-01 | ICT Project Management | 2011-07-01 | 2011-07-01 | 3132685 | TRUE | TRUE | Admin Line Item | 2700000 |  | Megan Swanson | 2700000 |  | 2700000 | 2700000 | Kristi Anderson | Other / Department Wide
418 | R60-ADMIN (FY18-24 IGA) Research Project Start! | R60-ADMIN (FY18-24 IGA) | R60-ADMIN (FY18-24 IGA) | 2 | R60-ADMIN (FY18-24 IGA): R60-ADMIN (FY18-24 IGA) | FY18-FY24 IGA |  | Kristi Anderson | 2017-07-01 | 2017-07-01 | Kristi Anderson | 2017-07-01 | 2017-07-01 | 3177391 | TRUE | TRUE | Admin Line Item | 3290000 | 728 | John Senger | 3290000 | In-State University | 1290000 | 1290000 | Kristi Anderson | Other / Department Wide | 3741.43
419 | R60-ADMIN (FY25-30 IGA) Research Project Start! | R60-ADMIN (FY25-30 IGA) | R60-ADMIN (FY25-30 IGA) | 2 | R60-ADMIN (FY25-30 IGA): R60-ADMIN (FY25-30 IGA) | Open |  | Nick York | 2024-07-01 | 2024-07-01 | Kristi Anderson [0.00 %], Abrielle Zinkl [0.00 %] | 2024-07-01 | 2024-07-01 | 888313 | TRUE | TRUE | Admin Line Item | 3900000 | 0 | John Senger | 3900000 | In-State University | 3900000 | 3900000 | Kristi Anderson | Other / Department Wide | 2332.67

## QPR
| Project ID | Project Title | Start Date | Original End Date | Current End Date | Original Budget | Proj. Spending to Date | IDOT Spending to Date | Current IDOT Budget | Current Proj. Budget | Primary Investigator | TRP Chair | TAGs
0 | R27-001 | Characterization of IL Aggregates for Subgrade Replacement and Subbase") | 2006-01-01 | 2008-06-30 | 2009-06-30 | 344799 | 430678 | 99329 | 299329 | 399101 | Erol Tutumluer | Riyad Wahab | PVMT
1 | R27-002 | Nighttime Construction: Evaluation of Lighting Glare for Highway Construction in IL") | 2006-01-01 | 2007-12-31 | 2007-12-31 | 218684 | 186724 | 31557 | 141164 | 223573 | Khaled El-Rayes | Dennis Huckaba | SAF
2 | R27-003 | Design and Concrete Material Requirements for Ultra-Thin Whitetopping Procedures") | 2006-01-01 | 2007-12-31 | 2008-03-31 | 230872 | 263052 | 85335 | 185764 | 247685 | Jeffery Roesler | James Krstulovich | PVMT
3 | R27-004 | Radiation Detection Pilot Program") | 2006-01-01 | 2007-06-30 | 2007-06-30 | 59789 | 37407 | 6355 | 44842 | 59789 | William Dunn | Joseph Hill | OPS
4 | R27-005 | Bus-Only Shoulder Riding") | 2007-08-16 | 2008-06-30 | 2009-01-31 | 90603 | 96025 | 7655 | 67952 | 90603 | Vonu Thakuriah | Charles Abraham | MFM
5 | R27-006 | Illinois StreamStats") | 2006-03-01 | 2008-06-30 | 2008-06-30 | 90000 | 85160 | 0 | 60000 | 120000 | David Soong | Matthew O'Connor | BAF
6 | R27-007 | Update the IL Carbon Monoxide Screen for Intersections Model (COSIM)") | 2007-02-01 | 2007-08-31 | 2007-08-31 | 22181 | 17661 | 2443 | 16635 | 22181 | Scott Peters | Walt Zyznieuski | ENV
7 | R27-008 | Hot Mix Asphalt (HMA) Sampling") | 2006-06-01 | 2007-06-30 | 2007-06-30 | 22100 | 15608 | 996 | 16550 | 22100 | Mostafa Elseifi | Jim Trepanier | PVMT
8 | R27-009 | I-39 Kishwaukee Bridge Monitoring") | 2006-07-01 | 2008-06-30 | 2008-06-30 | 133849 | 142801 | 611 | 101738 | 133849 | Ming Wang | Todd Ahrens | BAF
9 | R27-010 | Mobile Source Air Toxics (MSAT): A Midwest Peer Exchange") | 2006-07-01 | 2007-02-28 | 2007-02-28 | 50266 | 36329 | 5596 | 37679 | 50266 | Jane Lin | Walt Zyznieuski | ENV
10 | R27-011 | Determination of Usable Residual Asphalt Binder in RAP") | 2006-07-01 | 2008-06-30 | 2008-06-30 | 133919 | 222235 | 56577 | 157738 | 210340 | Imad Al-Qadi | Jim Trepanier | PVMT
11 | R27-012 | Cold In-Place Recycling with Asphalt Products (CIRwAP)") | 2006-07-01 | 2008-06-30 | 2008-08-31 | 150000 | 159675 | 12500 | 112500 | 150000 | Marshall Thompson | Kevin Burke | PVMT
12 | R27-013 | Update Condition Rating Survey (CRS) Calculation/Prediction Models") | 2006-07-01 | 2007-06-30 | 2007-08-31 | 139874 | 94853 | 6829 | 104905 | 139874 | Laura Heckel | David Felts | PLAN
13 | R27-014 | Commercial Vehicle Information Systems and Networks (CVISN)") | 2006-09-06 | 2007-03-31 | 2007-03-31 | 69297 | 49070 | 4572 | 51942 | 69297 | Peter Nelson | Charles Sikaras | PLAN
14 | R27-015 | Regional Warehouse Trip Production") | 2007-01-01 | 2007-12-31 | 2008-07-31 | 66667 | 70853 | 9920 | 50000 | 66667 | Jon Devries | Charles Abraham | MFM
15 | R27-016 | Truck Parking Facilities Program Design") | 2007-01-01 | 2008-03-31 | 2008-03-31 | 56132 | 27779 | 9572 | 40000 | 56132 | Peter Beltemacchi | Charles Abraham | MFM
16 | R27-017 | Effectiveness of Transit Strategies Targeting Elderly People") | 2006-07-01 | 2007-06-30 | 2008-11-30 | 82500 | 82987 | 8469 | 61875 | 82500 | Kouros Mohammadian | Charles Abraham | MFM
17 | R27-018 | Crash Data Analysis and Engineering Solutions for Local Agencies") | 2006-07-01 | 2007-12-31 | 2008-12-31 | 150000 | 159675 | 12500 | 123751 | 165001 | Yanfeng Ouyang | Kevin Burke | SAF
18 | R27-019 | Pier Scour Prediction in Cohesive Soils: Use of EFA-SRICOS Method in IL") | 2006-08-01 | 2009-06-30 | 2010-06-30 | 310667 | 360851 | 38000 | 238000 | 352167 | Tim Straub | Matthew O'Connor | BAF
19 | R27-020 | Develop Safety Performance Functions (SPF) for Illinois") | 2007-01-01 | 2008-12-31 | 2008-12-31 | 140000 | 154734 | 5001 | 105001 | 140000 | Yanfeng Ouyang | David Piper | SAF
20 | R27-021 | Alternative Intersections: Roundabout Evaluation and Design") | 2007-01-01 | 2007-12-31 | 2008-08-31 | 53663 | 56870 | 68 | 43368 | 57824 | Ray Benekohal | Sean Coyle | SAF
21 | R27-022 | Regional Data Archiving and Management for Northeast Illinois") | 2007-04-01 | 2008-06-30 | 2008-08-31 | 150000 | 79836 | 6249 | 56249 | 150000 | Yanfeng Ouyang | John Benda | OPS
22 | R27-023 | Evaluation of HMA Overlays in Illinois") | 2007-07-01 | 2008-06-30 | 2008-08-31 | 134940 | 140855 | 9240 | 99240 | 134940 | Angela Wolters | Jeffrey South | PLAN
23 | R27-024 | Evaluation/Modification of IDOT Foundation Piling Design and Construction Policy") | 2007-01-01 | 2008-12-31 | 2009-03-31 | 159000 | 161570 | 11752 | 118534 | 158045 | Jim Long | Bill Kramer | BAF
24 | R27-025 | Modification of IDOT Integral Abutment Design Limitations and Details") | 2007-01-01 | 2008-12-31 | 2009-03-31 | 119825 | 127990 | 6435 | 89835 | 119780 | Scott Olson | Bill Kramer | BAF
25 | R27-026 | Free-Cutting Brass Breakaway Couplings") | 2007-04-01 | 2008-09-30 | 2009-04-30 | 119647 | 125884 | 9734 | 89735 | 119647 | Dan Kuchma | Chris Hahin | BAF
26 | R27-027 | Expansive Characteristics of Reclaimed Asphalt") | 2007-02-01 | 2008-06-30 | 2009-04-30 | 75000 | 79561 | 6055 | 56250 | 75000 | Erol Tutumluer | Sheila Beshears | PVMT
27 | R27-028-T1 | Conference and Training Support") | 2007-09-01 | 2008-06-30 | 2011-06-30 | 194025 | 239813 | 59356 | 145518 | 194025 | Imad Al-Qadi | David Lippert | Other / Department Wide
28 | R27-028-T2 | Utah LTAP GIS Software Replication/ Training in IL") | 2007-11-01 | 2008-10-31 | 2008-10-31 | 75165 | 80013 | 6374 | 56374 | 75165 | Imad Al-Qadi | David Lippert | Other / Department Wide
29 | R27-028-T3 | 8th International Conference on Bearing Capacity of Roads") | 2009-05-01 | 2009-09-30 | 2009-09-30 | 15000 | 11250 | 1250 | 11250 | 15000 | Erol Tutumluer | Amy Schutzbach | PVMT
30 | R27-029 | Particulate Matter 2.5 and 10 Hot Spot Analysis: A Midwest Peer Exchange") | 2007-07-01 | 2008-02-29 | 2008-06-30 | 60000 | 63870 | 5000 | 45000 | 60000 | Jane Lin | Walt Zyznieuski | ENV
31 | R27-030 | Evaluation of 3-D Laser Scanning for Construction Applications") | 2007-09-16 | 2009-08-15 | 2009-08-15 | 200000 | 197347 | 42942 | 149452 | 199246 | Dianne Slattery | Ted Nemsky | CON
32 | R27-031 | Wind Powered Electrical Systems: Highway Rest Areas and Weigh Stations and Team Section Buildings") | 2007-08-01 | 2008-06-30 | 2008-12-31 | 70000 | 71058 | 64 | 52500 | 70000 | Patrick Chapman | Dave Johnson | OPS
33 | R27-032 | Rolling Lane Closures") | 2007-09-01 | 2008-08-31 | 2008-12-31 | 100017 | 105549 | 5001 | 75002 | 103779 | Doug Steele | Aaron Weatherholt | OPS
34 | R27-033 | Queue and Users' Cost in Highway Work Zones") | 2007-10-01 | 2009-11-30 | 2010-08-31 | 160000 | 175363 | 17717 | 120000 | 160000 | Ray Benekohal | Marshall Metcalf | OPS
35 | R27-034 | Pavement Program Planning Process Based on Benefit-Cost Analysis") | 2007-10-01 | 2008-09-30 | 2009-04-30 | 80000 | 88430 | 0 | 60000 | 80000 | Yanfeng Ouyang | Jeffrey South | PLAN
36 | R27-035 | Simple Cost Effective Scour Sensor") | 2007-08-01 | 2008-06-30 | 2008-10-31 | 77617 | 74220 | 2292 | 52500 | 77617 | Farhad Ansari | Dave Copenbarger | BAF
37 | R27-036 | Transfer and Development Length of Prestressing Tendons in Full-scale AASHTO Prestressed Concrete Girders using Self-Consolidating Concrete") | 2007-08-01 | 2008-06-30 | 2008-09-30 | 50000 | 53225 | 7500 | 37500 | 50000 | Bassem Andrawes | Tom Domagalski | BAF
38 | R27-037 | Impact of High RAP Content on Pavement Structural Performance") | 2008-07-01 | 2010-06-30 | 2011-12-31 | 242411 | 361082 | 40702 | 240702 | 320937 | Imad Al-Qadi | Jim Trepanier | PVMT
39 | R27-038 | Development of an Improved Specification for Maximum Plastic Concrete Temperatures") | 2007-09-01 | 2010-06-30 | 2010-06-30 | 247098 | 263195 | 85323 | 185323 | 247098 | John Popovics | Derek Parish | PVMT
40 | R27-039 | Context Sensitive Solutions Online Training Course Development") | 2008-02-16 | 2008-06-30 | 2008-09-30 | 50000 | 47724 | 3624 | 37500 | 50000 | James Hall | Susan Stitt | PLAN
41 | R27-040 | Safety Impacts of Highway Shoulder Attributes in Illinois") | 2008-01-01 | 2009-12-31 | 2010-09-30 | 140000 | 137586 | 1934 | 105000 | 140000 | Zongzhi Li | David Piper | SAF
42 | R27-041 | Performance of I-57 Recycled Concrete Pavement") | 2008-01-01 | 2008-06-30 | 2008-11-30 | 54000 | 57483 | 500 | 40500 | 54000 | Jeffery Roesler | Mark Gawedzinski | PVMT
43 | R27-042 | Thin Quiet Long-Lasting High Friction Surface Layer") | 2008-03-07 | 2011-06-30 | 2013-03-31 | 494890 | 782070 | 22814 | 523054 | 697405 | Imad Al-Qadi | Tom Zehr | PVMT
44 | R27-043 | Utah LTAP GIS Software Conversion and Training for IL Use") | 2007-11-01 | 2008-10-31 | 2008-10-31 | 20000 | 19812 | 5000 | 15000 | 20000 | Yanfeng Ouyang | Kevin Burke | Other / Department Wide
45 | R27-044 (FY09-11 IGA) | Tech Transfer (FY09-11 IGA)") | 2008-07-01 | 2011-06-30 | 2011-06-30 | 455539 | 327880 | 6864 | 341654 | 455539 | Imad Al-Qadi | Megan Swanson | Other / Department Wide
46 | R27-044 (FY12-17 IGA) | Tech Transfer (FY12-17 IGA)") | 2011-07-01 | 2017-06-30 | 2017-06-30 | 1650000 | 1663082 | 85103 | 1237500 | 1650000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide
47 | R27-044-T1 | IDOT Pavement Design Course Development") | 2012-06-01 | 2013-05-31 | 2013-07-31 | 150000 | 143971 | 8652 | 112500 | 150000 | Hasan Ozer | Charles Wienrank | PVMT
48 | R27-045 (FY09-11 IGA) | IT Support (FY09-11 IGA)") | 2008-07-01 | 2011-06-30 | 2011-06-30 | 447603 | 356113 | 28273 | 335702 | 447603 | Imad Al-Qadi | Megan Swanson | Other / Department Wide
49 | R27-045 (FY12-17 IGA) | IT Support (FY12-17 IGA)") | 2011-07-01 | 2017-06-30 | 2017-06-30 | 1002720 | 377742 | 48239 | 752040 | 1002720 | Imad Al-Qadi | Megan Swanson | Other / Department Wide
50 | R27-045-T1 | Evaluation of 3-D Laser Scanning Equipment") | 2013-10-01 | 2015-03-31 | 2018-06-30 | 197280 | 226522 | 9165 | 215121 | 286102 | Greg Renshaw | Ryan Culton | CON
51 | R27-046 (FY09-11 IGA) | Special Projects Eng (FY09-11 IGA)") | 2008-07-01 | 2011-06-30 | 2011-06-30 | 480000 | 445401 | 81010 | 360000 | 480000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide
52 | R27-046 (FY12-17 IGA) | Special Projects Eng (FY12-17 IGA)") | 2011-07-01 | 2017-06-30 | 2017-06-30 | 1600000 | 1527269 | 96535 | 1200000 | 1600000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide
53 | R27-047 | Illinois Tribunal Workshop") | 2008-05-13 | 2008-05-13 | 2008-05-13 | 0 | 0 |  | 0 | 0 |  |  | ENV
54 | R27-048 | Travel Demand Modeling for Small & Medium Size MPOs in Illinois") | 2009-01-01 | 2010-10-31 | 2011-06-30 | 160000 | 159652 | 19996 | 120000 | 160000 | Rita Morocoima-Black | Susan Stitt | PLAN
55 | R27-049 | Documentation of Contract Quantities Training") | 2008-05-01 | 2011-06-30 | 2010-06-30 | 300000 | 197298 | 50000 | 150000 | 200000 | Imad Al-Qadi | Mike Renner | CON
56 | R27-050 | Trip Chaining Behavior of Senior Travelers & Applications to Public Transportation Planning") | 2008-08-16 | 2009-12-31 | 2010-12-31 | 96063 | 110887 | 7675 | 77675 | 110887 | Kouros Mohammadian | Charles Abraham | MFM
57 | R27-051 | Guidelines | 2008-11-01 | 2009-10-31 | 2010-09-30 | 80536 | 77154 | 7618 | 59560 | 80536 | Peter Beltemacchi | Charles Abraham | MFM
58 | R27-052 | Studying & Minimizing Traffic Related Work Zone Crashes in Illinois") | 2008-09-16 | 2010-09-15 | 2010-09-15 | 209999 | 241292 | 57499 | 157499 | 209999 | Khaled El-Rayes | Marshall Metcalf | SAF
59 | R27-053 | Roadway Lighting Evaluation Tools") | 2008-09-04 | 2008-09-04 | 2008-09-04 | 0 | 0 |  | 0 | 0 |  |  | SAF
60 | R27-054 | Storm Water Pollution | 2009-01-01 | 2011-12-31 | 2012-12-31 | 450000 | 532380 | 74409 | 374422 | 499229 | Prasanta Kalita | Joe Vespa | ENV
61 | R27-055 | Instrumentation & Monitoring of Extreme Integral Abutment Bridges in Illinois") | 2008-08-16 | 2011-06-30 | 2012-03-31 | 330000 | 285982 | 24073 | 272249 | 362999 | Scott Olson | Bill Kramer | BAF
62 | R27-056 | Transfer & Development Lengths in Prestressed Self-Consolidating Concrete Bridge Box & I-Girders") | 2008-07-16 | 2010-06-30 | 2011-02-28 | 190000 | 204324 | 42284 | 142500 | 190000 | Bassem Andrawes | Tom Domagalski | BAF
63 | R27-057 | Superiority & Constructability of Fibrous Additives for Bridge Deck Overlays") | 2009-01-01 | 2010-12-31 | 2011-12-31 | 160000 | 165804 | 20000 | 120000 | 160000 | Mohammad Alhassan | Gary Kowalski | BAF
64 | R27-058 | Evaluation of Wireless Detection Systems at RR Crossings & Signalized Intersections") | 2008-07-01 | 2010-06-30 | 2011-03-31 | 219624 | 256877 | 63865 | 164718 | 219624 | Ray Benekohal | Yogesh Gautam | OPS
65 | R27-059 | Evaluation of Performance of Solar Powered Flashing Beacons") | 2008-07-01 | 2010-06-30 | 2011-03-31 | 218925 | 258061 | 64193 | 164194 | 218925 | Ray Benekohal | Yogesh Gautam | OPS
66 | R27-060 | Mechanistic-Empirical Design | 2008-07-01 | 2011-06-30 | 2014-06-30 | 207992 | 438622 | 30338 | 363118 | 484158 | Marshall Thompson | Charles Wienrank | PVMT
67 | R27-061 | Mechanistic-Empirical Design | 2009-01-01 | 2011-06-30 | 2014-08-31 | 236260 | 517489 | 47022 | 366506 | 488675 | Jeffery Roesler | Charles Wienrank | PVMT
68 | R27-062 | Material Quality Testing Risk Assessment & Multi-State Peer Exchange") | 2009-02-01 | 2010-01-31 | 2010-12-31 | 94934 | 93750 | 331 | 83200 | 110934 | Tim Murphy | David Lippert | PVMT
69 | R27-063 | Evaluation of the Long-Term Durability of Joints Cut Using Early-Entry Saws on Rigid Pavements") | 2008-11-01 | 2009-10-31 | 2010-09-30 | 86831 | 94730 | 930 | 70930 | 94574 | Thomas Dam | Mark Gawedzinski | PVMT
70 | R27-064 | Development of a Highway Incident Management Operational & Training Guide") | 2009-07-01 | 2011-06-30 | 2011-06-30 | 136400 | 149318 | 2011 | 102011 | 136400 | Huaguo Zhou | Geno Koehler | OPS
71 | R27-065 | Safety Analyst Software") | 2009-09-11 | 2009-09-11 | 2009-09-11 | 0 | 0 |  | 0 | 0 |  |  | SAF
72 | R27-066 | Effectiveness of Innovative Speed Enforcement Techniques in Illinois") | 2009-11-01 | 2012-10-31 | 2012-10-31 | 300397 | 314232 | 24654 | 225000 | 300397 | Hani Mahmassani | Paul Lorton | SAF
73 | R27-067 | National Safety Performance (SPF) Summit") | 2009-01-01 | 2009-12-31 | 2009-12-31 | 100000 | 102474 | 5000 | 75000 | 100000 | Yanfeng Ouyang | Priscilla Tobias | SAF
74 | R27-068 | Midwest Transportation Air Quality Summit") | 2009-03-16 | 2009-12-31 | 2009-12-31 | 70000 | 46467 | 4135 | 34135 | 45513 | Michael Koerber | Walt Zyznieuski | ENV
75 | R27-069 | Improved Design for Driven Piles Based on a Pile Load Test Program in Illinois") | 2009-01-01 | 2010-12-31 | 2012-06-30 | 413333 | 405571 | 1828 | 342818 | 457091 | Jim Long | Bill Kramer | BAF
76 | R27-070 | Calibration & Refinement of Illinois' Earthquake Resisting System Bridge Design Methodology") | 2009-01-01 | 2011-12-31 | 2012-12-31 | 625000 | 786244 | 62560 | 562560 | 750080 | James LaFave | Dan Tobias | BAF
77 | R27-071 | Field Implementation and Evaluation of the Simple Cost-Effective Scour Sensor") | 2009-02-01 | 2010-01-31 | 2010-06-30 | 164000 | 190892 | 61450 | 161450 | 215267 | Farhad Ansari | Dave Copenbarger | BAF
78 | R27-072 | Rolling Lane Closures - Phase II") | 2009-01-16 | 2010-01-31 | 2010-01-31 | 175000 | 175000 | 31250 | 131250 | 175000 | Doug Steele | Aaron Weatherholt | OPS
79 | R27-073 | Distance Technology Transfer Course Content Development") | 2009-02-01 | 2012-01-31 | 2013-03-31 | 300000 | 204143 | 61001 | 225000 | 300000 | James Hall | Kevin Burke | Other / Department Wide
80 | R27-074 | Green Friendly Best Management Practices (BMP) for Interstate Rest Areas") | 2010-01-01 | 2010-12-31 | 2010-12-31 | 100000 | 117472 | 5000 | 75000 | 100000 | Khaled El-Rayes | Craig Mitckes | ENV
81 | R27-075 | Clearview Font in Traffic Signs: Assessing IDOT Experiences and Needs") | 2010-04-01 | 2012-03-31 | 2012-03-31 | 230000 | 233196 | 68951 | 170665 | 230000 | Hani Mahmassani | Julia Fox | OPS
82 | R27-076 | LED Roadway Lighting Evaluation and Field Testing") | 2009-11-01 | 2011-10-31 | 2012-03-31 | 276200 | 318985 | 13410 | 226950 | 302599 | Ray Benekohal | Mark Seppelt | OPS
83 | R27-077 | Evaluating Pavement Markings on Portland Cement Concrete (PCC) & Various Asphalt Surfaces") | 2009-12-01 | 2012-11-30 | 2013-11-30 | 300000 | 372866 | 72902 | 276963 | 369284 | Carmine Dwyer | Kelly Senger | PVMT
84 | R27-078 | Evaluating the Effects of Various Asphalt Binder Additives/Modifiers on Moisture Sensitivity in HMA") | 2010-02-16 | 2012-08-15 | 2013-12-31 | 546078 | 616728 | 9478 | 409558 | 546077 | Imad Al-Qadi | Jim Trepanier | PVMT
85 | R27-079 | Designing | 2009-08-16 | 2011-12-31 | 2013-12-31 | 692716 | 678509 | 83384 | 519537 | 692716 | William Buttlar | Matt Mueller | PVMT
86 | R27-080 | Fatigue Testing of Brass Breakaway Couplings") | 2009-07-01 | 2010-06-30 | 2010-12-31 | 85000 | 97836 | 3750 | 63750 | 85000 | Greg Banas | Chris Hahin | BAF
87 | R27-081 | Field Performance Evaluations of IL Aggregates for Subgrade Replacement & Subbase - Phase II") | 2010-01-01 | 2011-12-31 | 2011-12-31 | 335017 | 346529 | 50451 | 251263 | 335017 | Erol Tutumluer | Greg Heckel | BAF
88 | R27-082 | Strength of Bridge Wood Pilings Retrofits for Moment Resistance") | 2009-08-16 | 2012-02-15 | 2012-08-15 | 180000 | 223345 | 50081 | 150000 | 200000 | Bassem Andrawes | Dan Tobias | BAF
89 | R27-083 | Good Movement Study in IL: Applications to Freight Transportation & Logistics") | 2010-01-01 | 2011-08-15 | 2011-08-15 | 159920 | 170852 | 19940 | 119940 | 159920 | Kouros Mohammadian | Mike Garcia | PLAN
90 | R27-084 | Develop Travel Reliability Inventory for Highway Networks") | 2010-04-01 | 2010-12-31 | 2011-06-30 | 125407 | 130317 | 520 | 91672 | 125407 | Marco Nie | Jeff Galas | PLAN
91 | R27-085 | R.E.'s Materials Mgmt. Training") | 2010-03-03 | 2010-03-03 | 2010-03-03 | 0 | 0 |  | 0 | 0 |  |  | PVMT
92 | R27-086 | An Expert Systems Approach to Highway Construction Scheduling") | 2010-07-01 | 2011-06-30 | 2011-06-30 | 89113 | 81901 | 1407 | 66833 | 89113 | Dianne Slattery | Mike Ripka | CON
93 | R27-087 | Implementing Pavement Management Systems for Local Agencies") | 2010-05-01 | 2011-10-31 | 2011-08-31 | 99851 | 109164 | 4324 | 74390 | 99851 | Angela Wolters | Kevin Burke | PLAN
94 | R27-088 | Bridge Decks: Mitigation of Cracking & Increased Durability") | 2010-05-16 | 2013-05-15 | 2013-06-15 | 299982 | 364520 | 48995 | 250779 | 334372 | Paramita Mondal | Dan Tobias | BAF
95 | R27-089 | Illinois Highway Safety Manual Workshop") | 2010-08-16 | 2011-03-15 | 2011-06-30 | 153333 | 169820 | 13583 | 115000 | 153333 | Yanfeng Ouyang | Priscilla Tobias | SAF
96 | R27-090 | Investigation of Contributing Factors of Wrong-Way Driving on Freeways") | 2010-07-01 | 2012-06-30 | 2015-09-30 | 230986 | 484303 | 53511 | 355576 | 474421 | Huaguo Zhou | Richard Coakley / Priscilla Tobias | SAF
97 | R27-091 | Evaluating of Traffic Flow Monitoring Technologies: Cicero-Midway Smart Corridor Case Study") | 2010-01-01 | 2010-12-31 | 2010-12-31 | 99938 | 106124 | 4954 | 74954 | 99938 | Jakob Eriksson | Jeff Galas | OPS
98 | R27-092 | Engineering Software Review: MicroStation vs. AutoCAD") | 2009-11-13 | 2009-11-13 | 2009-11-13 | 0 | 0 |  | 0 | 0 |  |  | Other / Department Wide
99 | R27-093 | Transportation Conformity Particulate Matter Hot-Spot Air Quality Modeling") | 2010-11-01 | 2011-10-31 | 2013-06-30 | 84430 | 108086 | 2791 | 73305 | 97749 | Jane Lin | Walt Zyznieuski | ENV
100 | R27-094 | Performance Evaluation of Snow & Ice Plows") | 2011-09-01 | 2013-08-31 | 2015-11-30 | 250000 | 355632 | 52708 | 253523 | 338708 | Souhail Elhouar | Tim Peters | OPS
101 | R27-095 | Field Evaluation of Smart Sensor Vehicle Detectors at Intersections & RR Crossings") | 2010-08-16 | 2012-08-15 | 2014-12-31 | 245086 | 334076 | 55665 | 255665 | 340887 | Ray Benekohal | Yogesh Gautam | OPS
102 | R27-096 | Pedestrian/Bicyclist Warning Devices & Signs at Hwy.-Rail & Pathway-Rail Grade Crossings") | 2011-01-01 | 2012-12-31 | 2012-12-31 | 200000 | 185679 | 43945 | 150000 | 202658 | Paul Metaxatos | Kyle Armstrong | OPS
103 | R27-097 | Evaluation of Flashing Yellow Arrows (FYA) for Protected/Permissive Left Turn (PPLT) Control") | 2010-11-01 | 2012-11-30 | 2016-03-31 | 243854 | 426681 | 63885 | 264649 | 399153 | Kerrie Schattler | Randy Laninga | SAF
104 | R27-098 | Evaluation of Concrete Cylinder Match Curing & Evaluation of 4") | 2010-08-16 | 2012-02-15 | 2012-06-30 | 188778 | 232068 | 66411 | 172500 | 230000 | John Popovics | Douglas Dirks | BAF
105 | R27-099 | Improvement for Determining the Axial Capacity of Drilled Shafts in Shale in Illinois") | 2011-11-01 | 2013-04-30 | 2013-04-30 | 172500 | 143970 | 2919 | 129375 | 172500 | Timothy Stark | Bill Kramer | BAF
106 | R27-100 | Best Practices for Implementation of Tack Coat TRP Recommendations") | 2010-09-16 | 2013-03-15 | 2013-03-15 | 529445 | 500001 | 47318 | 396093 | 529445 | Imad Al-Qadi | Derek Parish | PVMT
107 | R27-101 | Funding Set Aside for B.S. & M.S. Students") | 2011-01-01 | 2016-06-30 | 2017-06-30 | 275000 | 156542 | 4016 | 137500 | 275000 | Imad Al-Qadi | Amy Schutzbach | Other / Department Wide
108 | R27-102 | Installation & Performance Testing of Ditch Checks & Inlet Protection Structures") | 2011-08-16 | 2014-08-15 | 2016-01-15 | 300000 | 443056 | 8433 | 308433 | 411244 | Prasanta Kalita | Joe Vespa | ENV
109 | R27-103 | Green Friendly Best Management Practices (BMP) for Interstate Rest Areas - Phase 2") | 2011-01-01 | 2012-12-31 | 2013-06-30 | 220000 | 245434 | 64721 | 165000 | 220000 | Khaled El-Rayes | Matt Sunderland | ENV
110 | R27-104 | Native Vegetation Establishment for IDOT Erosion Control BMPs") | 2012-01-01 | 2013-12-31 | 2014-05-31 | 192091 | 165257 | 44068 | 144068 | 192090 | Heidi Howard | Scott Marlow | ENV
111 | R27-105 | Improvement of IDOT Bridge Scour Estimation Method at Sites with Cohesive Soils Using SRICOS Zmax - Phase 2") | 2011-04-01 | 2013-03-31 | 2013-03-31 | 204000 | 156000 | 53000 | 153000 | 204000 | Tim Straub | Neil VanBebber | BAF
112 | R27-106 | Formability of New High Performance Grade 50 Structural Steel") | 2011-12-01 | 2012-11-30 | 2013-10-31 | 90000 | 103501 | 7626 | 77626 | 103500 | Semyon Vaynman | Chris Hahin | BAF
113 | R27-107 | Plate & Tube Short-Span Bridges for Co Roads") | 2013-07-02 | 2013-07-02 | 2013-07-02 | 0 | 0 |  | 0 | 0 |  |  | BAF
114 | R27-108 | Improving the Effectiveness of Nighttime Temporary Traffic Control Warning Devices") | 2011-09-01 | 2013-04-30 | 2013-10-31 | 160000 | 230949 | 70949 | 180000 | 240000 | Doug Steele | Tim Kell | OPS
115 | R27-109 | Effects of Flaggers & Spotters in Directing Work Zone Traffic for Illinois Freeways & Expressways") | 2011-11-01 | 2013-10-31 | 2013-10-31 | 167066 | 181106 | 25025 | 125299 | 167066 | Khaled El-Rayes | Paul Lorton | SAF
116 | R27-110 | Training & Implementing Findings of Queue & Users' Costs in Highway Work Zones - Phase 2") | 2012-04-16 | 2013-04-15 | 2013-04-15 | 85303 | 98409 | 3977 | 63977 | 85303 | Ray Benekohal | Paul Lorton | SAF
117 | R27-111 | Effects of Intersection Right-Turn Lane Design & Skew on Safety & Operations") | 2011-09-01 | 2013-08-31 | 2016-06-30 | 115800 | 296065 | 74877 | 175000 | 255415 | Kerrie Schattler | Dan Mlacnik | SAF
118 | R27-112 | Testing of Portland Cement (Current ASTM C150) with Limestone & Process Addition (ASTM C465)") | 2011-05-01 | 2013-04-30 | 2013-12-31 | 400001 | 424697 | 99780 | 299995 | 399987 | Mohsen Issa | John Huang | PVMT
119 | R27-113 | Modeling Seniors Activity - Travel Data - Phase 2") | 2011-07-01 | 2012-12-31 | 2013-08-15 | 125063 | 136286 | 3793 | 93793 | 125063 | Kouros Mohammadian | Amy Welk | MFM
120 | R27-114 | Restoration Progress & Flood Disturbance at IDOT Wetland Mitigation Sites") | 2011-10-01 | 2012-09-30 | 2013-03-31 | 81214 | 64762 | 1155 | 60000 | 81214 | Geoffrey Pociask | Tom Brooks | ENV
121 | R27-115 | Analysis of Superstructures of Integral Abutment Bridges") | 2012-03-01 | 2015-02-28 | 2017-08-15 | 300000 | 388957 | 58468 | 259178 | 345571 | James LaFave | Mark Shaffer | BAF
122 | R27-116 | Investigation of Methods & Approaches for Collecting & Recording Highway Inventory Data") | 2012-01-01 | 2013-06-30 | 2013-06-30 | 215000 | 217202 | 60859 | 161250 | 215000 | Huaguo Zhou | Rob Robinson | SAF
123 | R27-117 | National State Safety Engineers and Traffic Engineers Peer to Peer Workshop") | 2012-08-01 | 2013-06-30 | 2013-06-30 | 50000 | 57375 | 7500 | 37500 | 50000 | Yanfeng Ouyang | Priscilla Tobias | SAF
124 | R27-118 | Development of a Highway Incident Management Operational & Training Guide - Phase 2") | 2011-08-16 | 2013-08-15 | 2014-06-30 | 300001 | 374668 | 80896 | 280896 | 374668 | Ryan Fries | Geno Koehler | OPS
125 | R27-119 | Real-Time Information Dissemination Requirements for Illinois per New Federal Rules") | 2013-08-16 | 2015-02-15 | 2016-02-15 | 161256 | 234997 | 71829 | 172645 | 235770 | Ryan Fries | Kevin Price / Bruce Carmitchel | PLAN
126 | R27-120 | Evaluating All-Weather Pavement Markings & Lab Methods to Simulate Field Exposure") | 2012-04-01 | 2014-12-31 | 2019-06-30 | 400000 | 516044 | 70186 | 378585 | 500614 | Neal Hawkins | Kelly Senger | OPS
127 | R27-121 | Polymer-Modified HMA & WMA Mixtures w/ RAP & RAS (Phase 1)") | 2015-03-05 | 2015-03-05 | 2015-03-05 | 0 | 0 |  | 0 | 0 |  |  | PVMT
128 | R27-122 | Improvement of Driven Pile Installation and Design in Illinois: Phase 2") | 2012-07-01 | 2014-06-30 | 2014-08-31 | 304792 | 303084 | 28594 | 228594 | 304792 | Jim Long | Bill Kramer | BAF
129 | R27-123 | Street Lighting Technologies--LED Street Lighting Evaluation | 2012-10-16 | 2014-10-15 | 2015-01-15 | 282000 | 337802 | 11500 | 211500 | 282000 | Ray Benekohal | Mark Seppelt | OPS
130 | R27-124 | Evaluation of Porous Granular Embankment Materials Used as Pavement Subgrade/Granular Subbase") | 2012-08-16 | 2014-08-15 | 2015-07-31 | 460000 | 506080 | 64958 | 364963 | 486617 | Erol Tutumluer | Sheila Beshears | PVMT
131 | R27-125 | Sustainable Aggregates Production -- Green Applications for Aggregate By-Products") | 2013-02-01 | 2015-01-31 | 2015-05-31 | 220000 | 257562 | 65000 | 165000 | 220000 | Erol Tutumluer | Sheila Beshears | PVMT
132 | R27-126 | Temporary Stabilization Specification Improvements") | 2012-08-01 | 2014-06-30 | 2014-09-30 | 249996 | 206779 | 47360 | 187497 | 249996 | Mark Grinter | Matt Sunderland | ENV
133 | R27-127 | Safety and Efficiency Benefits of Implementing Adaptive Signal Control Technology in Illinois") | 2013-01-01 | 2015-12-31 | 2019-06-30 | 400000 | 1075446 | 64874 | 764874 | 1019832 | Ray Benekohal | Kyle Armstrong | OPS
134 | R27-128 | Testing Protocols to Ensure Performance of High Asphalt Binder Replacement Mixes Using RAP & RAS") | 2013-01-01 | 2015-12-31 | 2015-12-31 | 585000 | 831023 | 54667 | 584390 | 779997 | Imad Al-Qadi | Matt Mueller | PVMT
135 | R27-129 | Implementation of AIMS in Measuring Aggregate Resistance to Polishing | 2012-12-01 | 2014-02-28 | 2014-02-28 | 125000 | 125035 | 2845 | 93750 | 125000 | Enad Mahmoud | Sheila Beshears | PVMT
136 | R27-130 | Development of Improved Overlay Thickness Design Alternatives for Local Roads") | 2012-08-16 | 2014-08-15 | 2015-07-31 | 120000 | 143441 | 0 | 90000 | 120000 | Erol Tutumluer | Thomas Winkelman / Scott Lackey | PVMT
137 | R27-131 | Leveraging Traffic and Surveillance Video Cameras for Urban Traffic") | 2012-07-01 | 2013-12-31 | 2014-12-31 | 100000 | 231412 | 47842 | 149985 | 199980 | Jakob Eriksson | William Morgan | PLAN
138 | R27-132 | Incorporating NEPA into the IDOT and MPO Planning Process") | 2012-07-01 | 2014-06-30 | 2014-06-30 | 179703 | 205772 | 34561 | 134777 | 179703 | Nora El-Gohary | Bruce Carmitchel | PLAN
139 | R27-133 | Calibration and Refinement of Illinois Earthquake Resisting System Bridge Design Methodology | 2013-10-01 | 2016-06-30 | 2018-08-31 | 300000 | 358653 | 25401 | 225847 | 301129 | James LaFave | Mark Shaffer | BAF
140 | R27-134 | Strengthening of Bridge Wood Pilings Retrofits for Moment Resistance - Phase II") | 2012-11-16 | 2015-11-15 | 2016-05-15 | 350000 | 367383 | 56976 | 262500 | 350000 | Bassem Andrawes | Jeff Burke | BAF
141 | R27-135 | Enhancements to the Highway Construction Expert System | 2013-05-01 | 2015-01-31 | 2015-05-31 | 180968 | 188165 | 32183 | 133614 | 180968 | Dianne Slattery | Ted Nemsky | CON
142 | R27-136 | Development of Public Right-of Way Accessibility Guideline (PROWAG) Resource Material") | 2013-10-01 | 2015-11-30 | 2016-01-31 | 216665 | 253629 | 62485 | 162499 | 216665 | Khaled El-Rayes | Juliet Shoultz | OPS
143 | R27-137 | Evaluation of PCC Pavement and Structure Coring and In Situ Testing Alternatives") | 2013-07-01 | 2015-12-31 | 2016-12-31 | 250000 | 305865 | 770 | 215625 | 287500 | John Popovics | Douglas Dirks | BAF
144 | R27-138 | Options & Recommendations for Web Data Base of Material & Construction Inspection") | 2013-09-01 | 2014-02-28 | 2014-04-30 | 80000 | 75129 | 6844 | 60000 | 80000 | Constance Kelly | Mark Neale | CON
145 | R27-139 | Bridge Decks: Mitigation of Shrinkage Cracking (Phase 2 Study)") | 2013-07-01 | 2016-06-30 | 2016-06-30 | 300000 | 418685 | 74159 | 275805 | 367739 | Paramita Mondal | James Krstulovich | PVMT
146 | R27-140 | Effectiveness of Exterior Beam Rotation Prevention Systems for Bridge Deck Construction") | 2014-01-01 | 2014-01-01 | 2016-06-30 | 300000 | 360552 | 24267 | 225000 | 300000 | Riyadh Hindi | Mark Thomson | BAF
147 | R27-141 | Effective Post-Construction Best Management Practices to Infiltrate & Retain Storm Water Run-Off") | 2014-02-01 | 2017-01-31 | 2017-06-30 | 299442 | 347320 | 56891 | 256892 | 344303 | Abdolreza Osouli | Scott Marlow | OPS
148 | R27-142 | Evaluation of Software Simulation of Road Weather Information System") | 2014-10-01 | 2016-03-31 | 2016-09-30 | 250000 | 283440 | 12580 | 212580 | 283440 | Carmine Dwyer | Derek Parish / Ruben Boehler | OPS
149 | R27-143 | Tree Establishment in Response to Hydrology at IDOT Wetland Mitigation Sites") | 2013-09-01 | 2015-02-28 | 2015-02-28 | 79843 | 69194 | 6157 | 59882 | 79843 | Jeffrey Matthews | Tom Brooks | ENV
150 | R27-144 | Development & Implementation of Updated Urban Regional Flood Frequency Equations for Illinois (Phase 2 Study)") | 2013-08-01 | 2016-01-31 | 2016-06-30 | 426000 | 466000 | 49350 | 349350 | 466000 | Audrey Ishii | Matthew O'Connor | BAF
151 | R27-145 | Modified Standard Penetration Test-based Drilled Shaft Design Method for Weak Rocks (Phase 2 Study)") | 2014-01-01 | 2016-12-31 | 2017-12-16 | 669312 | 731350 | 46777 | 552200 | 736267 | Timothy Stark | Bill Kramer | BAF
152 | R27-146 | Ultrasonic Imaging for Concrete Infrastructure Condition Assessment and Quality Assurance") | 2013-07-01 | 2016-06-30 | 2017-04-30 | 500000 | 547904 | 75000 | 375000 | 500000 | John Popovics | Douglas Dirks / Gary Kowalski | CON
153 | R27-147 | Chloride Reduction Training") | 2014-03-17 | 2014-09-15 | 2014-09-15 | 100000 | 100000 | 5000 | 75000 | 100000 | Wilfrid Nixon | Tim Peters | OPS
154 | R27-148 | Development of Low-Water Crossing Design Guidelines for Very Low ADT Routes in Illinois") | 2015-01-01 | 2016-12-31 | 2016-12-31 | 200000 | 202837 | 26609 | 150000 | 200000 | Prasanta Kalita | Thomas Winkelman / Jayme Schiff | BAF
155 | R27-149-1 | Mechanistic-Empirical (M-E) Design Implementation & Monitoring for Flexible Pavements") | 2014-07-01 | 2017-06-30 | 2018-06-30 | 230689 | 252806 | 3375 | 206897 | 275863 | Marshall Thompson | Charles Wienrank | PVMT
156 | R27-149-2 | Mechanistic-Empirical (M-E) Design Implementation & Monitoring for Rigid Pavements") | 2014-07-01 | 2017-06-30 | 2018-08-31 | 324999 | 432944 | 92195 | 292194 | 389592 | Jeffery Roesler | Charles Wienrank | PVMT
157 | R27-150 | Revised Condition Rating Survey models to Reflect All Distresses") | 2015-01-01 | 2016-12-31 | 2018-02-28 | 200000 | 227930 | 54195 | 154195 | 203343 | Hasan Ozer | Travis Lobmaster / Joe Vespa | PLAN
158 | R27-151 | Investigating the Optimum Performance of Reflective Pavement Markers") | 2014-10-01 | 2018-11-30 | 2019-11-30 | 300000 | 468261 | 52575 | 353105 | 466640 | Carmine Dwyer | Kelly Senger / Kyle Armstrong | OPS
159 | R27-152 | Validation and Revision of Fees Charged for Oversize/Overweight Vehicle Permits ") | 2015-03-01 | 2017-02-28 | 2017-02-28 | 300000 | 246391 | 71869 | 225001 | 300000 | Imad Al-Qadi | Justan Mann | OPS
160 | R27-153 | Best Management Practices and Incentives to Expedite Utility Relocation") | 2014-09-01 | 2017-03-31 | 2017-07-31 | 230000 | 257510 | 71870 | 172500 | 230000 | Khaled El-Rayes | Tim Kell | CON
161 | R27-154 | Effect of Early-Age Concrete Elastic Properties on Fatigue Damage in PCC Pavements Containing Fibers") | 2015-01-01 | 2017-06-30 | 2017-12-15 | 299998 | 388767 | 66484 | 266484 | 355313 | Mohsen Issa | James Krstulovich | PVMT
162 | R27-155 | Improving the Effectiveness of Smart Work Zone Technologies") | 2014-10-15 | 2016-10-14 | 2016-11-30 | 225000 | 241781 | 58246 | 168750 | 225000 | Daniel Work | Paul Lorton | SAF
163 | R27-156 | Repair & Strengthening of Distressed/Damaged Ends of Prestressed Beams with FRP Composites") | 2014-11-01 | 2017-07-31 | 2018-01-31 | 299999 | 337762 | 33694 | 234124 | 312165 | Bassem Andrawes | Victor Veliz | BAF
164 | R27-157 | Plasticity Requirements of the Aggregates as Subbase | 2015-01-01 | 2017-10-31 | 2018-09-30 | 160947 | 221361 | 60788 | 160788 | 210219 | Abdolreza Osouli | Heather Shoup | PVMT
165 | R27-158 | Crack Induction in Cement Stabalized Layers") | 2015-04-23 | 2015-04-23 | 2015-04-23 | 0 | 0 |  | 0 | 0 |  |  | PVMT
166 | R27-159 | Transportation Problems - Sustainability") | 2013-12-09 | 2013-12-09 | 2013-12-09 | 0 | 0 |  | 0 | 0 |  |  | SUS
167 | R27-160 | Sustainability Engineering and Support") | 2013-12-09 | 2016-06-30 | 2017-06-30 | 1000000 | 801388 | 17915 | 750000 | 1000000 | Imad Al-Qadi | Kelly Senger | SUS
168 | R27-161 | Construction and Performance Monitoring of Various Asphalt Mixes") | 2014-10-01 | 2017-09-30 | 2017-12-31 | 674407 | 980732 | 83085 | 729097 | 969729 | Imad Al-Qadi | Jim Trepanier | SUS
169 | R27-162 | Chemical and Compositional Characterization of Recycled Binders") | 2015-01-01 | 2016-03-31 | 2017-01-31 | 144345 | 147923 | 7515 | 108259 | 144345 | B.K. Sharma | Ronald Price | PVMT
170 | R27-163 | Adapting Construction Staking and Inspection to Modern Technology") | 2015-08-16 | 2017-08-15 | 2017-08-15 | 210000 | 249266 | 68090 | 169988 | 226651 | Nora El-Gohary | Tim Kell | CON
171 | R27-164 | Design of Living Barriers to Reduce the Impacts of Snow Drifts on Illinois Freeways") | 2015-11-01 | 2018-04-30 | 2020-12-15 | 300000 | 394210 | 83479 | 283480 | 373806 | Xianming Shi | Rodney Lashuay | OPS
172 | R27-165 | (CANCELLED) Determining Whether a Deck with a Microsilica or Latex Concrete Overlay in Place Can Be Overlaid") | 2016-01-01 | 2016-02-08 | 2016-02-08 | 3524 | 3551 | 643 | 2643 | 3524 | John Popovics | Dave Copenbarger | BAF
173 | R27-166 | Effectiveness of Waterproofing Systems for Bituminous Overlays on Bridge Decks") | 2015-06-29 | 2015-06-29 | 2015-06-29 | 0 | 0 |  | 0 | 0 |  |  | BAF
174 | R27-167 | Establishing Procedures and Guidelines for Pedestrian Treatments at Uncontrolled Locations ") | 2015-08-16 | 2017-02-15 | 2017-08-15 | 175000 | 185542 | 32304 | 132297 | 176109 | Yan Qi | Kyle Armstrong | SAF
175 | R27-168 | Field Performance Evaluations of Sustainable Aggregate By-Product Applications (Phase II)") | 2015-09-01 | 2018-02-28 | 2018-09-30 | 500000 | 720399 | 22403 | 522403 | 696537 | Erol Tutumluer | Jim Trepanier | PVMT
176 | R27-169 | Opportunistic Traffic Sensing Using Existing Video Sources (Phase II) ") | 2015-05-16 | 2016-11-15 | 2018-08-15 | 100000 | 244850 | 77044 | 177838 | 237117 | Jakob Eriksson | William Morgan | PLAN
177 | R27-170 | Pavement Rehabilitation Strategy Course Development") | 2016-01-01 | 2018-12-31 | 2019-03-31 | 449750 | 580149 | 94707 | 398152 | 527045 | Hasan Ozer | Charles Wienrank | PVMT
178 | R27-171 | Refinement of load factors for Illinois-specific LRFR bridge load rating using WIM data") | 2015-12-01 | 2018-05-31 | 2019-02-28 | 300000 | 363173 | 68132 | 268132 | 353343 | Gongkang Fu | Timothy Armbrecht | BAF
179 | R27-172 | Roadway Lighting's Impact on Altering Soybean Growth") | 2016-01-01 | 2016-12-31 | 2018-06-30 | 100000 | 158431 | 19915 | 120140 | 156952 | Ronald Gibbons | Mark Seppelt | ENV
180 | R27-173 | Thermodynamics of HMA Plant Production with ABR Mixes") | 2014-11-01 | 2014-11-01 | 2014-11-01 | 0 | 0 |  | 0 | 0 |  |  | PVMT
181 | R27-174 | Methodology for Evaluation of Seal Coat | 2016-01-01 | 2018-12-31 | 2019-06-30 | 300000 | 350625 | 54187 | 256588 | 337953 | Mohammad Hossain | Tim Peters | PVMT
182 | R27-175 | Development of Long-Term Aging Protocol for Implementation of the Illinois Flexibility Index Test (I-FIT)") | 2017-01-01 | 2018-12-31 | 2019-08-31 | 599968 | 916752 | 674 | 700675 | 880546 | Imad Al-Qadi | Tom Zehr | PVMT
183 | R27-176 | Alternative Noise Barrier Approvals") | 2017-09-01 | 2018-08-31 | 2018-11-30 | 115384 | 96230 | 8788 | 86538 | 115384 | Khaled El-Rayes | Scott Stitt | ENV
184 | R27-177 | Dynamic Travel Time Estimation for Northeast Illinois Expressways") | 2017-09-01 | 2019-03-31 | 2020-06-30 | 173077 | 286552 | 94129 | 194170 | 258892 | Kouros Mohammadian | Kevin Price | PLAN
185 | R27-178-1 | Bridge Decks: Mitigation of Shrinkage Cracking - Phase III") | 2017-09-15 | 2020-09-15 | 2020-12-15 | 195834 | 216456 | 52779 | 153125 | 200000 | Paramita Mondal | James Krstulovich | BAF
186 | R27-178-2 | Bridge Decks: Mitigation of Shrinkage Cracking - Phase III") | 2017-09-15 | 2020-09-15 | 2020-12-15 | 195834 | 232933 | 76080 | 178400 | 233700 | Riyadh Hindi | James Krstulovich | BAF
187 | R27-179 | Effectiveness of Exterior Beam Rotation Prevention Systems for Bridge Deck Construction - Phase II") | 2017-09-15 | 2019-09-15 | 2019-09-15 | 262500 | 216890 | 64175 | 200000 | 262500 | Riyadh Hindi | Douglas Dirks / Mark Thomson | CON
188 | R27-180 | Concrete Pavement Mixtures with High Supplementary Cementitious Materials (SCM) Content") | 2017-10-01 | 2021-06-30 | 2021-09-30 | 403846 | 773177 | 65622 | 565626 | 750000 | Jeffery Roesler | James Krstulovich | PVMT
189 | R27-181 | Updated and Unified StreamStats Peak Discharges for Streams of Illinois") | 2017-10-01 | 2020-06-30 | 2023-12-31 | 426300 | 598450 | 2880 | 402880 | 596300 | Thomas Over | Neil VanBebber | BAF
190 | R27-182 | Size and Shape Determination of the Rip Rap and Large Sized Aggregates Using Field Imaging") | 2018-01-01 | 2019-12-31 | 2020-06-30 | 392716 | 428332 | 94454 | 294537 | 392716 | Erol Tutumluer | Andrew Stolba | PVMT
191 | R27-183-HS | Evaluation of On-Site and In-situ Treatment Alternatives for Contaminated Soils") | 2018-02-01 | 2021-01-31 | 2021-06-30 | 512500 | 550665 | 14336 | 461826 | 611898 | Amanda Hohner | Douglas Dirks / James Curtis | ENV
192 | R27-184 | Evaluating the Beneficial Effects of Winter Maintenance Best Practices on Water Quality") | 2017-10-31 | 2017-10-31 | 2017-10-31 | 0 | 0 |  | 0 | 0 |  |  | OPS
193 | R27-185 | Evaluation of the HMA Resurfacing Policy for State Maintained Highways Other than Interstates") | 2017-11-17 | 2017-11-17 | 2017-11-17 | 0 | 0 |  | 0 | 0 |  |  | PVMT
194 | R27-186 | Correlation Between Work Zone Exposure and Work Zone-Related Fatal and A-Injury Crashes") | 2018-02-01 | 2020-01-31 | 2020-01-31 | 262500 | 263956 | 98384 | 198479 | 262500 | Kerrie Schattler | Juan Pava | SAF
195 | R27-187 | Pavement Surface Treatments for Ice-Prone Locations in the Illinois Highway System") | 2018-02-01 | 2020-01-31 | 2018-12-31 | 260668 | 60511 | 6523 | 159168 | 209845 | Xianming Shi | Frank Sharpe | SAF
196 | R27-188 | Evaluating the Accuracy and Use of Drilled Shaft Integrity Testing Methods in Illinois") | 2018-02-01 | 2020-07-31 | 2022-11-30 | 448027 | 493820 | 31433 | 405289 | 537551 | Timothy Stark | Michael Short | BAF
197 | R27-189 | Evaluation of Data Trends and Variability in the Quality for Performance (QCP) and Pay for Performance (PFP) Programs") | 2018-01-01 | 2019-12-31 | 2020-06-30 | 521297 | 606971 | 57797 | 457917 | 572397 | Imad Al-Qadi | Jim Trepanier | PVMT
198 | R27-190 | Evaluation of Various Products for Perimeter Barrier") | 2018-05-16 | 2020-11-15 | 2021-05-15 | 299997 | 290219 | 99075 | 224998 | 299997 | Rabin Bhattarai | Michael Brownlee | ENV
199 | R27-191 | Evaluating the Costs & Benefits of Snow Fences in Illinois") | 2018-08-16 | 2020-02-15 | 2021-02-15 | 187500 | 189649 | 43749 | 143750 | 187500 | Yan Qi | Mark Bloome / Laura Shanley | OPS
200 | R27-192 | Maritime Freight Data Collection System & Database to Support Performance Measures & Market Analyses") | 2018-05-16 | 2020-05-15 | 2020-12-15 | 375000 | 434138 | 81249 | 281250 | 375000 | P.S. Sriraj | B J Murray / Clayton Stambaugh | PLAN
201 | R27-193-1 | Flexible Pavement Recycling Techniques") | 2018-07-16 | 2021-07-15 | 2021-07-15 | 125220 | 110656 | 9060 | 100176 | 125220 | Marshall Thompson | Charles Wienrank | PVMT
202 | R27-193-2 | Flexible Pavement Design (Full-Depth and Rubblization)") | 2018-07-16 | 2021-07-15 | 2021-07-15 | 125220 | 98628 | 3280 | 100176 | 125220 | Marshall Thompson | Charles Wienrank | PVMT
203 | R27-193-3 | Evaluation of Geosynthetics Use in Pavement Foundation Layers & Their Effects on Design Methods") | 2018-08-16 | 2021-08-15 | 2021-08-15 | 198520 | 216345 | 38964 | 138964 | 198520 | Erol Tutumluer | Heather Shoup / Veniecy Pearman-Green | PVMT
204 | R27-193-4 | Premature Cracking Mechanisms for Jointed Plain Concrete Pavement (JPCP)") | 2018-08-16 | 2020-02-15 | 2021-01-15 | 152047 | 159109 | 6433 | 106433 | 152047 | Jeffery Roesler | Charles Wienrank | PVMT
205 | R27-193-5 | Review of Improved Subgrade and Stabilized Subbases to Evaluate Performance of Concrete") | 2019-06-16 | 2021-06-15 | 2021-06-15 | 74497 | 81636 | 4325 | 55873 | 74497 | Erol Tutumluer | Heather Shoup | PVMT
206 | R27-193-6 | Performance Evaluation of Stabilized Support Layers for Concrete Pavements") | 2019-10-16 | 2021-03-31 | 2022-02-28 | 74497 | 98071 | 6988 | 66992 | 89322 | Jeffery Roesler | Charles Wienrank | PVMT
207 | R27-194 | Evaluation of Spatial and Temporal Load Distribution in Steel Bridge Superstructures") | 2018-07-01 | 2022-06-30 | 2026-06-30 | 600000 | 1446528 | 65104 | 928948 | 1238597 | Larry Fahnestock | Mark Shaffer | BAF
208 | R27-195 | Best Practice Operation of Reversible Express Lanes for Kennedy Expressway") | 2018-10-16 | 2020-05-15 | 2021-10-31 | 220000 | 356891 | 94715 | 195581 | 260777 | Kouros Mohammadian | Matthew Daeda | OPS
209 | R27-196-HS | Rheology-Chemical Based Procedure to Evaluate Additives/Modifiers used in Asphalt Binders for Performance Enhancements (Phase 2)") | 2018-07-01 | 2020-12-31 | 2021-06-30 | 350000 | 394070 | 82702 | 311905 | 415873 | B.K. Sharma | Kelly Senger | PVMT
210 | R27-197 | Characterization of the Bond Strength of Textured Epoxy-Coated (TEC) Reinforcement Bars (Phase 2)") | 2018-07-16 | 2021-01-15 | 2022-01-15 | 300000 | 367709 | 68417 | 268417 | 357889 | Bassem Andrawes | Jayme Schiff / Dan Tobias | BAF
211 | R27-198 | Development of Guidelines for Implementation of Horizontal Directional Drilling") | 2018-07-16 | 2021-07-15 | 2021-09-15 | 400000 | 406550 | 0 | 300000 | 400000 | Youssef Hashash | Heather Shoup / Joseph Angeli | BAF
212 | R27-199 | Optimizing the Benefits of Smoother Roads against the Increased Costs to Build Them") | 2018-08-16 | 2020-01-15 | 2020-10-15 | 237500 | 239650 | 81250 | 181250 | 237500 | Hyung Lee | John Senger / Douglas Dirks | CON
213 | R27-200 | Construction of Pedestrian Infrastructure Along Transit Corridors") | 2018-08-16 | 2020-08-15 | 2021-03-15 | 248915 | 259497 | 84338 | 186686 | 248915 | Lindsay Braun | Charles Abraham | MFM
214 | R27-201 | Motor Vehicle Crashes Among Older Population") | 2018-08-16 | 2020-08-15 | 2020-10-15 | 112500 | 110206 | 3056 | 87500 | 112500 | Yan Qi | Cynthia Watters | SAF
215 | R27-202 | Roadway Lighting's Effect on Pedestrian Safety at Intersection and Midblock Crosswalks") | 2018-09-16 | 2021-03-15 | 2021-09-15 | 384905 | 408370 | 7413 | 307687 | 406080 | Rajaram Bhagavathula | Bernard Griffin / Marshall Metcalf | SAF
216 | R27-203 | Truck Platooning on Illinois Flexible Pavements") | 2019-06-01 | 2021-05-31 | 2021-05-31 | 380000 | 381964 | 4000 | 304000 | 380000 | Imad Al-Qadi | Brian Hill / Charles Wienrank | PVMT
217 | R27-204 | Optimized Hot-mix Asphalt (HMA) Lift Configuration for Performance") | 2019-08-16 | 2022-02-15 | 2023-05-31 | 550000 | 778862 | 11700 | 612048 | 767787 | Imad Al-Qadi | John Senger / Laura Heckel | PVMT
218 | R27-205 | Development of Bridge Load Testing Program for Load Rating of Concrete Bridges") | 2019-07-16 | 2022-07-15 | 2024-12-15 | 450000 | 661083 | 55704 | 555906 | 741208 | Bassem Andrawes | Ruben Boehler | BAF
219 | R27-206 | Evaluation of Roadway High Mast Tower Lighting") | 2019-08-16 | 2022-08-15 | 2023-10-31 | 362500 | 474245 | 38578 | 338950 | 447766 | Ronald Gibbons | Marshall Metcalf / Kyle Armstrong | SAF
220 | R27-207 | Technical and Financial Feasibility Study for Installation of Solar Panels at IDOT Owned Facilities") | 2019-08-16 | 2021-08-15 | 2021-08-15 | 347500 | 354382 | 63748 | 263750 | 347500 | Brian Deal | Christopher Schmidt | PLAN
221 | R27-208 | Measuring Transport Properties of Portland Cement Concrete Using Electrical Resistivity") | 2019-08-16 | 2021-08-15 | 2023-08-15 | 322443 | 355702 | 44957 | 244957 | 318276 | Julie Hartell | James Krstulovich | PVMT
222 | R27-209 | Report Tracking of Public Maintenance Needs/Requests") | 2019-05-16 | 2019-05-16 | 2019-05-16 | 0 | 0 |  | 0 | 0 |  |  | OPS
223 | R27-210 | Cone Penetration Testing (CPT) for Illinois Subsurface Characterization and Geotechnical Design") | 2019-08-16 | 2022-08-15 | 2024-05-31 | 512500 | 518944 | 87500 | 387500 | 512500 | Jorge Macedo | Brian Laningham / Brad Hessing | BAF
224 | R27-211 | Policy and Design Guidelines to Plan for Connected and Autonomous Vehicles (CAVs)") | 2019-08-16 | 2022-02-15 | 2022-08-15 | 180000 | 212076 | 61348 | 161815 | 215753 | Arnab Chakraborty | Shawn Wilcockson | PLAN
225 | R27-212 | Beneficial Use of Dredged Material from the Illinois Marine Transportation System") | 2019-09-01 | 2021-08-31 | 2022-11-30 | 150000 | 68473 | 3576 | 134999 | 179998 | Timothy Stark | B J Murray / Heather Shoup | PLAN
226 | R27-213 | Reducing Concrete Cure Times Based on a Quantitative Assessment of Resistivity and Porosity") | 2020-08-16 | 2022-08-15 | 2023-09-30 | 200000 | 239521 | 78335 | 178392 | 237856 | Nishant Garg | Douglas Dirks | CON
227 | R27-214 | 3D Image Analysis Using Deep Learning for Size and Shape Characterization of Stockpile Riprap Aggregates - Phase 2") | 2020-07-01 | 2022-06-30 | 2023-06-30 | 390000 | 364578 | 86231 | 292500 | 390000 | Erol Tutumluer | Andrew Stolba | PVMT
228 | R27-215 | Analyzing the Impacts of a Successful Diffusion of Shared E-Scooter and Other Micromobility Devices and Efficient Management Strategies for Successful Operations in Illinois") | 2020-05-16 | 2022-05-15 | 2022-05-15 | 200000 | 210769 | 49995 | 150000 | 200000 | Kouros Mohammadian | Charles Abraham | MFM
229 | R27-216 | Optimizing the Use of Local Aggregates in Stone-matrix Asphalt (SMA)") | 2020-08-16 | 2023-08-15 | 2026-04-30 | 700000 | 1221299 | 34593 | 996290 | 1245362 | Imad Al-Qadi | Brian Hill | PVMT
230 | R27-217 | Taxation of Ridesharing") | 2020-08-16 | 2021-08-15 | 2021-12-15 | 160000 | 142085 | 6808 | 120000 | 160000 | Lewis Lehe | Charles Abraham | MFM
231 | R27-218 | Railroad-Highway Crossing (RHC) Safety Improvement Evaluation and Prioritization Tool") | 2020-05-16 | 2023-05-15 | 2023-06-30 | 385000 | 393321 | 88750 | 288750 | 385000 | P.S. Sriraj | Bill Pearsall | SAF
232 | R27-219 | Influence of Field-Curing Conditions on Strength of Concrete Test Specimens") | 2020-08-16 | 2022-08-15 | 2023-11-15 | 262497 | 265394 | 99998 | 199998 | 262497 | Pranshoo Solanki | Douglas Dirks / James Krstulovich | CON
233 | R27-220 | Developing Scour-Depth Estimation Using the In Situ and Portable Scour Testing Devices (ISTD and PSTD) for Illinois Cohesive Soils") | 2020-10-01 | 2023-09-30 | 2026-10-31 | 462500 | 827578 | 4655 | 728633 | 963765 | Abdolreza Osouli | Heather Shoup / Neil VanBebber | BAF
234 | R27-221 | Chip-Seal Quality Assurance Using Percent Embedment") | 2020-08-16 | 2023-02-15 | 2023-12-31 | 312500 | 447586 | 37202 | 337202 | 445436 | Ahmad Alhasan | John Senger | PVMT
235 | R27-222 | Evaluating IDOT's Community Impact Assessment Manual to Determine Socioeconomic Impacts of Projects") | 2020-08-16 | 2022-02-15 | 2022-08-15 | 209128 | 198318 | 60692 | 161334 | 209128 | Lindsay Braun | John Sherrill / Michael Vanderhoof | ENV
236 | R27-223 | Crash Modification Factors (CMFs) for Contrast Pavement Markings on Light-Colored Pavement") | 2020-08-16 | 2022-08-15 | 2022-08-15 | 91986 | 66362 | 7826 | 62005 | 91986 | Michael Williamson | Marshall Metcalf | OPS
237 | R27-224 | Developing an Effective Crack-Sealing Procedure by Leveraging Chemistry and Computer Vision") | 2020-08-16 | 2023-08-15 | 2022-06-30 | 399998 | 267650 | 18345 | 234932 | 313242 | Nishant Garg | Kelly Senger / Mark Shaffer | PVMT
238 | R27-225 | Strength and Serviceability of Damaged Steel Girders") | 2020-10-01 | 2023-09-30 | 2026-06-30 | 500000 | 683244 | 81157 | 698298 | 931064 | Larry Fahnestock | Spencer Koehler | BAF
239 | R27-226 | Residual Capacity of Precast Prestressed Concrete (PPC) Deck Beams with Transverse Cracks") | 2020-08-16 | 2023-08-15 | 2025-05-15 | 300000 | 350619 | 63711 | 269778 | 359704 | Bassem Andrawes | Robert Perkins | BAF
240 | R27-227 | Moisture Content and In-Place Density of Cold Recycle Treatments") | 2020-05-16 | 2022-05-15 | 2022-05-15 | 295000 | 286389 | 35428 | 236000 | 295000 | Imad Al-Qadi | John Senger | PVMT
241 | R27-228 | Illinois | 2021-04-16 | 2022-10-15 | 2023-06-15 | 399745 | 400352 | 86547 | 306059 | 399745 | Angeli Jayme | Michael Vanderhoof | PLAN
242 | R27-229 | Evaluation of Net-free Erosion Control Blankets") | 2021-05-16 | 2023-11-15 | 2023-12-15 | 240000 | 224098 | 61928 | 180000 | 240000 | Rabin Bhattarai | Scott Marlow | ENV
243 | R27-230 | Performance and Design of Continuously Reinforced Concrete Pavements (CRCP) ") | 2021-05-16 | 2023-05-15 | 2024-05-31 | 285000 | 309387 | 13276 | 213750 | 285000 | Jeffery Roesler | Charles Wienrank | PVMT
244 | R27-231 | Evaluation of the Asphalt Mixture Design Framework for Airfield Pavements in Illinois") | 2021-08-16 | 2023-08-15 | 2023-08-15 | 368000 | 327724 | 61064 | 294400 | 368000 | Uthman Mohamed Ali | Bill Eves | PVMT
245 | R27-232 | Utilizing a Particle Packing Approach for an Illinois-specific | 2021-07-01 | 2024-06-30 | 2024-09-30 | 309375 | 337342 | 49355 | 249355 | 329680 | Nishant Garg | James Krstulovich / Mark Shaffer | BAF
246 | R27-233 | Mechanistic - Empirical Design Procedures for Flexible Pavements") | 2021-05-16 | 2024-05-15 | 2024-05-15 | 350000 | 366737 | 62500 | 262500 | 350000 | Ramez Hajj | Charles Wienrank / Brian Hill | PVMT
247 | R27-234 | Effectiveness of Geosynthetics in Soil/Aggregate Stabilization - Evaluation using Bender Element Sensor Technology") | 2021-10-01 | 2024-03-31 | 2025-06-30 | 342000 | 451093 | 27096 | 327097 | 436130 | Erol Tutumluer | Heather Shoup / Andrew Stolba | PVMT
248 | R27-235 | Thickness Design for Cement-Treated Base Pavements") | 2021-07-01 | 2024-06-30 | 2024-06-30 | 120000 | 103475 | 5759 | 96000 | 120000 | Marshall Thompson | James Krstulovich / Tim Peters | PVMT
249 | R27-236 | Electric Vehicle Infrastructure Plan in Illinois") | 2021-07-01 | 2022-12-31 | 2022-12-31 | 238415 | 142008 | 6663 | 178812 | 238415 | Ria Kontou | Christopher Schmidt | PLAN
250 | R27-237 | 48-Volt Cabinets") | 2021-07-09 | 2021-07-09 | 2021-07-09 | 0 | 0 |  | 0 | 0 |  |  | OPS
251 | R27-238 | Developing Deterioration Curves for Bridge Elements") | 2021-08-01 | 2022-10-31 | 2024-02-29 | 212497 | 214553 | 62409 | 162498 | 212497 | Gongkang Fu | William Beisner | BAF
252 | R27-239 | Development of Commercial Vehicle Emission Inventory and Analysis") | 2021-08-16 | 2023-08-15 | 2024-02-15 | 500000 | 487110 | 74994 | 375000 | 500000 | Jane Lin | Christopher Schmidt | PLAN
253 | R27-240 | Development of Potential Strategies for Unmarked and Low Traffic Volume Roadways in Illinois") | 2021-09-01 | 2023-08-31 | 2023-08-31 | 261610 | 266026 | 99332 | 199332 | 261610 | Arudi Rajagopal | Laura Shanley / Tim Peters | OPS
254 | R27-241 | Advancing Air Mobility in Illinois") | 2021-09-01 | 2023-08-31 | 2024-02-29 | 462500 | 467510 | 50000 | 350000 | 462500 | Hani Mahmassani | William Viste | PLAN
255 | R27-242 | Economical Impact of Full Closure for Accelerated Bridge Construction and Conventional Staged Construction") | 2021-08-16 | 2023-08-15 | 2023-08-15 | 149982 | 154334 | 11551 | 112487 | 149982 | Khaled El-Rayes | Patrik Claussen | BAF
256 | R27-243 | Pavement Friction") | 2021-10-06 | 2021-10-06 | 2021-10-06 | 0 | 0 |  | 0 | 0 |  |  | PVMT
257 | R27-244 | Improved Geotechnical Site Characterization Using Measurement While Drilling") | 2021-08-16 | 2024-08-15 | 2027-03-31 | 562500 | 574167 | 19544 | 499769 | 662192 | Ann Christine Sychterz | Brad Hessing / Scott Kassel | BAF
258 | R27-245-HS | Quantification of the Effectiveness and External Noise of Rumble Strip Designs") | 2021-11-01 | 2023-10-31 | 2024-11-30 | 200000 | 695990 | 26591 | 529982 | 662478 | Khaled El-Rayes | Benjamin Sperry | SAF
259 | R27-246 | Development of Design Guidance for Smart Work Zone Systems") | 2022-01-01 | 2023-06-30 | 2024-01-31 | 219912 | 215127 | 64736 | 164934 | 219912 | Khaled El-Rayes | Juan Pava | SAF
260 | R27-247 | Automated and Contactless Identification of Asphalt Pavement Surface Friction Based on Computer Vision Image-based 3D Reconstruction and Machine Learning Techniques") | 2022-07-01 | 2026-06-30 | 2026-09-30 | 750000 | 559790 | 15583 | 600000 | 750000 | Imad Al-Qadi | John Senger | PVMT
261 | R27-248 | Investigation of Dolomite Aggregate Long-Term Cementation and Its Potential Advantage for Building Roads") | 2022-07-01 | 2024-12-31 | 2025-12-31 | 390000 | 631770 | 29001 | 484481 | 645974 | Erol Tutumluer | Andrew Stolba | PVMT
262 | R27-249 | Evaluating the Benefits of Implementing Mobile Road Weather Information Sensors (Phase II)") | 2022-07-01 | 2025-06-30 | 2026-06-30 | 630330 | 642060 | 88723 | 627439 | 836585 | Khaled El-Rayes | Keith Donovan | OPS
263 | R27-250 | Using Advanced Binder Rheological Parameters to Predict Cracking Potential of Hot-Mix Asphalt Mixtures with Modified Binders") | 2022-08-16 | 2025-02-15 | 2025-10-31 | 540443 | 575818 | 32465 | 432354 | 540443 | Imad Al-Qadi | Kelly Senger / Brian Hill | PVMT
264 | R27-251 | Optimum Traffic Signal Condition Assessment and Strategic Maintenance Planning") | 2022-08-16 | 2024-08-15 | 2024-08-15 | 187500 | 173506 | 22904 | 154493 | 198243 | Ryan Fries | Kenneth Davis / Kyle Armstrong | OPS
265 | R27-252 | Impact of Commercial Electric Vehicles on Flexible Pavement Performance") | 2022-08-16 | 2025-02-15 | 2025-05-15 | 412500 | 461132 | 35839 | 332051 | 418052 | Angeli Jayme | John Senger | PVMT
266 | R27-253 | Bicycle Detection") | 2022-09-14 | 2022-09-14 | 2022-09-14 | 0 | 0 |  | 0 | 0 |  |  | MFM
267 | R27-254 | Development of Equipment Rental Schedule for Illinois") | 2022-08-16 | 2024-08-15 | 2026-01-15 | 273243 | 189444 | 15513 | 210742 | 273243 | Zheyong Bian | Douglas Dirks / Tim Peters | CON
268 | R27-255 | Illinois Department of Transportation's Seeding Standards and Best Management Practices") | 2022-08-16 | 2025-05-15 | 2025-06-15 | 269953 | 252137 | 70695 | 202465 | 269953 | Jeffrey Matthews | Scott Hall | ENV
269 | R27-256 | Work Zone Queue Analysis Training Classes") | 2022-04-16 | 2023-04-15 | 2023-11-30 | 52940 | 36741 | 8372 | 39705 | 52940 | Ray Benekohal | Juan Pava | SAF
270 | R27-257 | Seismic Damping Effects on Bridges") | 2024-01-01 | 2025-12-31 | 2026-10-31 | 281586 | 80371 | 5433 | 211189 | 281586 | James LaFave | Mark Shaffer | BAF
271 | R27-258 | Evaluation of Digital Alert Systems Associated to Emergency Response Vehicles and Compliance with Move Over Law") | 2023-03-01 | 2026-02-28 | 2026-02-28 | 250000 | 421229 | 28557 | 333258 | 444344 | Alireza Talebpour | Juan Pava | SAF
272 | R27-259 | State Department of Transportation Support for Operationalizing Transit Signal Priority ") | 2023-07-01 | 2025-06-30 | 2025-06-30 | 310744 | 351226 | 41332 | 246486 | 321487 | Kouros Mohammadian | Charles Abraham / Taqhi Mohammed | MFM
273 | R27-260 | Characterization of the Long-term Behavior of Textured Epoxy Coated Rebars in Bridge Decks") | 2023-08-16 | 2026-12-15 | 2026-12-15 | 750000 | 673188 | 20158 | 820005 | 1093340 | Bassem Andrawes | Mark Shaffer | BAF
274 | R27-261 | Urban Mobility") | 2022-12-13 | 2022-12-13 | 2022-12-13 | 0 | 0 |  | 0 | 0 |  |  | MFM
275 | R27-262 | Developing a Framework for Establishing a Risk-Based Geotechnical Asset Management Program in Illinois") | 2023-08-16 | 2026-08-15 | 2026-08-15 | 510743 | 364484 | 72872 | 396486 | 521486 | Mike Prohaska | Heather Shoup / Laura Heckel | PVMT
276 | R27-263 | Advancements in Profiler Certification") | 2024-08-01 | 2026-07-31 | 2026-07-31 | 371238 | 581406 | 46378 | 289172 | 381981 | Steve Karamihas | John Senger | PVMT
277 | R27-264 | Development of a Pavement Friction Management Program") | 2023-09-01 | 2026-02-28 | 2026-05-31 | 360745 | 285737 | 97541 | 273245 | 360745 | Yanfeng Ouyang | John Senger | PVMT
278 | R27-265 | Experimental and Numerical Investigation of Integral Abutment Bridges: Single and Group Pile Behavior") | 2024-01-01 | 2026-12-31 | 2026-12-31 | 541546 | 254826 | 16743 | 406159 | 540254 | Mohsen Issa | Mark Shaffer / Yazan Alshawabkeh | BAF
279 | R27-266 | Pavement Electromagnetic Energy Harvesting System from Highway-Speed Vehicles") | 2024-05-16 | 2026-05-15 | 2026-12-15 | 479724 | 353083 | 64819 | 460180 | 575225 | Imad Al-Qadi | John Senger | PVMT
280 | R27-267 | Illinois Flexible Pavement Design and Monitoring") | 2024-07-01 | 2027-06-30 | 2027-06-30 | 400000 | 188119 | 45441 | 300000 | 400000 | Ramez Hajj | Charles Wienrank / Brian Hill | PVMT
281 | R27-268 | Quarry By-product Fines for Otta Seal Surfacing of Local Roads") | 2024-08-16 | 2026-08-15 | 2026-08-15 | 367000 | 173645 | 18589 | 275250 | 367000 | Erol Tutumluer | John Senger / Andrew Stolba | PVMT
282 | R27-269 | Estimation of the Load Rating of Existing Highway Bridges Based on Bridge Weigh-in-Motion Data") | 2024-08-16 | 2027-08-15 | 2027-08-15 | 500000 | 85092 | 43 | 375000 | 500000 | Mohamad Alipour | Mark Shaffer | BAF
283 | R27-270 | Field Assessment of Traffic Control Devices") | 2024-08-16 | 2026-08-15 | 2026-12-31 | 299817 | 56938 | 7462 | 224863 | 299817 | Khaled El-Rayes | Douglas Dirks | CON
284 | R27-271 | Development of a Project-Scale Air Quality Screening Tool") | 2024-08-16 | 2027-02-15 | 2027-02-15 | 300000 | 117747 | 7996 | 225000 | 300000 | Jane Lin | Benjamin Sperry | ENV
285 | R27-272 | Identifying and Minimizing Illinois’ Transit Deserts and Gray Areas") | 2024-08-16 | 2027-08-15 | 2027-08-15 | 299771 | 148254 | 7358 | 224828 | 299771 | Bumsoo Lee | Hannah Schmidt / Charles Abraham | MFM
286 | R27-273 | ITAG (Illinois TrAnsit GHG): a User-Friendly Tool to Estimate and Compare Greenhouse Gas Emissions from Transit Operations in Illinois") | 2024-08-16 | 2027-08-15 | 2027-08-15 | 300000 | 114127 | 9094 | 225000 | 300000 | Sybil Derrible | Christopher Schmidt | PLAN
287 | R27-274 | Mobility and Funding Assessment for the Expansion of Free and Reduced Fares") | 2024-08-16 | 2026-05-15 | 2026-12-31 | 400000 | 149204 | 9373 | 300000 | 400000 | Kouros Mohammadian | Hannah Schmidt | PLAN
288 | R27-275 | Seismic Ground Motions for IDOT Geotechnical Assets") | 2025-08-16 | 2028-08-15 | 2028-08-15 | 799999 | 21095 | 5460 | 599999 | 799999 | Youssef Hashash | Heather Shoup / Mark Shaffer | BAF
289 | R27-276 | Investigation of Alternative Solvents for Asphalt Extraction and Recovery") | 2024-10-01 | 2026-09-30 | 2026-09-30 | 481011 | 139089 | 4691 | 394957 | 481011 | Ramez Hajj | Kelly Senger | PVMT
290 | R27-277 | Update of Traffic Factor Equations for IDOT Mechanistic-Empirical Pavement Design") | 2025-01-01 | 2027-06-30 | 2027-06-30 | 488510 | 88319 | 5197 | 390808 | 488510 | Imad Al-Qadi | Charles Wienrank | PVMT
291 | R27-278 | Requirements of Aggregate Materials as Subbase | 2025-08-16 | 2028-08-15 | 2028-08-15 | 970846 | 0 |  | 733506 | 970846 | Erol Tutumluer | Andrew Stolba / Heather Shoup | PVMT
292 | R27-279 | Advancing Self-explaining streets Phase 2: Evaluating the use of Roadway design elements and target speeds to reduce operating speed ") | 2025-07-01 | 2027-06-30 | 2027-06-30 | 300000 | 36510 | 6644 | 225000 | 300000 | Alireza Talebpour | Stephane Seck-Birhame / Victoria Barrett | SAF
293 | R27-280 | Economic | 2025-07-01 | 2028-06-30 | 2028-06-30 | 280000 | 32554 | 3138 | 210000 | 280000 | Ria Kontou | Jason Lange | PLAN
294 | R27-281 | IL-Pave: Development of an Integrated Tool to Optimize Pavement Energy and Cost") | 2025-08-16 | 2028-08-15 | 2028-08-15 | 960000 | 104500 | 5242 | 768000 | 960000 | Imad Al-Qadi | John Senger | PVMT
295 | R27-282 | Effectiveness of Wearable Safety Lights for Nighttime Workers ") | 2025-08-16 | 2027-08-15 | 2027-08-15 | 196485 | 0 |  | 152735 | 196485 | Ronald Gibbons | Greg Gurski / Keith Donovan | SAF
296 | R27-283 | Turn-on-Red Prohibitions for Dual Right-Turn Lanes") | 2025-08-16 | 2027-02-15 | 2027-02-15 | 171485 | 33213 | 9130 | 133985 | 171485 | Christopher Day | Meiwu An | OPS
297 | R27-284 | Utilizing Performance Measures for Metropolitan Planning Organizations") | 2025-08-16 | 2027-08-15 | 2027-08-15 | 421487 | 23433 | 7455 | 321486 | 421487 | Yazan Abukhalil | Bob Innis | PLAN
298 | R27-285 | Replacing the Illinois Traffic Projection Tool") | 2025-08-16 | 2027-08-15 | 2027-08-15 | 421485 | 51239 | 6189 | 321485 | 421485 | L.D. White | Mike Miller / William Morgan | PLAN
299 | R27-286 | Laws | 2025-08-16 | 2027-02-15 | 2027-02-15 | 199917 | 839 | 56 | 149938 | 199917 | Timothy Stark | John Senger | SAF
300 | R27-287 | Facilitating Further Scalability and Field Implementation of Illinois-Specific Nonproprietary UHPC Mixes") | 2025-08-16 | 2028-08-15 | 2028-08-15 | 521484 | 16281 | 722 | 396484 | 521484 | Nishant Garg | Mark Shaffer | BAF
301 | R27-288 | Modernization and Web-Based Implementation of the Illinois Pavement Feedback System") | 2026-03-01 | 2028-02-29 | 2028-02-29 | 653944 | 0 |  | 523155 | 653944 | Hong Lang | John Senger | PVMT
302 | R27-289 | Effects of Target Air Voids on Hot Mix Asphalt (HMA) Performance Tests") | 2026-05-01 | 2029-04-30 | 2029-04-30 | 965317 | 0 |  | 772254 | 965317 | Imad Al-Qadi | Brian Hill | PVMT
303 | R27-ALS | Accelerated Transportation Loading Assembly Repairs and Upgrades Project") | 2020-08-01 | 2022-01-31 | 2024-08-31 | 500000 | 883382 | 61429 | 761429 | 951786 | Imad Al-Qadi | John Senger | Other / Department Wide
304 | R27-ET2 (FY18-24 IGA) | Editorial Support and Technology Transfer (FY18-24 IGA)") | 2017-07-01 | 2020-06-30 | 2024-06-30 | 480000 | 689358 | 45910 | 1135000 | 1135000 | Kristi Anderson | John Senger | Other / Department Wide
305 | R27-ET2 (FY25-30 IGA) | R27-ET2 (FY25-30 IGA) Editorial Support and Technology Transfer (FY25-30 IGA)") | 2024-07-01 | 2030-06-30 | 2030-06-30 | 1095000 | 211103 | 90299 | 1095000 | 1095000 | Kristi Anderson | John Senger | Other / Department Wide
306 | R27-PC (FY18-24 IGA) | RD&T Activity Management – Project Coordination (FY18-24 IGA)") | 2017-07-01 | 2020-06-30 | 2024-06-30 | 840000 | 1617512 | 519397 | 2321525 | 2321525 | Kristi Anderson | John Senger | Other / Department Wide
307 | R27-PC (FY25-30 IGA) | R27-PC (FY25-30 IGA) RD&T Activity Management – Project Coordination (FY25-30 IGA)") | 2024-07-01 | 2030-06-30 | 2030-06-30 | 2600000 | 440913 | 97461 | 2600000 | 2600000 | Kristi Anderson | John Senger | Other / Department Wide
308 | R27-RDI (FY18-24 IGA) | Research Dissemination and Implementation (FY18-24 IGA)") | 2017-07-01 | 2020-06-30 | 2024-06-30 | 312000 | 296690 | 76407 | 772000 | 772000 | Kristi Anderson | John Senger | Other / Department Wide
309 | R27-RDI (FY25-30 IGA) | Research Dissemination and Implementation (FY25-30 IGA)") | 2024-07-01 | 2030-06-30 | 2030-06-30 | 660000 | 148289 | 33675 | 660000 | 660000 | Kristi Anderson | John Senger | Other / Department Wide
310 | R27-SP# (FY06-08 IGA) | R27-SP# (FY06-08 IGA)") | 2005-07-01 | 2008-06-30 | 2008-06-30 | 225000 | 0 |  | 168750 | 225000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide
311 | R27-SP# (FY09-11 IGA) | R27-SP# (FY09-11 IGA)") | 2008-07-01 | 2011-06-30 | 2011-06-30 | 450000 | 0 |  | 337500 | 450000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide
312 | R27-SP01 | Median Cable Scanning Tour (Special Project)") | 2005-08-22 | 2006-01-31 | 2006-01-31 | 9969 | 10612 | 477 | 7477 | 9969 | Ray Benekohal | David Lippert | SAF
313 | R27-SP02 | Chicago Bridge Columns (Special Project)") | 2006-01-01 | 2008-06-30 | 2008-06-30 | 24673 | 26265 | 8506 | 18506 | 24673 | Imad Al-Qadi | David Lippert | BAF
314 | R27-SP03 | Profile Equipment Verification FY06 (Special Project)") | 2006-04-17 | 2006-06-30 | 2006-06-30 | 5567 | 5911 | 165 | 4175 | 5567 | Imad Al-Qadi | David Lippert | PVMT
315 | R27-SP04 | Highway Maintenance Manpower Needs Study (Special Project)") | 2007-01-01 | 2007-06-30 | 2007-06-30 | 45515 | 48450 | 4135 | 34136 | 45515 | Yanfeng Ouyang | Joseph Hill | OPS
316 | R27-SP05 | Profile Equipment Verification FY07 (Special Project)") | 2007-04-01 | 2007-06-30 | 2007-06-30 | 13231 | 8976 | 324 | 9923 | 13231 | Imad Al-Qadi | David Lippert | PVMT
317 | R27-SP06 | 2008 RILEM Conference on Cracking in Pavement (Special Project)") | 2006-07-01 | 2008-06-30 | 2008-06-30 | 20000 | 21290 | 5000 | 15000 | 20000 | Imad Al-Qadi | David Lippert | PVMT
318 | R27-SP07 | Non-Destructive Evaluation of Reinforced Concrete Structures (Special Project)") | 2007-09-12 | 2008-06-30 | 2008-06-30 | 27333 | 28932 | 384 | 20500 | 27333 | Imad Al-Qadi | David Lippert | PVMT
319 | R27-SP08 | Wireless Internet Service on Trains (Special Project)") | 2007-10-01 | 2007-12-31 | 2007-12-31 | 63115 | 66259 | 6683 | 47336 | 63115 | R. Sreenivas | Mark Kinkaid | MFM
320 | R27-SP09 | Profile Equipment Verification (Special Project)") | 2008-02-16 | 2008-06-30 | 2008-06-30 | 21664 | 20344 | 4334 | 16248 | 21664 | Imad Al-Qadi | David Lippert | PVMT
321 | R27-SP10 | Online Training Course Prototype (Special Project)") | 2008-04-15 | 2008-06-30 | 2008-06-30 | 32167 | 29383 | 702 | 24125 | 32167 | James Hall | Kevin Burke | OPS
322 | R27-SP11 | Analysis of I-57 Recycled CRCP Cores (Special Project)") | 2008-07-01 | 2008-09-30 | 2008-09-30 | 13333 | 13567 | 0 | 10000 | 13333 | Jeffery Roesler | Mark Gawedzinski | PVMT
323 | R27-SP12 | DeKalb County Bridge Collapse Investigation (Special Project)") | 2008-09-10 | 2008-12-31 | 2009-05-15 | 20280 | 19481 | 3004 | 15210 | 20280 | Bassem Andrawes | James Klein | BAF
324 | R27-SP13 | Profile Equipment Verification 2009 (Special Project)") | 2009-04-01 | 2009-12-31 | 2010-06-30 | 45000 | 44578 | 3750 | 33750 | 45000 | Imad Al-Qadi | LaDonna Rowden | PVMT
325 | R27-SP14 | Texas-AASHTO Retroreflective Sign Sheeting Specifications (Special Project)") | 2009-05-01 | 2009-08-15 | 2009-09-30 | 27168 | 26912 | 375 | 20376 | 27168 | Liang Liu | Kelly Senger | PVMT
326 | R27-SP15 | Snowplow Simulator Training Study (Special Project)") | 2009-11-01 | 2010-06-30 | 2010-09-30 | 27012 | 25402 | 9281 | 20259 | 27012 | Thomas O'Rourke | Dave Johnson | OPS
327 | R27-SP16 | Evaluation of Horizontal Directional Drilling (HDD) (Special Project)") | 2009-07-16 | 2009-12-31 | 2010-08-15 | 19893 | 22361 | 4920 | 14920 | 19893 | Youssef Hashash | Terri Peterson | Other / Department Wide
328 | R27-SP17 | Warm Mix Asphalt Study (Special Project)") | 2009-07-16 | 2010-03-15 | 2010-07-31 | 23408 | 26471 | 7556 | 17556 | 23408 | Imad Al-Qadi | Tom Zehr | PVMT
329 | R27-SP18 | Developing Best Practices (BPs) for Bicycle Trail Construction & Maintenance in Illinois (Special Project)") | 2011-08-16 | 2012-02-15 | 2012-06-30 | 30000 | 29148 | 2500 | 22500 | 30000 | Barry Dempsey | Todd Hill | ENV
330 | R27-SP19 | Evaluation of the Effect of RAS on IDOT Asphalt Mixtures (Special Project)") | 2011-12-16 | 2012-06-15 | 2012-06-15 | 30000 | 32790 | 2500 | 22500 | 30000 | Hasan Ozer | David Lippert | PVMT
331 | R27-SP20 | Safety Benefits of Implementing Adaptive Signal Control Technologies (ASCT) (Special Project)") | 2012-04-16 | 2012-09-15 | 2012-12-15 | 30000 | 36524 | 2500 | 22500 | 30000 | Ray Benekohal | Kyle Armstrong | OPS
332 | R27-SP21 | Illinois Carbon Monoxide Screen for Intersection Modeling (COSIM) 2012 Update (Special Project)") | 2012-06-01 | 2012-11-30 | 2013-04-30 | 25524 | 12680 | 777 | 19143 | 25524 | Scott Peters | Walt Zyznieuski | ENV
333 | R27-SP22 | Impact of HPMS Sample Counting for 24 Hours Versus 48 Hours (Special Project)") | 2013-03-01 | 2013-08-31 | 2014-04-30 | 25400 | 25001 | 8916 | 19050 | 25400 | James Hall | William Morgan | PLAN
334 | R27-SP23 | Illinois Drainage Laws Update (Special Project)") | 2013-09-16 | 2014-03-15 | 2014-07-31 | 30000 | 37048 | 2500 | 22500 | 30000 | Art Schmidt | Thomas Winkelman | Other / Department Wide
335 | R27-SP24 | TrafficTurk Evaluation (Special Project)") | 2013-08-16 | 2014-02-15 | 2014-02-15 | 30000 | 29181 | 2500 | 22500 | 30000 | Daniel Work | Paul Lorton | SAF
336 | R27-SP25 | Data Analysis for Local Roadway Safety Assessments (Special Project)") | 2013-11-01 | 2014-04-30 | 2014-04-30 | 30000 | 31385 | 2499 | 22500 | 30000 | Yanfeng Ouyang | Mike Gillette | SAF
337 | R27-SP26-C | Evaluation of Agricultural-Based Alternative Deicers (Confidential Special Project)") | 2014-03-01 | 2014-08-28 | 2014-11-30 | 30000 | 35148 | 2500 | 22500 | 30000 | Jim Meister | Tim Peters | OPS
338 | R27-SP27 | AIMS Implementation - Investigation of Relationships between AIMS Shape Properties and VST Friction Values (Special Project)") | 2014-06-01 | 2015-01-31 | 2015-02-28 | 30000 | 30255 | 2306 | 22500 | 30000 | Enad Mahmoud | Sheila Beshears | PVMT
339 | R27-SP28 | Evaluation of PG graded Asphalts with Low-level of ReOB (Special Project)") | 2014-10-01 | 2015-05-31 | 2016-02-15 | 30000 | 34695 | 2500 | 22500 | 30000 | Hasan Ozer | Ronald Price | SUS
340 | R27-SP29 | Thermodynamics Between RAP/RAS and Virgin Aggregates during Asphalt Concrete Production - A Literature Review") | 2015-01-01 | 2015-10-31 | 2015-10-31 | 30000 | 30296 | 2500 | 22500 | 30000 | Mohammad Hossain | Matt Mueller | PVMT
341 | R27-SP30 | Speed Harmonization - Design Speed vs. Operating Speed (SAF) ") | 2015-09-16 | 2016-07-15 | 2016-10-15 | 30000 | 29180 | 2500 | 22500 | 30000 | Yanfeng Ouyang | Kyle Armstrong | SAF
342 | R27-SP31 | Evaluation of I-FIT Results and Machine Variability using MnRoad Test Track Mixtures") | 2016-08-16 | 2017-05-15 | 2017-06-30 | 30000 | 31395 | 9565 | 22500 | 30000 | Hasan Ozer | Tom Zehr | PVMT
343 | R27-SP32 | Crash-Based Evaluation of Red Light Running Cameras in Illinois") | 2016-08-16 | 2017-04-15 | 2017-04-15 | 30000 | 35519 | 2317 | 22350 | 30000 | Kerrie Schattler | Paul Lorton | SAF
344 | R27-SP33 | Spillover Effect and Economic Analysis of Red Light Running Cameras in Illinois") | 2016-08-16 | 2017-04-15 | 2017-04-15 | 30000 | 34457 | 2493 | 22500 | 30000 | Yanfeng Ouyang | Paul Lorton | SAF
345 | R27-SP34 | Evaluation of Various Tack Coat Materials Using Interface Shear Device and Recommendations on a Simplified Device") | 2017-05-01 | 2017-12-31 | 2017-12-31 | 30000 | 35689 | 1492 | 36813 | 46029 | Hasan Ozer | Jim Trepanier | PVMT
346 | R27-SP35 | Behavior of Epoxy Coated Textured Reinforcement Bars") | 2017-05-15 | 2018-01-31 | 2018-04-30 | 30000 | 37068 | 6800 | 29198 | 38930 | Bassem Andrawes | Jayme Schiff | PVMT
347 | R27-SP36 | Modified Micro-Deval Procedure for Polishing of Fine Asphalt Mix Aggregates") | 2017-09-01 | 2018-05-31 | 2018-05-31 | 36000 | 37548 | 7000 | 27000 | 36000 | Zina Eluri | John Senger | PVMT
348 | R27-SP37-C | Safety Implications of Speed Limit Increase to 70 mph on Illinois Interstate Highways") | 2017-09-15 | 2018-06-30 | 2018-08-31 | 35987 | 34145 | 6990 | 26990 | 35987 | Hadi Meidani | Kyle Armstrong | SAF
349 | R27-SP38 | Durability Aspects of Stabilized Quarry By-product Pavement Applications") | 2019-02-01 | 2019-10-31 | 2019-10-31 | 36000 | 37106 | 6998 | 27000 | 36000 | Erol Tutumluer | Heather Shoup | PVMT
350 | R27-SP39 | Current Policies throughout the Nation for Pedestrian Hybrid Beacons (PHB) Installation") | 2019-03-16 | 2019-09-15 | 2019-09-15 | 36000 | 31917 | 6254 | 27000 | 36000 | Stacey DeLorenzo | Jon McCormick / Marshall Metcalf | SAF
351 | R27-SP40 | Literature Review on Distracted Driving in Illinois") | 2019-04-01 | 2019-12-31 | 2020-04-30 | 48500 | 52188 | 9496 | 39500 | 48500 | Yan Qi | Juan Pava / Adam Gabany | SAF
352 | R27-SP41 | Small Cell Installation in Transportation Infrastructure - A Literature Review") | 2019-09-01 | 2019-11-30 | 2020-01-31 | 48500 | 52426 | 9498 | 39500 | 48500 | Mohammad Hossain | Marshall Metcalf | OPS
353 | R27-SP42 | Destructive Testing of IDOT Structure Number 020-3087") | 2019-11-16 | 2020-08-15 | 2020-08-15 | 36000 | 35687 | 6998 | 27000 | 36000 | BF Spencer | Robert Perkins | BAF
354 | R27-SP43 | Aggregate Subgrade Improvements Using Quarry By-Products: A Field Investigation") | 2020-05-16 | 2021-05-15 | 2021-06-30 | 36000 | 33176 | 4951 | 27000 | 36000 | Erol Tutumluer | Michael Short | PVMT
355 | R27-SP44 | HMA Pothole Maintenance Best Practices") | 2020-05-01 | 2021-01-31 | 2021-02-28 | 36000 | 32250 | 5333 | 27000 | 36000 | Ramez Hajj | Laura Shanley | OPS
356 | R27-SP45 | Quantifying Impacts of Prolonged Events on Transit System Ridership") | 2020-11-16 | 2021-08-15 | 2021-09-15 | 36000 | 39029 | 7000 | 27000 | 36000 | Yanfeng Ouyang | Charles Abraham / Jessica Hector-Hsu | MFM
357 | R27-SP46 | Bridge Deterioration and Preservation Model Refinement / Development ") | 2021-01-01 | 2021-09-30 | 2021-09-30 | 48500 | 50660 | 9500 | 39500 | 48500 | Gongkang Fu | Travis Lobmaster / William Morgan | PLAN
358 | R27-SP47 | Evaluating the Benefits of Implementing Mobile Road Weather Information Sensors") | 2021-04-16 | 2022-01-15 | 2022-02-28 | 35997 | 27659 | 5929 | 26997 | 35997 | Khaled El-Rayes | Laura Shanley | OPS
359 | R27-SP48 | Longitudinal Cracking Investigation on I-72 Experimental Unbonded Concrete Overlay") | 2021-05-01 | 2022-01-31 | 2022-02-28 | 36000 | 34290 | 6999 | 27000 | 36000 | Jeffery Roesler | Charles Wienrank | PVMT
360 | R27-SP49 | Optimal Approach for Addressing Reinforcement Corrosion for Concrete Bridge Decks in Illinois") | 2021-08-16 | 2022-05-16 | 2022-05-16 | 48500 | 50650 | 9500 | 39500 | 48500 | Matthew Gombeda | Jayme Schiff / Dan Tobias | BAF
361 | R27-SP50 | Review of Methodologies to Assess Bridge Safety During and After Floods") | 2021-09-01 | 2022-05-31 | 2022-05-31 | 36000 | 37615 | 5990 | 27000 | 36000 | Marcelo Garcia | Timothy Armbrecht / Dan Brydl | BAF
362 | R27-SP51-HS | Effectiveness and External Noise of Transverse Rumble Strip Designs") | 2021-09-01 | 2022-03-31 | 2022-06-30 | 36000 | 5565 | 264 | 28800 | 36000 | Imad Al-Qadi | Issam Rayyan | SAF
363 | R27-SP52 | Optimal Approach for Addressing Reinforcement Corrosion for Concrete Bridge Decks in Illinois - Phase II") | 2022-05-16 | 2023-02-15 | 2023-05-15 | 48500 | 50650 | 9500 | 39500 | 48500 | Matthew Gombeda | Curt Evoy / Del Reeves | BAF
364 | R27-SP53 | Statistical Analysis of COVID-19's Impact on Transit Ridership for CTA Rail | 2022-05-16 | 2023-02-15 | 2023-04-15 | 36000 | 34487 | 7000 | 27000 | 36000 | Yanfeng Ouyang | Charles Abraham / Cemal Ayvalik | MFM
365 | R27-SP54 | Brine Rates") | 2023-01-11 | 2023-01-11 | 2023-01-11 | 0 | 0 |  | 0 | 0 |  |  | OPS
366 | R27-SP55 | Development of Guidelines for Messages in Dynamic Messaging Signs to Improve Safety | 2023-06-01 | 2024-02-29 | 2024-05-31 | 36000 | 34789 | 6147 | 27000 | 36000 | Yanfeng Ouyang | Sean Martschinke | OPS
367 | R27-SP56 | Investigating the Use of Reclaimed Asphalt Pavement in Pavement Preservation Treatments") | 2023-05-01 | 2023-10-31 | 2023-10-31 | 36000 | 36287 | 8102 | 28800 | 36000 | Imad Al-Qadi | John Senger | PVMT
368 | R27-SP57 | Investigating Statewide Alternative Fuel Technician Needs") | 2023-06-01 | 2024-02-29 | 2024-06-30 | 46814 | 44438 | 1881 | 37814 | 46814 | Reggie Greenwood | Charles Abraham / Zoe Keller | MFM
369 | R27-SP58 | Investigating Statewide Transit Maintenance Needs") | 2023-04-01 | 2023-12-31 | 2023-12-31 | 36000 | 29156 | 6283 | 27000 | 36000 | Yanfeng Ouyang | Charles Abraham / Zoe Keller | MFM
370 | R27-SP59 | Field Performance of Unacceptable Hot Mix Asphalt Test Parameters ") | 2023-04-16 | 2024-01-15 | 2024-05-31 | 36000 | 40981 | 7000 | 27000 | 36000 | Ramez Hajj | Douglas Dirks | CON
371 | R27-SP60 | E-Ticketing") | 2023-01-19 | 2023-01-19 | 2023-01-19 | 0 | 0 |  | 0 | 0 |  |  | CON
372 | R27-SP61 | Illinois Department of Transportation Wetland and Stream Mitigation Needs Assessment | 2023-05-16 | 2024-02-15 | 2024-02-15 | 36000 | 31521 | 2111 | 27000 | 36000 | Geoffrey Pociask | Kimberly Burkwald / Shawn Wilcockson | ENV
373 | R27-SP62 | Concrete Bridge Deck Crack Sealing") | 2023-07-01 | 2024-03-31 | 2024-03-31 | 36000 | 36397 | 7000 | 27000 | 36000 | Mohsen Issa | Mark Shaffer | BAF
374 | R27-SP63 | Data Analysis and Review of Multiple Stress Creep and Recovery (MSCR) vs. Performance-graded High temperature Test Results | 2023-04-01 | 2023-12-31 | 2023-12-31 | 36000 | 38801 | 6542 | 27000 | 36000 | Ramez Hajj | Kelly Senger | PVMT
375 | R27-SP64 | Environmental – Endangered Species Mitigation Needs Assessment") | 2023-05-16 | 2024-02-15 | 2024-02-15 | 36000 | 33826 | 1828 | 27000 | 36000 | Wendy Schelsky | Kimberly Burkwald / Shawn Wilcockson | ENV
376 | R27-SP65 | Low-Clearance Early Warning Devices") | 2023-11-01 | 2024-07-31 | 2024-07-31 | 36000 | 32962 | 6818 | 27000 | 36000 | Yanfeng Ouyang | Kyle Armstrong | OPS
377 | R27-SP66 | Anti-Graffiti Protection Systems") | 2024-01-16 | 2024-10-15 | 2024-10-15 | 75743 | 98656 | 7036 | 67036 | 83286 | Yasser Khodair | Mark Shaffer | BAF
378 | R27-SP67 | Avoiding and Minimizing Impacts to Aquatic Resources through Construction Design Standards") | 2024-08-16 | 2025-05-15 | 2025-05-15 | 64977 | 42536 | 7882 | 48733 | 64977 | Dusty Swedberg | Vincent Hamer | ENV
379 | R27-SP68 | Development of Recommended Best Management Practices for IDOT Related to the Rusty Patched Bumblebee") | 2024-09-01 | 2025-05-31 | 2025-11-30 | 65000 | 65398 | 8284 | 48750 | 65000 | Jason Robinson | Kimberly Burkwald | ENV
380 | R27-SP69 | IDOT Development of Special Management Areas ") | 2024-10-01 | 2025-06-30 | 2025-06-30 | 65000 | 65302 | 8750 | 48750 | 65000 | David Zaya | Jake Vancil | ENV
381 | R27-SP70 | Understanding Wildlife Vehicle Collisions in Illinois") | 2024-10-01 | 2025-06-30 | 2025-06-30 | 57867 | 42633 | 1095 | 43400 | 57867 | Kirk Stodola | Bradley Daugherty | ENV
382 | R27-SP71 | Advancing Our Understanding of Self-enforcing Streets and the Use of Target Speeds to Improve Safety.") | 2024-02-16 | 2024-11-15 | 2024-12-15 | 65000 | 72873 | 8749 | 48750 | 65000 | Alireza Talebpour | Stephane Seck-Birhame / Victoria Barrett | SAF
383 | R27-SP72 | Field and Lab Evaluation of Roller Compacted Concrete (RCC) Mixtures for Pavements") | 2024-04-16 | 2025-01-15 | 2025-10-31 | 65000 | 64703 | 8748 | 48750 | 65000 | Jeffery Roesler | John Senger | PVMT
384 | R27-SP73 | Mussel Relocation") | 2025-01-23 | 2025-01-23 | 2025-01-23 | 0 | 0 |  | 0 | 0 |  |  | ENV
385 | R27-SP74 | Evaluation of Concrete Overlays") | 2024-11-16 | 2025-08-15 | 2025-09-30 | 65000 | 65213 | 8747 | 48750 | 65000 | Jeffery Roesler | Charles Wienrank | PVMT
386 | R27-SP75 | Development of Pavement Temperature Measurement System for ICART") | 2025-06-01 | 2026-02-28 | 2026-08-31 | 65000 | 16597 | 1272 | 48750 | 65000 | Ramez Hajj | John Senger | PVMT
387 | R27-SP76 | In-Service Evaluation of Temporary Sign Support Systems Against Wind Load") | 2025-06-01 | 2026-02-28 | 2026-05-31 | 65000 | 7325 | 265 | 48750 | 65000 | Yanfeng Ouyang | Juan Pava | SAF
388 | R27-SP77 | Synthesis of Capabilities | 2025-09-16 | 2026-06-15 | 2026-09-15 | 64997 | 7336 | 835 | 48748 | 64997 | Mohamad Alipour | Mark Shaffer | BAF
389 | R27-SP78 | Concrete Strength Sensing Using REBEL Sensors") | 2025-09-01 | 2026-05-31 | 2026-08-31 | 85948 | 0 |  | 69698 | 85948 | Mohammad Hossain | Charles Wienrank / Xinyu Sun | PVMT
390 | R27-SP79 | IDOT | 2025-10-16 | 2026-07-15 | 2026-07-15 | 65000 | 13636 | 865 | 48750 | 65000 | Dan Salas | Kimberly Burkwald | ENV
391 | R27-SP80 | Statistical Evaluation of Illinois Modified AASHTO T161 Freeze–Thaw Testing Following Laboratory Relocation") | 2026-04-01 | 2026-12-31 | 2026-12-31 | 65000 | 0 |  | 48750 | 65000 | Nishant Garg | Andrew Stolba | PVMT
392 | R27-SP81 | Audible Warning System on TMA and Maintenance Trucks") | 2026-03-01 | 2026-11-30 | 2026-11-30 | 65000 | 0 |  | 48750 | 65000 | Yanfeng Ouyang | Meiwu An / Greg Gurski | OPS
393 | R27-SP83 | Ladle Furnace Slag Properties When Blended with Dolomitic Underutilized Quarry Materials") | 2026-03-01 | 2026-11-30 | 2026-11-30 | 65000 | 0 |  | 48750 | 65000 | Erol Tutumluer | Andrew Stolba | PVMT
394 | R28-001 | Mechanistic-Empirical Design | 2005-07-01 | 2008-06-30 | 2008-06-30 | 42000 | 132720 | 3509 | 95135 | 126846 | Marshall Thompson | David Lippert | PVMT
395 | R28-002 | Binder / Mixture Testing & Analysis - Addition to R28 Mechanistic Design") | 2008-01-01 | 2008-08-31 | 2008-08-31 | 42000 | 47016 | 3125 | 31500 | 42000 | Samuel Carpenter | Amy Schutzbach | PVMT
396 | R39-001 | Validation Of Extended Life HMA Pavement Design Concepts") | 2002-07-01 | 2006-06-30 | 2006-12-31 | 120018 | 184480 | 29976 | 127514 | 170020 | Samuel Carpenter | Amy Schutzbach | PVMT
397 | R39-002 | Nondestructive Pavement Evaluation Using ILLI-PAVE Based Artificial Neural Network Models") | 2004-08-01 | 2008-06-30 | 2008-08-31 | 84818 | 86795 | 1152 | 63614 | 84818 | Erol Tutumluer | Charles Wienrank | PVMT
398 | R43 | Traffic Operations Lab - Signal Systems Testing") | 2005-07-01 | 2008-06-30 | 2008-06-30 | 444631 | 454367 | 20127 | 333473 | 444631 | Ray Benekohal | Yogesh Gautam | OPS
399 | R44 | Performance and Acceptance of Self-Consolidating Concrete") | 2003-07-01 | 2007-09-15 | 2007-09-15 | 151414 | 202464 | 42647 | 142646 | 190196 | David Lange | James Krstulovich | PVMT
400 | R53 | Concrete Distress Identification") | 2005-07-01 | 2006-06-30 | 2006-06-30 | 71729 | 83983 | 9171 | 59176 | 78902 | Leslie Struble | Patricia Broers | PVMT
401 | R54 | Development of Standard for Lifting Loops in Shallow Precast Deck Beams") | 2005-07-01 | 2007-12-31 | 2008-09-30 | 258833 | 296818 | 9125 | 209124 | 278832 | Dan Kuchma | Kevin Riechers | BAF
402 | R55 | Tack Coat Optimization For HMA Overlays") | 2005-07-01 | 2008-06-30 | 2008-12-31 | 435702 | 745278 | 20205 | 520942 | 694590 | Imad Al-Qadi | Jim Trepanier | PVMT
403 | R56 | Speed Photo-Enforcement in Illinois Work Zones") | 2005-07-01 | 2007-06-30 | 2008-06-30 | 289438 | 329031 | 31821 | 231821 | 309095 | Ray Benekohal | Priscilla Tobias | SAF
404 | R57 | Evaluation and Implementation of Improved CRCP And JPCP Design") | 2005-09-01 | 2008-06-30 | 2008-12-31 | 249449 | 321183 | 26291 | 226361 | 301814 | Jeffery Roesler | Amy Schutzbach | PVMT
405 | R58 | Cost-Effectiveness and Performance of Overlay Systems in IL / Reflective Crack Control") | 2005-07-01 | 2008-06-30 | 2008-12-31 | 294535 | 329558 | 32192 | 232192 | 309589 | William Buttlar | Joe Vespa | PVMT
406 | R59 | Evaluation of Pavement Damage Due to New Tire Designs") | 2006-01-01 | 2008-12-31 | 2008-12-31 | 311599 | 317494 | 19353 | 220420 | 293893 | Imad Al-Qadi | Mark Gawedzinski | PVMT
407 | R60-ADMIN (FY06-08 IGA) | R60-ADMIN (FY06-08 IGA)") | 2005-07-01 | 2008-06-30 | 2008-06-30 | 1040000 | 779998 | 79998 | 780000 | 1040000 | Kristi Anderson | Megan Swanson | Other / Department Wide
408 | R60-ADMIN (FY09-11 IGA) | R60-ADMIN (FY09-11 IGA)") | 2008-07-01 | 2011-06-30 | 2011-06-30 | 995000 | 892939 | 92939 | 995000 | 995000 | Kristi Anderson | Megan Swanson | Other / Department Wide
409 | R60-ADMIN (FY12-17 IGA) | R60-ADMIN (FY12-17 IGA)") | 2011-07-01 | 2017-06-30 | 2017-06-30 | 2700000 | 3132685 | 54691 | 2700000 | 2700000 | Kristi Anderson | Megan Swanson | Other / Department Wide
410 | R60-ADMIN (FY18-24 IGA) | Program Management and Administration (FY18-24 IGA)") | 2017-07-01 | 2020-06-30 | 2024-06-30 | 1290000 | 3177391 | 177391 | 3290000 | 3290000 | Kristi Anderson | John Senger | Other / Department Wide
411 | R60-ADMIN (FY25-30 IGA) | Program Management and Administration (FY25-30 IGA)") | 2024-07-01 | 2030-06-30 | 2030-06-30 | 3900000 | 888313 | 88313 | 3900000 | 3900000 | Kristi Anderson | John Senger | Other / Department Wide

## Dashboard
| Project ID | Research Conducted By | Start Date | Original End Date | Current End Date | Project Length Years | Current IDOT Budget | Current Proj. Budget | Primary Investigator | TRP Chair | TAGs | Active
0 | R27-001 |  | 2006-01-01 | 2008-06-30 | 2009-06-30 | 3 | 299329 | 399101 | Erol Tutumluer | Riyad Wahab | PVMT | No
1 | R27-002 |  | 2006-01-01 | 2007-12-31 | 2007-12-31 | 2 | 141164 | 223573 | Khaled El-Rayes | Dennis Huckaba | SAF | No
2 | R27-003 |  | 2006-01-01 | 2007-12-31 | 2008-03-31 | 2 | 185764 | 247685 | Jeffery Roesler | James Krstulovich | PVMT | No
3 | R27-004 |  | 2006-01-01 | 2007-06-30 | 2007-06-30 | 1 | 44842 | 59789 | William Dunn | Joseph Hill | OPS | No
4 | R27-005 |  | 2007-08-16 | 2008-06-30 | 2009-01-31 | 1 | 67952 | 90603 | Vonu Thakuriah | Charles Abraham | MFM | No
5 | R27-006 |  | 2006-03-01 | 2008-06-30 | 2008-06-30 | 2 | 60000 | 120000 | David Soong | Matthew O'Connor | BAF | No
6 | R27-007 |  | 2007-02-01 | 2007-08-31 | 2007-08-31 | 1 | 16635 | 22181 | Scott Peters | Walt Zyznieuski | ENV | No
7 | R27-008 |  | 2006-06-01 | 2007-06-30 | 2007-06-30 | 1 | 16550 | 22100 | Mostafa Elseifi | Jim Trepanier | PVMT | No
8 | R27-009 |  | 2006-07-01 | 2008-06-30 | 2008-06-30 | 2 | 101738 | 133849 | Ming Wang | Todd Ahrens | BAF | No
9 | R27-010 |  | 2006-07-01 | 2007-02-28 | 2007-02-28 | 1 | 37679 | 50266 | Jane Lin | Walt Zyznieuski | ENV | No
10 | R27-011 |  | 2006-07-01 | 2008-06-30 | 2008-06-30 | 2 | 157738 | 210340 | Imad Al-Qadi | Jim Trepanier | PVMT | No
11 | R27-012 |  | 2006-07-01 | 2008-06-30 | 2008-08-31 | 2 | 112500 | 150000 | Marshall Thompson | Kevin Burke | PVMT | No
12 | R27-013 |  | 2006-07-01 | 2007-06-30 | 2007-08-31 | 1 | 104905 | 139874 | Laura Heckel | David Felts | PLAN | No
13 | R27-014 |  | 2006-09-06 | 2007-03-31 | 2007-03-31 | 1 | 51942 | 69297 | Peter Nelson | Charles Sikaras | PLAN | No
14 | R27-015 |  | 2007-01-01 | 2007-12-31 | 2008-07-31 | 2 | 50000 | 66667 | Jon Devries | Charles Abraham | MFM | No
15 | R27-016 |  | 2007-01-01 | 2008-03-31 | 2008-03-31 | 1 | 40000 | 56132 | Peter Beltemacchi | Charles Abraham | MFM | No
16 | R27-017 |  | 2006-07-01 | 2007-06-30 | 2008-11-30 | 2 | 61875 | 82500 | Kouros Mohammadian | Charles Abraham | MFM | No
17 | R27-018 |  | 2006-07-01 | 2007-12-31 | 2008-12-31 | 3 | 123751 | 165001 | Yanfeng Ouyang | Kevin Burke | SAF | No
18 | R27-019 |  | 2006-08-01 | 2009-06-30 | 2010-06-30 | 4 | 238000 | 352167 | Tim Straub | Matthew O'Connor | BAF | No
19 | R27-020 |  | 2007-01-01 | 2008-12-31 | 2008-12-31 | 2 | 105001 | 140000 | Yanfeng Ouyang | David Piper | SAF | No
20 | R27-021 |  | 2007-01-01 | 2007-12-31 | 2008-08-31 | 2 | 43368 | 57824 | Ray Benekohal | Sean Coyle | SAF | No
21 | R27-022 |  | 2007-04-01 | 2008-06-30 | 2008-08-31 | 1 | 56249 | 150000 | Yanfeng Ouyang | John Benda | OPS | No
22 | R27-023 |  | 2007-07-01 | 2008-06-30 | 2008-08-31 | 1 | 99240 | 134940 | Angela Wolters | Jeffrey South | PLAN | No
23 | R27-024 |  | 2007-01-01 | 2008-12-31 | 2009-03-31 | 2 | 118534 | 158045 | Jim Long | Bill Kramer | BAF | No
24 | R27-025 |  | 2007-01-01 | 2008-12-31 | 2009-03-31 | 2 | 89835 | 119780 | Scott Olson | Bill Kramer | BAF | No
25 | R27-026 |  | 2007-04-01 | 2008-09-30 | 2009-04-30 | 2 | 89735 | 119647 | Dan Kuchma | Chris Hahin | BAF | No
26 | R27-027 |  | 2007-02-01 | 2008-06-30 | 2009-04-30 | 2 | 56250 | 75000 | Erol Tutumluer | Sheila Beshears | PVMT | No
27 | R27-028-T1 |  | 2007-09-01 | 2008-06-30 | 2011-06-30 | 4 | 145518 | 194025 | Imad Al-Qadi | David Lippert | Other / Department Wide | No
28 | R27-028-T2 |  | 2007-11-01 | 2008-10-31 | 2008-10-31 | 1 | 56374 | 75165 | Imad Al-Qadi | David Lippert | Other / Department Wide | No
29 | R27-028-T3 |  | 2009-05-01 | 2009-09-30 | 2009-09-30 | 0 | 11250 | 15000 | Erol Tutumluer | Amy Schutzbach | PVMT | No
30 | R27-029 |  | 2007-07-01 | 2008-02-29 | 2008-06-30 | 1 | 45000 | 60000 | Jane Lin | Walt Zyznieuski | ENV | No
31 | R27-030 |  | 2007-09-16 | 2009-08-15 | 2009-08-15 | 2 | 149452 | 199246 | Dianne Slattery | Ted Nemsky | CON | No
32 | R27-031 |  | 2007-08-01 | 2008-06-30 | 2008-12-31 | 1 | 52500 | 70000 | Patrick Chapman | Dave Johnson | OPS | No
33 | R27-032 |  | 2007-09-01 | 2008-08-31 | 2008-12-31 | 1 | 75002 | 103779 | Doug Steele | Aaron Weatherholt | OPS | No
34 | R27-033 |  | 2007-10-01 | 2009-11-30 | 2010-08-31 | 3 | 120000 | 160000 | Ray Benekohal | Marshall Metcalf | OPS | No
35 | R27-034 |  | 2007-10-01 | 2008-09-30 | 2009-04-30 | 2 | 60000 | 80000 | Yanfeng Ouyang | Jeffrey South | PLAN | No
36 | R27-035 |  | 2007-08-01 | 2008-06-30 | 2008-10-31 | 1 | 52500 | 77617 | Farhad Ansari | Dave Copenbarger | BAF | No
37 | R27-036 |  | 2007-08-01 | 2008-06-30 | 2008-09-30 | 1 | 37500 | 50000 | Bassem Andrawes | Tom Domagalski | BAF | No
38 | R27-037 |  | 2008-07-01 | 2010-06-30 | 2011-12-31 | 3 | 240702 | 320937 | Imad Al-Qadi | Jim Trepanier | PVMT | No
39 | R27-038 |  | 2007-09-01 | 2010-06-30 | 2010-06-30 | 3 | 185323 | 247098 | John Popovics | Derek Parish | PVMT | No
40 | R27-039 |  | 2008-02-16 | 2008-06-30 | 2008-09-30 | 1 | 37500 | 50000 | James Hall | Susan Stitt | PLAN | No
41 | R27-040 |  | 2008-01-01 | 2009-12-31 | 2010-09-30 | 3 | 105000 | 140000 | Zongzhi Li | David Piper | SAF | No
42 | R27-041 |  | 2008-01-01 | 2008-06-30 | 2008-11-30 | 1 | 40500 | 54000 | Jeffery Roesler | Mark Gawedzinski | PVMT | No
43 | R27-042 |  | 2008-03-07 | 2011-06-30 | 2013-03-31 | 5 | 523054 | 697405 | Imad Al-Qadi | Tom Zehr | PVMT | No
44 | R27-043 |  | 2007-11-01 | 2008-10-31 | 2008-10-31 | 1 | 15000 | 20000 | Yanfeng Ouyang | Kevin Burke | Other / Department Wide | No
45 | R27-044 (FY09-11 IGA) |  | 2008-07-01 | 2011-06-30 | 2011-06-30 | 3 | 341654 | 455539 | Imad Al-Qadi | Megan Swanson | Other / Department Wide | No
46 | R27-044 (FY12-17 IGA) |  | 2011-07-01 | 2017-06-30 | 2017-06-30 | 6 | 1237500 | 1650000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide | No
47 | R27-044-T1 |  | 2012-06-01 | 2013-05-31 | 2013-07-31 | 1 | 112500 | 150000 | Hasan Ozer | Charles Wienrank | PVMT | No
48 | R27-045 (FY09-11 IGA) |  | 2008-07-01 | 2011-06-30 | 2011-06-30 | 3 | 335702 | 447603 | Imad Al-Qadi | Megan Swanson | Other / Department Wide | No
49 | R27-045 (FY12-17 IGA) |  | 2011-07-01 | 2017-06-30 | 2017-06-30 | 6 | 752040 | 1002720 | Imad Al-Qadi | Megan Swanson | Other / Department Wide | No
50 | R27-045-T1 | In-State University | 2013-10-01 | 2015-03-31 | 2018-06-30 | 5 | 215121 | 286102 | Greg Renshaw | Ryan Culton | CON | No
51 | R27-046 (FY09-11 IGA) |  | 2008-07-01 | 2011-06-30 | 2011-06-30 | 3 | 360000 | 480000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide | No
52 | R27-046 (FY12-17 IGA) |  | 2011-07-01 | 2017-06-30 | 2017-06-30 | 6 | 1200000 | 1600000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide | No
53 | R27-047 |  | 2008-05-13 | 2008-05-13 | 2008-05-13 | 0 |  |  |  |  | ENV | No
54 | R27-048 |  | 2009-01-01 | 2010-10-31 | 2011-06-30 | 2 | 120000 | 160000 | Rita Morocoima-Black | Susan Stitt | PLAN | No
55 | R27-049 |  | 2008-05-01 | 2011-06-30 | 2010-06-30 | 2 | 150000 | 200000 | Imad Al-Qadi | Mike Renner | CON | No
56 | R27-050 |  | 2008-08-16 | 2009-12-31 | 2010-12-31 | 2 | 77675 | 110887 | Kouros Mohammadian | Charles Abraham | MFM | No
57 | R27-051 |  | 2008-11-01 | 2009-10-31 | 2010-09-30 | 2 | 59560 | 80536 | Peter Beltemacchi | Charles Abraham | MFM | No
58 | R27-052 |  | 2008-09-16 | 2010-09-15 | 2010-09-15 | 2 | 157499 | 209999 | Khaled El-Rayes | Marshall Metcalf | SAF | No
59 | R27-053 |  | 2008-09-04 | 2008-09-04 | 2008-09-04 | 0 |  |  |  |  | SAF | No
60 | R27-054 |  | 2009-01-01 | 2011-12-31 | 2012-12-31 | 4 | 374422 | 499229 | Prasanta Kalita | Joe Vespa | ENV | No
61 | R27-055 |  | 2008-08-16 | 2011-06-30 | 2012-03-31 | 4 | 272249 | 362999 | Scott Olson | Bill Kramer | BAF | No
62 | R27-056 |  | 2008-07-16 | 2010-06-30 | 2011-02-28 | 3 | 142500 | 190000 | Bassem Andrawes | Tom Domagalski | BAF | No
63 | R27-057 |  | 2009-01-01 | 2010-12-31 | 2011-12-31 | 3 | 120000 | 160000 | Mohammad Alhassan | Gary Kowalski | BAF | No
64 | R27-058 |  | 2008-07-01 | 2010-06-30 | 2011-03-31 | 3 | 164718 | 219624 | Ray Benekohal | Yogesh Gautam | OPS | No
65 | R27-059 |  | 2008-07-01 | 2010-06-30 | 2011-03-31 | 3 | 164194 | 218925 | Ray Benekohal | Yogesh Gautam | OPS | No
66 | R27-060 |  | 2008-07-01 | 2011-06-30 | 2014-06-30 | 6 | 363118 | 484158 | Marshall Thompson | Charles Wienrank | PVMT | No
67 | R27-061 |  | 2009-01-01 | 2011-06-30 | 2014-08-31 | 6 | 366506 | 488675 | Jeffery Roesler | Charles Wienrank | PVMT | No
68 | R27-062 |  | 2009-02-01 | 2010-01-31 | 2010-12-31 | 2 | 83200 | 110934 | Tim Murphy | David Lippert | PVMT | No
69 | R27-063 |  | 2008-11-01 | 2009-10-31 | 2010-09-30 | 2 | 70930 | 94574 | Thomas Dam | Mark Gawedzinski | PVMT | No
70 | R27-064 |  | 2009-07-01 | 2011-06-30 | 2011-06-30 | 2 | 102011 | 136400 | Huaguo Zhou | Geno Koehler | OPS | No
71 | R27-065 |  | 2009-09-11 | 2009-09-11 | 2009-09-11 | 0 |  |  |  |  | SAF | No
72 | R27-066 |  | 2009-11-01 | 2012-10-31 | 2012-10-31 | 3 | 225000 | 300397 | Hani Mahmassani | Paul Lorton | SAF | No
73 | R27-067 |  | 2009-01-01 | 2009-12-31 | 2009-12-31 | 1 | 75000 | 100000 | Yanfeng Ouyang | Priscilla Tobias | SAF | No
74 | R27-068 |  | 2009-03-16 | 2009-12-31 | 2009-12-31 | 1 | 34135 | 45513 | Michael Koerber | Walt Zyznieuski | ENV | No
75 | R27-069 |  | 2009-01-01 | 2010-12-31 | 2012-06-30 | 3 | 342818 | 457091 | Jim Long | Bill Kramer | BAF | No
76 | R27-070 |  | 2009-01-01 | 2011-12-31 | 2012-12-31 | 4 | 562560 | 750080 | James LaFave | Dan Tobias | BAF | No
77 | R27-071 |  | 2009-02-01 | 2010-01-31 | 2010-06-30 | 1 | 161450 | 215267 | Farhad Ansari | Dave Copenbarger | BAF | No
78 | R27-072 |  | 2009-01-16 | 2010-01-31 | 2010-01-31 | 1 | 131250 | 175000 | Doug Steele | Aaron Weatherholt | OPS | No
79 | R27-073 |  | 2009-02-01 | 2012-01-31 | 2013-03-31 | 4 | 225000 | 300000 | James Hall | Kevin Burke | Other / Department Wide | No
80 | R27-074 |  | 2010-01-01 | 2010-12-31 | 2010-12-31 | 1 | 75000 | 100000 | Khaled El-Rayes | Craig Mitckes | ENV | No
81 | R27-075 |  | 2010-04-01 | 2012-03-31 | 2012-03-31 | 2 | 170665 | 230000 | Hani Mahmassani | Julia Fox | OPS | No
82 | R27-076 |  | 2009-11-01 | 2011-10-31 | 2012-03-31 | 2 | 226950 | 302599 | Ray Benekohal | Mark Seppelt | OPS | No
83 | R27-077 |  | 2009-12-01 | 2012-11-30 | 2013-11-30 | 4 | 276963 | 369284 | Carmine Dwyer | Kelly Senger | PVMT | No
84 | R27-078 |  | 2010-02-16 | 2012-08-15 | 2013-12-31 | 4 | 409558 | 546077 | Imad Al-Qadi | Jim Trepanier | PVMT | No
85 | R27-079 |  | 2009-08-16 | 2011-12-31 | 2013-12-31 | 4 | 519537 | 692716 | William Buttlar | Matt Mueller | PVMT | No
86 | R27-080 |  | 2009-07-01 | 2010-06-30 | 2010-12-31 | 2 | 63750 | 85000 | Greg Banas | Chris Hahin | BAF | No
87 | R27-081 |  | 2010-01-01 | 2011-12-31 | 2011-12-31 | 2 | 251263 | 335017 | Erol Tutumluer | Greg Heckel | BAF | No
88 | R27-082 |  | 2009-08-16 | 2012-02-15 | 2012-08-15 | 3 | 150000 | 200000 | Bassem Andrawes | Dan Tobias | BAF | No
89 | R27-083 |  | 2010-01-01 | 2011-08-15 | 2011-08-15 | 2 | 119940 | 159920 | Kouros Mohammadian | Mike Garcia | PLAN | No
90 | R27-084 |  | 2010-04-01 | 2010-12-31 | 2011-06-30 | 1 | 91672 | 125407 | Marco Nie | Jeff Galas | PLAN | No
91 | R27-085 |  | 2010-03-03 | 2010-03-03 | 2010-03-03 | 0 |  |  |  |  | PVMT | No
92 | R27-086 |  | 2010-07-01 | 2011-06-30 | 2011-06-30 | 1 | 66833 | 89113 | Dianne Slattery | Mike Ripka | CON | No
93 | R27-087 |  | 2010-05-01 | 2011-10-31 | 2011-08-31 | 1 | 74390 | 99851 | Angela Wolters | Kevin Burke | PLAN | No
94 | R27-088 |  | 2010-05-16 | 2013-05-15 | 2013-06-15 | 3 | 250779 | 334372 | Paramita Mondal | Dan Tobias | BAF | No
95 | R27-089 |  | 2010-08-16 | 2011-03-15 | 2011-06-30 | 1 | 115000 | 153333 | Yanfeng Ouyang | Priscilla Tobias | SAF | No
96 | R27-090 |  | 2010-07-01 | 2012-06-30 | 2015-09-30 | 5 | 355576 | 474421 | Huaguo Zhou | Richard Coakley / Priscilla Tobias | SAF | No
97 | R27-091 |  | 2010-01-01 | 2010-12-31 | 2010-12-31 | 1 | 74954 | 99938 | Jakob Eriksson | Jeff Galas | OPS | No
98 | R27-092 |  | 2009-11-13 | 2009-11-13 | 2009-11-13 | 0 |  |  |  |  | Other / Department Wide | No
99 | R27-093 |  | 2010-11-01 | 2011-10-31 | 2013-06-30 | 3 | 73305 | 97749 | Jane Lin | Walt Zyznieuski | ENV | No
100 | R27-094 |  | 2011-09-01 | 2013-08-31 | 2015-11-30 | 4 | 253523 | 338708 | Souhail Elhouar | Tim Peters | OPS | No
101 | R27-095 |  | 2010-08-16 | 2012-08-15 | 2014-12-31 | 4 | 255665 | 340887 | Ray Benekohal | Yogesh Gautam | OPS | No
102 | R27-096 |  | 2011-01-01 | 2012-12-31 | 2012-12-31 | 2 | 150000 | 202658 | Paul Metaxatos | Kyle Armstrong | OPS | No
103 | R27-097 |  | 2010-11-01 | 2012-11-30 | 2016-03-31 | 5 | 264649 | 399153 | Kerrie Schattler | Randy Laninga | SAF | No
104 | R27-098 |  | 2010-08-16 | 2012-02-15 | 2012-06-30 | 2 | 172500 | 230000 | John Popovics | Douglas Dirks | BAF | No
105 | R27-099 |  | 2011-11-01 | 2013-04-30 | 2013-04-30 | 1 | 129375 | 172500 | Timothy Stark | Bill Kramer | BAF | No
106 | R27-100 |  | 2010-09-16 | 2013-03-15 | 2013-03-15 | 2 | 396093 | 529445 | Imad Al-Qadi | Derek Parish | PVMT | No
107 | R27-101 |  | 2011-01-01 | 2016-06-30 | 2017-06-30 | 6 | 137500 | 275000 | Imad Al-Qadi | Amy Schutzbach | Other / Department Wide | No
108 | R27-102 |  | 2011-08-16 | 2014-08-15 | 2016-01-15 | 4 | 308433 | 411244 | Prasanta Kalita | Joe Vespa | ENV | No
109 | R27-103 |  | 2011-01-01 | 2012-12-31 | 2013-06-30 | 2 | 165000 | 220000 | Khaled El-Rayes | Matt Sunderland | ENV | No
110 | R27-104 |  | 2012-01-01 | 2013-12-31 | 2014-05-31 | 2 | 144068 | 192090 | Heidi Howard | Scott Marlow | ENV | No
111 | R27-105 |  | 2011-04-01 | 2013-03-31 | 2013-03-31 | 2 | 153000 | 204000 | Tim Straub | Neil VanBebber | BAF | No
112 | R27-106 |  | 2011-12-01 | 2012-11-30 | 2013-10-31 | 2 | 77626 | 103500 | Semyon Vaynman | Chris Hahin | BAF | No
113 | R27-107 |  | 2013-07-02 | 2013-07-02 | 2013-07-02 | 0 |  |  |  |  | BAF | No
114 | R27-108 |  | 2011-09-01 | 2013-04-30 | 2013-10-31 | 2 | 180000 | 240000 | Doug Steele | Tim Kell | OPS | No
115 | R27-109 |  | 2011-11-01 | 2013-10-31 | 2013-10-31 | 2 | 125299 | 167066 | Khaled El-Rayes | Paul Lorton | SAF | No
116 | R27-110 |  | 2012-04-16 | 2013-04-15 | 2013-04-15 | 1 | 63977 | 85303 | Ray Benekohal | Paul Lorton | SAF | No
117 | R27-111 |  | 2011-09-01 | 2013-08-31 | 2016-06-30 | 5 | 175000 | 255415 | Kerrie Schattler | Dan Mlacnik | SAF | No
118 | R27-112 |  | 2011-05-01 | 2013-04-30 | 2013-12-31 | 3 | 299995 | 399987 | Mohsen Issa | John Huang | PVMT | No
119 | R27-113 |  | 2011-07-01 | 2012-12-31 | 2013-08-15 | 2 | 93793 | 125063 | Kouros Mohammadian | Amy Welk | MFM | No
120 | R27-114 |  | 2011-10-01 | 2012-09-30 | 2013-03-31 | 1 | 60000 | 81214 | Geoffrey Pociask | Tom Brooks | ENV | No
121 | R27-115 | In-State University | 2012-03-01 | 2015-02-28 | 2017-08-15 | 5 | 259178 | 345571 | James LaFave | Mark Shaffer | BAF | No
122 | R27-116 |  | 2012-01-01 | 2013-06-30 | 2013-06-30 | 1 | 161250 | 215000 | Huaguo Zhou | Rob Robinson | SAF | No
123 | R27-117 |  | 2012-08-01 | 2013-06-30 | 2013-06-30 | 1 | 37500 | 50000 | Yanfeng Ouyang | Priscilla Tobias | SAF | No
124 | R27-118 |  | 2011-08-16 | 2013-08-15 | 2014-06-30 | 3 | 280896 | 374668 | Ryan Fries | Geno Koehler | OPS | No
125 | R27-119 |  | 2013-08-16 | 2015-02-15 | 2016-02-15 | 2 | 172645 | 235770 | Ryan Fries | Kevin Price / Bruce Carmitchel | PLAN | No
126 | R27-120 | Out-of-State University | 2012-04-01 | 2014-12-31 | 2019-06-30 | 7 | 378585 | 500614 | Neal Hawkins | Kelly Senger | OPS | No
127 | R27-121 |  | 2015-03-05 | 2015-03-05 | 2015-03-05 | 0 |  |  |  |  | PVMT | No
128 | R27-122 |  | 2012-07-01 | 2014-06-30 | 2014-08-31 | 2 | 228594 | 304792 | Jim Long | Bill Kramer | BAF | No
129 | R27-123 |  | 2012-10-16 | 2014-10-15 | 2015-01-15 | 2 | 211500 | 282000 | Ray Benekohal | Mark Seppelt | OPS | No
130 | R27-124 |  | 2012-08-16 | 2014-08-15 | 2015-07-31 | 3 | 364963 | 486617 | Erol Tutumluer | Sheila Beshears | PVMT | No
131 | R27-125 |  | 2013-02-01 | 2015-01-31 | 2015-05-31 | 2 | 165000 | 220000 | Erol Tutumluer | Sheila Beshears | PVMT | No
132 | R27-126 |  | 2012-08-01 | 2014-06-30 | 2014-09-30 | 2 | 187497 | 249996 | Mark Grinter | Matt Sunderland | ENV | No
133 | R27-127 | In-State University | 2013-01-01 | 2015-12-31 | 2019-06-30 | 6 | 764874 | 1019832 | Ray Benekohal | Kyle Armstrong | OPS | No
134 | R27-128 |  | 2013-01-01 | 2015-12-31 | 2015-12-31 | 3 | 584390 | 779997 | Imad Al-Qadi | Matt Mueller | PVMT | No
135 | R27-129 |  | 2012-12-01 | 2014-02-28 | 2014-02-28 | 1 | 93750 | 125000 | Enad Mahmoud | Sheila Beshears | PVMT | No
136 | R27-130 |  | 2012-08-16 | 2014-08-15 | 2015-07-31 | 3 | 90000 | 120000 | Erol Tutumluer | Thomas Winkelman / Scott Lackey | PVMT | No
137 | R27-131 |  | 2012-07-01 | 2013-12-31 | 2014-12-31 | 2 | 149985 | 199980 | Jakob Eriksson | William Morgan | PLAN | No
138 | R27-132 |  | 2012-07-01 | 2014-06-30 | 2014-06-30 | 2 | 134777 | 179703 | Nora El-Gohary | Bruce Carmitchel | PLAN | No
139 | R27-133 | In-State University | 2013-10-01 | 2016-06-30 | 2018-08-31 | 5 | 225847 | 301129 | James LaFave | Mark Shaffer | BAF | No
140 | R27-134 |  | 2012-11-16 | 2015-11-15 | 2016-05-15 | 3 | 262500 | 350000 | Bassem Andrawes | Jeff Burke | BAF | No
141 | R27-135 |  | 2013-05-01 | 2015-01-31 | 2015-05-31 | 2 | 133614 | 180968 | Dianne Slattery | Ted Nemsky | CON | No
142 | R27-136 |  | 2013-10-01 | 2015-11-30 | 2016-01-31 | 2 | 162499 | 216665 | Khaled El-Rayes | Juliet Shoultz | OPS | No
143 | R27-137 |  | 2013-07-01 | 2015-12-31 | 2016-12-31 | 4 | 215625 | 287500 | John Popovics | Douglas Dirks | BAF | No
144 | R27-138 |  | 2013-09-01 | 2014-02-28 | 2014-04-30 | 1 | 60000 | 80000 | Constance Kelly | Mark Neale | CON | No
145 | R27-139 |  | 2013-07-01 | 2016-06-30 | 2016-06-30 | 3 | 275805 | 367739 | Paramita Mondal | James Krstulovich | PVMT | No
146 | R27-140 |  | 2014-01-01 | 2014-01-01 | 2016-06-30 | 2 | 225000 | 300000 | Riyadh Hindi | Mark Thomson | BAF | No
147 | R27-141 |  | 2014-02-01 | 2017-01-31 | 2017-06-30 | 3 | 256892 | 344303 | Abdolreza Osouli | Scott Marlow | OPS | No
148 | R27-142 |  | 2014-10-01 | 2016-03-31 | 2016-09-30 | 2 | 212580 | 283440 | Carmine Dwyer | Derek Parish / Ruben Boehler | OPS | No
149 | R27-143 |  | 2013-09-01 | 2015-02-28 | 2015-02-28 | 1 | 59882 | 79843 | Jeffrey Matthews | Tom Brooks | ENV | No
150 | R27-144 |  | 2013-08-01 | 2016-01-31 | 2016-06-30 | 3 | 349350 | 466000 | Audrey Ishii | Matthew O'Connor | BAF | No
151 | R27-145 | In-State University | 2014-01-01 | 2016-12-31 | 2017-12-16 | 4 | 552200 | 736267 | Timothy Stark | Bill Kramer | BAF | No
152 | R27-146 |  | 2013-07-01 | 2016-06-30 | 2017-04-30 | 4 | 375000 | 500000 | John Popovics | Douglas Dirks / Gary Kowalski | CON | No
153 | R27-147 |  | 2014-03-17 | 2014-09-15 | 2014-09-15 | 0 | 75000 | 100000 | Wilfrid Nixon | Tim Peters | OPS | No
154 | R27-148 |  | 2015-01-01 | 2016-12-31 | 2016-12-31 | 2 | 150000 | 200000 | Prasanta Kalita | Thomas Winkelman / Jayme Schiff | BAF | No
155 | R27-149-1 | In-State University | 2014-07-01 | 2017-06-30 | 2018-06-30 | 4 | 206897 | 275863 | Marshall Thompson | Charles Wienrank | PVMT | No
156 | R27-149-2 | In-State University | 2014-07-01 | 2017-06-30 | 2018-08-31 | 4 | 292194 | 389592 | Jeffery Roesler | Charles Wienrank | PVMT | No
157 | R27-150 | In-State University | 2015-01-01 | 2016-12-31 | 2018-02-28 | 3 | 154195 | 203343 | Hasan Ozer | Travis Lobmaster / Joe Vespa | PLAN | No
158 | R27-151 | Private Industry | 2014-10-01 | 2018-11-30 | 2019-11-30 | 5 | 353105 | 466640 | Carmine Dwyer | Kelly Senger / Kyle Armstrong | OPS | No
159 | R27-152 |  | 2015-03-01 | 2017-02-28 | 2017-02-28 | 2 | 225001 | 300000 | Imad Al-Qadi | Justan Mann | OPS | No
160 | R27-153 | In-State University | 2014-09-01 | 2017-03-31 | 2017-07-31 | 3 | 172500 | 230000 | Khaled El-Rayes | Tim Kell | CON | No
161 | R27-154 | In-State University | 2015-01-01 | 2017-06-30 | 2017-12-15 | 3 | 266484 | 355313 | Mohsen Issa | James Krstulovich | PVMT | No
162 | R27-155 |  | 2014-10-15 | 2016-10-14 | 2016-11-30 | 2 | 168750 | 225000 | Daniel Work | Paul Lorton | SAF | No
163 | R27-156 | In-State University | 2014-11-01 | 2017-07-31 | 2018-01-31 | 3 | 234124 | 312165 | Bassem Andrawes | Victor Veliz | BAF | No
164 | R27-157 | In-State University | 2015-01-01 | 2017-10-31 | 2018-09-30 | 4 | 160788 | 210219 | Abdolreza Osouli | Heather Shoup | PVMT | No
165 | R27-158 |  | 2015-04-23 | 2015-04-23 | 2015-04-23 | 0 |  |  |  |  | PVMT | No
166 | R27-159 |  | 2013-12-09 | 2013-12-09 | 2013-12-09 | 0 |  |  |  |  | SUS | No
167 | R27-160 |  | 2013-12-09 | 2016-06-30 | 2017-06-30 | 4 | 750000 | 1000000 | Imad Al-Qadi | Kelly Senger | SUS | No
168 | R27-161 | In-State University & Private Industry | 2014-10-01 | 2017-09-30 | 2017-12-31 | 3 | 729097 | 969729 | Imad Al-Qadi | Jim Trepanier | SUS | No
169 | R27-162 |  | 2015-01-01 | 2016-03-31 | 2017-01-31 | 2 | 108259 | 144345 | B.K. Sharma | Ronald Price | PVMT | No
170 | R27-163 | In-State University | 2015-08-16 | 2017-08-15 | 2017-08-15 | 2 | 169988 | 226651 | Nora El-Gohary | Tim Kell | CON | No
171 | R27-164 | Out-of-State University | 2015-11-01 | 2018-04-30 | 2020-12-15 | 5 | 283480 | 373806 | Xianming Shi | Rodney Lashuay | OPS | No
172 | R27-165 |  | 2016-01-01 | 2016-02-08 | 2016-02-08 | 0 | 2643 | 3524 | John Popovics | Dave Copenbarger | BAF | No
173 | R27-166 |  | 2015-06-29 | 2015-06-29 | 2015-06-29 | 0 |  |  |  |  | BAF | No
174 | R27-167 | In-State University | 2015-08-16 | 2017-02-15 | 2017-08-15 | 2 | 132297 | 176109 | Yan Qi | Kyle Armstrong | SAF | No
175 | R27-168 | In-State University | 2015-09-01 | 2018-02-28 | 2018-09-30 | 3 | 522403 | 696537 | Erol Tutumluer | Jim Trepanier | PVMT | No
176 | R27-169 | In-State University | 2015-05-16 | 2016-11-15 | 2018-08-15 | 3 | 177838 | 237117 | Jakob Eriksson | William Morgan | PLAN | No
177 | R27-170 | In-State University | 2016-01-01 | 2018-12-31 | 2019-03-31 | 3 | 398152 | 527045 | Hasan Ozer | Charles Wienrank | PVMT | No
178 | R27-171 | In-State University | 2015-12-01 | 2018-05-31 | 2019-02-28 | 3 | 268132 | 353343 | Gongkang Fu | Timothy Armbrecht | BAF | No
179 | R27-172 | Out-of-State University | 2016-01-01 | 2016-12-31 | 2018-06-30 | 2 | 120140 | 156952 | Ronald Gibbons | Mark Seppelt | ENV | No
180 | R27-173 |  | 2014-11-01 | 2014-11-01 | 2014-11-01 | 0 |  |  |  |  | PVMT | No
181 | R27-174 | In-State University | 2016-01-01 | 2018-12-31 | 2019-06-30 | 3 | 256588 | 337953 | Mohammad Hossain | Tim Peters | PVMT | No
182 | R27-175 | In-State University | 2017-01-01 | 2018-12-31 | 2019-08-31 | 3 | 700675 | 880546 | Imad Al-Qadi | Tom Zehr | PVMT | No
183 | R27-176 | In-State University | 2017-09-01 | 2018-08-31 | 2018-11-30 | 1 | 86538 | 115384 | Khaled El-Rayes | Scott Stitt | ENV | No
184 | R27-177 | In-State University | 2017-09-01 | 2019-03-31 | 2020-06-30 | 3 | 194170 | 258892 | Kouros Mohammadian | Kevin Price | PLAN | No
185 | R27-178-1 | In-State University & Out-of-State University | 2017-09-15 | 2020-09-15 | 2020-12-15 | 3 | 153125 | 200000 | Paramita Mondal | James Krstulovich | BAF | No
186 | R27-178-2 | Out-of-State University | 2017-09-15 | 2020-09-15 | 2020-12-15 | 3 | 178400 | 233700 | Riyadh Hindi | James Krstulovich | BAF | No
187 | R27-179 | Out-of-State University | 2017-09-15 | 2019-09-15 | 2019-09-15 | 2 | 200000 | 262500 | Riyadh Hindi | Douglas Dirks / Mark Thomson | CON | No
188 | R27-180 | In-State University & Out-of-State University | 2017-10-01 | 2021-06-30 | 2021-09-30 | 4 | 565626 | 750000 | Jeffery Roesler | James Krstulovich | PVMT | No
189 | R27-181 | Federal Organization | 2017-10-01 | 2020-06-30 | 2023-12-31 | 6 | 402880 | 596300 | Thomas Over | Neil VanBebber | BAF | No
190 | R27-182 | In-State University | 2018-01-01 | 2019-12-31 | 2020-06-30 | 2 | 294537 | 392716 | Erol Tutumluer | Andrew Stolba | PVMT | No
191 | R27-183-HS | In-State University & Out-of-State University | 2018-02-01 | 2021-01-31 | 2021-06-30 | 3 | 461826 | 611898 | Amanda Hohner | Douglas Dirks / James Curtis | ENV | No
192 | R27-184 |  | 2017-10-31 | 2017-10-31 | 2017-10-31 | 0 |  |  |  |  | OPS | No
193 | R27-185 |  | 2017-11-17 | 2017-11-17 | 2017-11-17 | 0 |  |  |  |  | PVMT | No
194 | R27-186 | In-State University | 2018-02-01 | 2020-01-31 | 2020-01-31 | 2 | 198479 | 262500 | Kerrie Schattler | Juan Pava | SAF | No
195 | R27-187 | Out-of-State University | 2018-02-01 | 2020-01-31 | 2018-12-31 | 1 | 159168 | 209845 | Xianming Shi | Frank Sharpe | SAF | No
196 | R27-188 | In-State University | 2018-02-01 | 2020-07-31 | 2022-11-30 | 5 | 405289 | 537551 | Timothy Stark | Michael Short | BAF | No
197 | R27-189 | In-State University | 2018-01-01 | 2019-12-31 | 2020-06-30 | 2 | 457917 | 572397 | Imad Al-Qadi | Jim Trepanier | PVMT | No
198 | R27-190 | In-State University | 2018-05-16 | 2020-11-15 | 2021-05-15 | 3 | 224998 | 299997 | Rabin Bhattarai | Michael Brownlee | ENV | No
199 | R27-191 | In-State University | 2018-08-16 | 2020-02-15 | 2021-02-15 | 3 | 143750 | 187500 | Yan Qi | Mark Bloome / Laura Shanley | OPS | No
200 | R27-192 | In-State University | 2018-05-16 | 2020-05-15 | 2020-12-15 | 3 | 281250 | 375000 | P.S. Sriraj | B J Murray / Clayton Stambaugh | PLAN | No
201 | R27-193-1 | In-State University | 2018-07-16 | 2021-07-15 | 2021-07-15 | 3 | 100176 | 125220 | Marshall Thompson | Charles Wienrank | PVMT | No
202 | R27-193-2 | In-State University | 2018-07-16 | 2021-07-15 | 2021-07-15 | 3 | 100176 | 125220 | Marshall Thompson | Charles Wienrank | PVMT | No
203 | R27-193-3 | In-State University | 2018-08-16 | 2021-08-15 | 2021-08-15 | 3 | 138964 | 198520 | Erol Tutumluer | Heather Shoup / Veniecy Pearman-Green | PVMT | No
204 | R27-193-4 | In-State University | 2018-08-16 | 2020-02-15 | 2021-01-15 | 2 | 106433 | 152047 | Jeffery Roesler | Charles Wienrank | PVMT | No
205 | R27-193-5 | In-State University | 2019-06-16 | 2021-06-15 | 2021-06-15 | 2 | 55873 | 74497 | Erol Tutumluer | Heather Shoup | PVMT | No
206 | R27-193-6 | In-State University | 2019-10-16 | 2021-03-31 | 2022-02-28 | 2 | 66992 | 89322 | Jeffery Roesler | Charles Wienrank | PVMT | No
207 | R27-194 | In-State University | 2018-07-01 | 2022-06-30 | 2026-06-30 | 8 | 928948 | 1238597 | Larry Fahnestock | Mark Shaffer | BAF | Yes
208 | R27-195 | In-State University | 2018-10-16 | 2020-05-15 | 2021-10-31 | 3 | 195581 | 260777 | Kouros Mohammadian | Matthew Daeda | OPS | No
209 | R27-196-HS | In-State University | 2018-07-01 | 2020-12-31 | 2021-06-30 | 3 | 311905 | 415873 | B.K. Sharma | Kelly Senger | PVMT | No
210 | R27-197 | In-State University | 2018-07-16 | 2021-01-15 | 2022-01-15 | 4 | 268417 | 357889 | Bassem Andrawes | Jayme Schiff / Dan Tobias | BAF | No
211 | R27-198 | In-State University | 2018-07-16 | 2021-07-15 | 2021-09-15 | 3 | 300000 | 400000 | Youssef Hashash | Heather Shoup / Joseph Angeli | BAF | No
212 | R27-199 | Private Industry | 2018-08-16 | 2020-01-15 | 2020-10-15 | 2 | 181250 | 237500 | Hyung Lee | John Senger / Douglas Dirks | CON | No
213 | R27-200 | In-State University | 2018-08-16 | 2020-08-15 | 2021-03-15 | 3 | 186686 | 248915 | Lindsay Braun | Charles Abraham | MFM | No
214 | R27-201 | In-State University | 2018-08-16 | 2020-08-15 | 2020-10-15 | 2 | 87500 | 112500 | Yan Qi | Cynthia Watters | SAF | No
215 | R27-202 | Out-of-State University | 2018-09-16 | 2021-03-15 | 2021-09-15 | 3 | 307687 | 406080 | Rajaram Bhagavathula | Bernard Griffin / Marshall Metcalf | SAF | No
216 | R27-203 | In-State University | 2019-06-01 | 2021-05-31 | 2021-05-31 | 2 | 304000 | 380000 | Imad Al-Qadi | Brian Hill / Charles Wienrank | PVMT | No
217 | R27-204 | In-State University & Out-of-State University | 2019-08-16 | 2022-02-15 | 2023-05-31 | 4 | 612048 | 767787 | Imad Al-Qadi | John Senger / Laura Heckel | PVMT | No
218 | R27-205 | In-State University | 2019-07-16 | 2022-07-15 | 2024-12-15 | 5 | 555906 | 741208 | Bassem Andrawes | Ruben Boehler | BAF | No
219 | R27-206 | Out-of-State University | 2019-08-16 | 2022-08-15 | 2023-10-31 | 4 | 338950 | 447766 | Ronald Gibbons | Marshall Metcalf / Kyle Armstrong | SAF | No
220 | R27-207 | In-State University | 2019-08-16 | 2021-08-15 | 2021-08-15 | 2 | 263750 | 347500 | Brian Deal | Christopher Schmidt | PLAN | No
221 | R27-208 | Out-of-State University | 2019-08-16 | 2021-08-15 | 2023-08-15 | 4 | 244957 | 318276 | Julie Hartell | James Krstulovich | PVMT | No
222 | R27-209 |  | 2019-05-16 | 2019-05-16 | 2019-05-16 | 0 |  |  |  |  | OPS | No
223 | R27-210 | Out-of-State University | 2019-08-16 | 2022-08-15 | 2024-05-31 | 5 | 387500 | 512500 | Jorge Macedo | Brian Laningham / Brad Hessing | BAF | No
224 | R27-211 | In-State University | 2019-08-16 | 2022-02-15 | 2022-08-15 | 3 | 161815 | 215753 | Arnab Chakraborty | Shawn Wilcockson | PLAN | No
225 | R27-212 | In-State University | 2019-09-01 | 2021-08-31 | 2022-11-30 | 3 | 134999 | 179998 | Timothy Stark | B J Murray / Heather Shoup | PLAN | No
226 | R27-213 | In-State University | 2020-08-16 | 2022-08-15 | 2023-09-30 | 3 | 178392 | 237856 | Nishant Garg | Douglas Dirks | CON | No
227 | R27-214 | In-State University | 2020-07-01 | 2022-06-30 | 2023-06-30 | 3 | 292500 | 390000 | Erol Tutumluer | Andrew Stolba | PVMT | No
228 | R27-215 | In-State University | 2020-05-16 | 2022-05-15 | 2022-05-15 | 2 | 150000 | 200000 | Kouros Mohammadian | Charles Abraham | MFM | No
229 | R27-216 | In-State University | 2020-08-16 | 2023-08-15 | 2026-04-30 | 6 | 996290 | 1245362 | Imad Al-Qadi | Brian Hill | PVMT | Yes
230 | R27-217 | In-State University | 2020-08-16 | 2021-08-15 | 2021-12-15 | 1 | 120000 | 160000 | Lewis Lehe | Charles Abraham | MFM | No
231 | R27-218 | In-State University | 2020-05-16 | 2023-05-15 | 2023-06-30 | 3 | 288750 | 385000 | P.S. Sriraj | Bill Pearsall | SAF | No
232 | R27-219 | In-State University | 2020-08-16 | 2022-08-15 | 2023-11-15 | 3 | 199998 | 262497 | Pranshoo Solanki | Douglas Dirks / James Krstulovich | CON | No
233 | R27-220 | In-State University | 2020-10-01 | 2023-09-30 | 2026-10-31 | 6 | 728633 | 963765 | Abdolreza Osouli | Heather Shoup / Neil VanBebber | BAF | Yes
234 | R27-221 | Private Industry | 2020-08-16 | 2023-02-15 | 2023-12-31 | 3 | 337202 | 445436 | Ahmad Alhasan | John Senger | PVMT | No
235 | R27-222 | In-State University & Out-of-State University | 2020-08-16 | 2022-02-15 | 2022-08-15 | 2 | 161334 | 209128 | Lindsay Braun | John Sherrill / Michael Vanderhoof | ENV | No
236 | R27-223 | Out-of-State University | 2020-08-16 | 2022-08-15 | 2022-08-15 | 2 | 62005 | 91986 | Michael Williamson | Marshall Metcalf | OPS | No
237 | R27-224 | In-State University | 2020-08-16 | 2023-08-15 | 2022-06-30 | 2 | 234932 | 313242 | Nishant Garg | Kelly Senger / Mark Shaffer | PVMT | No
238 | R27-225 | In-State University | 2020-10-01 | 2023-09-30 | 2026-06-30 | 6 | 698298 | 931064 | Larry Fahnestock | Spencer Koehler | BAF | Yes
239 | R27-226 | In-State University | 2020-08-16 | 2023-08-15 | 2025-05-15 | 5 | 269778 | 359704 | Bassem Andrawes | Robert Perkins | BAF | No
240 | R27-227 | In-State University | 2020-05-16 | 2022-05-15 | 2022-05-15 | 2 | 236000 | 295000 | Imad Al-Qadi | John Senger | PVMT | No
241 | R27-228 | In-State University & Private Industry | 2021-04-16 | 2022-10-15 | 2023-06-15 | 2 | 306059 | 399745 | Angeli Jayme | Michael Vanderhoof | PLAN | No
242 | R27-229 | In-State University | 2021-05-16 | 2023-11-15 | 2023-12-15 | 3 | 180000 | 240000 | Rabin Bhattarai | Scott Marlow | ENV | No
243 | R27-230 | In-State University | 2021-05-16 | 2023-05-15 | 2024-05-31 | 3 | 213750 | 285000 | Jeffery Roesler | Charles Wienrank | PVMT | No
244 | R27-231 | In-State University | 2021-08-16 | 2023-08-15 | 2023-08-15 | 2 | 294400 | 368000 | Uthman Mohamed Ali | Bill Eves | PVMT | No
245 | R27-232 | In-State University | 2021-07-01 | 2024-06-30 | 2024-09-30 | 3 | 249355 | 329680 | Nishant Garg | James Krstulovich / Mark Shaffer | BAF | No
246 | R27-233 | In-State University | 2021-05-16 | 2024-05-15 | 2024-05-15 | 3 | 262500 | 350000 | Ramez Hajj | Charles Wienrank / Brian Hill | PVMT | No
247 | R27-234 | In-State University | 2021-10-01 | 2024-03-31 | 2025-06-30 | 4 | 327097 | 436130 | Erol Tutumluer | Heather Shoup / Andrew Stolba | PVMT | No
248 | R27-235 | In-State University | 2021-07-01 | 2024-06-30 | 2024-06-30 | 3 | 96000 | 120000 | Marshall Thompson | James Krstulovich / Tim Peters | PVMT | No
249 | R27-236 | In-State University | 2021-07-01 | 2022-12-31 | 2022-12-31 | 2 | 178812 | 238415 | Ria Kontou | Christopher Schmidt | PLAN | No
250 | R27-237 |  | 2021-07-09 | 2021-07-09 | 2021-07-09 | 0 | 0 | 0 |  |  | OPS | No
251 | R27-238 | In-State University | 2021-08-01 | 2022-10-31 | 2024-02-29 | 3 | 162498 | 212497 | Gongkang Fu | William Beisner | BAF | No
252 | R27-239 | In-State University | 2021-08-16 | 2023-08-15 | 2024-02-15 | 2 | 375000 | 500000 | Jane Lin | Christopher Schmidt | PLAN | No
253 | R27-240 | Private Industry | 2021-09-01 | 2023-08-31 | 2023-08-31 | 2 | 199332 | 261610 | Arudi Rajagopal | Laura Shanley / Tim Peters | OPS | No
254 | R27-241 | In-State University | 2021-09-01 | 2023-08-31 | 2024-02-29 | 2 | 350000 | 462500 | Hani Mahmassani | William Viste | PLAN | No
255 | R27-242 | In-State University | 2021-08-16 | 2023-08-15 | 2023-08-15 | 2 | 112487 | 149982 | Khaled El-Rayes | Patrik Claussen | BAF | No
256 | R27-243 |  | 2021-10-06 | 2021-10-06 | 2021-10-06 | 0 |  |  |  |  | PVMT | No
257 | R27-244 | In-State University & Out-of-State University | 2021-08-16 | 2024-08-15 | 2027-03-31 | 6 | 499769 | 662192 | Ann Christine Sychterz | Brad Hessing / Scott Kassel | BAF | Yes
258 | R27-245-HS | In-State University | 2021-11-01 | 2023-10-31 | 2024-11-30 | 3 | 529982 | 662478 | Khaled El-Rayes | Benjamin Sperry | SAF | No
259 | R27-246 | In-State University | 2022-01-01 | 2023-06-30 | 2024-01-31 | 2 | 164934 | 219912 | Khaled El-Rayes | Juan Pava | SAF | No
260 | R27-247 | In-State University | 2022-07-01 | 2026-06-30 | 2026-09-30 | 4 | 600000 | 750000 | Imad Al-Qadi | John Senger | PVMT | Yes
261 | R27-248 | In-State University | 2022-07-01 | 2024-12-31 | 2025-12-31 | 4 | 484481 | 645974 | Erol Tutumluer | Andrew Stolba | PVMT | No
262 | R27-249 | In-State University | 2022-07-01 | 2025-06-30 | 2026-06-30 | 4 | 627439 | 836585 | Khaled El-Rayes | Keith Donovan | OPS | Yes
263 | R27-250 | In-State University | 2022-08-16 | 2025-02-15 | 2025-10-31 | 3 | 432354 | 540443 | Imad Al-Qadi | Kelly Senger / Brian Hill | PVMT | No
264 | R27-251 | In-State University | 2022-08-16 | 2024-08-15 | 2024-08-15 | 2 | 154493 | 198243 | Ryan Fries | Kenneth Davis / Kyle Armstrong | OPS | No
265 | R27-252 | In-State University & Out-of-State University | 2022-08-16 | 2025-02-15 | 2025-05-15 | 3 | 332051 | 418052 | Angeli Jayme | John Senger | PVMT | No
266 | R27-253 |  | 2022-09-14 | 2022-09-14 | 2022-09-14 | 0 |  |  |  |  | MFM | No
267 | R27-254 | In-State University & Out-of-State University | 2022-08-16 | 2024-08-15 | 2026-01-15 | 3 | 210742 | 273243 | Zheyong Bian | Douglas Dirks / Tim Peters | CON | No
268 | R27-255 | In-State University | 2022-08-16 | 2025-05-15 | 2025-06-15 | 3 | 202465 | 269953 | Jeffrey Matthews | Scott Hall | ENV | No
269 | R27-256 | In-State University | 2022-04-16 | 2023-04-15 | 2023-11-30 | 2 | 39705 | 52940 | Ray Benekohal | Juan Pava | SAF | No
270 | R27-257 | In-State University | 2024-01-01 | 2025-12-31 | 2026-10-31 | 3 | 211189 | 281586 | James LaFave | Mark Shaffer | BAF | Yes
271 | R27-258 | In-State University | 2023-03-01 | 2026-02-28 | 2026-02-28 | 3 | 333258 | 444344 | Alireza Talebpour | Juan Pava | SAF | No
272 | R27-259 | In-State University | 2023-07-01 | 2025-06-30 | 2025-06-30 | 2 | 246486 | 321487 | Kouros Mohammadian | Charles Abraham / Taqhi Mohammed | MFM | No
273 | R27-260 | In-State University | 2023-08-16 | 2026-12-15 | 2026-12-15 | 3 | 820005 | 1093340 | Bassem Andrawes | Mark Shaffer | BAF | Yes
274 | R27-261 |  | 2022-12-13 | 2022-12-13 | 2022-12-13 | 0 |  |  |  |  | MFM | No
275 | R27-262 | Private Industry | 2023-08-16 | 2026-08-15 | 2026-08-15 | 3 | 396486 | 521486 | Mike Prohaska | Heather Shoup / Laura Heckel | PVMT | Yes
276 | R27-263 | Private Industry | 2024-08-01 | 2026-07-31 | 2026-07-31 | 2 | 289172 | 381981 | Steve Karamihas | John Senger | PVMT | Yes
277 | R27-264 | In-State University | 2023-09-01 | 2026-02-28 | 2026-05-31 | 3 | 273245 | 360745 | Yanfeng Ouyang | John Senger | PVMT | Yes
278 | R27-265 | In-State University | 2024-01-01 | 2026-12-31 | 2026-12-31 | 3 | 406159 | 540254 | Mohsen Issa | Mark Shaffer / Yazan Alshawabkeh | BAF | Yes
279 | R27-266 | In-State University | 2024-05-16 | 2026-05-15 | 2026-12-15 | 3 | 460180 | 575225 | Imad Al-Qadi | John Senger | PVMT | Yes
280 | R27-267 | In-State University | 2024-07-01 | 2027-06-30 | 2027-06-30 | 3 | 300000 | 400000 | Ramez Hajj | Charles Wienrank / Brian Hill | PVMT | Yes
281 | R27-268 | In-State University | 2024-08-16 | 2026-08-15 | 2026-08-15 | 2 | 275250 | 367000 | Erol Tutumluer | John Senger / Andrew Stolba | PVMT | Yes
282 | R27-269 | In-State University | 2024-08-16 | 2027-08-15 | 2027-08-15 | 3 | 375000 | 500000 | Mohamad Alipour | Mark Shaffer | BAF | Yes
283 | R27-270 | In-State University | 2024-08-16 | 2026-08-15 | 2026-12-31 | 2 | 224863 | 299817 | Khaled El-Rayes | Douglas Dirks | CON | Yes
284 | R27-271 | In-State University | 2024-08-16 | 2027-02-15 | 2027-02-15 | 2 | 225000 | 300000 | Jane Lin | Benjamin Sperry | ENV | Yes
285 | R27-272 | In-State University | 2024-08-16 | 2027-08-15 | 2027-08-15 | 3 | 224828 | 299771 | Bumsoo Lee | Hannah Schmidt / Charles Abraham | MFM | Yes
286 | R27-273 | In-State University | 2024-08-16 | 2027-08-15 | 2027-08-15 | 3 | 225000 | 300000 | Sybil Derrible | Christopher Schmidt | PLAN | Yes
287 | R27-274 | In-State University | 2024-08-16 | 2026-05-15 | 2026-12-31 | 2 | 300000 | 400000 | Kouros Mohammadian | Hannah Schmidt | PLAN | Yes
288 | R27-275 | In-State University | 2025-08-16 | 2028-08-15 | 2028-08-15 | 3 | 599999 | 799999 | Youssef Hashash | Heather Shoup / Mark Shaffer | BAF | Yes
289 | R27-276 | In-State University | 2024-10-01 | 2026-09-30 | 2026-09-30 | 2 | 394957 | 481011 | Ramez Hajj | Kelly Senger | PVMT | Yes
290 | R27-277 | In-State University | 2025-01-01 | 2027-06-30 | 2027-06-30 | 2 | 390808 | 488510 | Imad Al-Qadi | Charles Wienrank | PVMT | Yes
291 | R27-278 | In-State University | 2025-08-16 | 2028-08-15 | 2028-08-15 | 3 | 733506 | 970846 | Erol Tutumluer | Andrew Stolba / Heather Shoup | PVMT | Yes
292 | R27-279 | In-State University | 2025-07-01 | 2027-06-30 | 2027-06-30 | 2 | 225000 | 300000 | Alireza Talebpour | Stephane Seck-Birhame / Victoria Barrett | SAF | Yes
293 | R27-280 | In-State University | 2025-07-01 | 2028-06-30 | 2028-06-30 | 3 | 210000 | 280000 | Ria Kontou | Jason Lange | PLAN | Yes
294 | R27-281 | In-State University | 2025-08-16 | 2028-08-15 | 2028-08-15 | 3 | 768000 | 960000 | Imad Al-Qadi | John Senger | PVMT | Yes
295 | R27-282 | Out-of-State University | 2025-08-16 | 2027-08-15 | 2027-08-15 | 2 | 152735 | 196485 | Ronald Gibbons | Greg Gurski / Keith Donovan | SAF | Yes
296 | R27-283 | Out-of-State University | 2025-08-16 | 2027-02-15 | 2027-02-15 | 2 | 133985 | 171485 | Christopher Day | Meiwu An | OPS | Yes
297 | R27-284 | Out-of-State University | 2025-08-16 | 2027-08-15 | 2027-08-15 | 2 | 321486 | 421487 | Yazan Abukhalil | Bob Innis | PLAN | Yes
298 | R27-285 | Out-of-State University | 2025-08-16 | 2027-08-15 | 2027-08-15 | 2 | 321485 | 421485 | L.D. White | Mike Miller / William Morgan | PLAN | Yes
299 | R27-286 | In-State University | 2025-08-16 | 2027-02-15 | 2027-02-15 | 2 | 149938 | 199917 | Timothy Stark | John Senger | SAF | Yes
300 | R27-287 | In-State University | 2025-08-16 | 2028-08-15 | 2028-08-15 | 3 | 396484 | 521484 | Nishant Garg | Mark Shaffer | BAF | Yes
301 | R27-288 | In-State University | 2026-03-01 | 2028-02-29 | 2028-02-29 | 2 | 523155 | 653944 | Hong Lang | John Senger | PVMT | Yes
302 | R27-289 | In-State University | 2026-05-01 | 2029-04-30 | 2029-04-30 | 1900-01-02 | 772254 | 965317 | Imad Al-Qadi | Brian Hill | PVMT | No
303 | R27-SP# (FY06-08 IGA) |  | 2005-07-01 | 2008-06-30 | 2008-06-30 | 3 | 168750 | 225000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide | No
304 | R27-SP# (FY09-11 IGA) |  | 2008-07-01 | 2011-06-30 | 2011-06-30 | 3 | 337500 | 450000 | Imad Al-Qadi | Megan Swanson | Other / Department Wide | No
305 | R27-SP01 |  | 2005-08-22 | 2006-01-31 | 2006-01-31 | 0 | 7477 | 9969 | Ray Benekohal | David Lippert | SAF | No
306 | R27-SP02 |  | 2006-01-01 | 2008-06-30 | 2008-06-30 | 2 | 18506 | 24673 | Imad Al-Qadi | David Lippert | BAF | No
307 | R27-SP03 |  | 2006-04-17 | 2006-06-30 | 2006-06-30 | 0 | 4175 | 5567 | Imad Al-Qadi | David Lippert | PVMT | No
308 | R27-SP04 |  | 2007-01-01 | 2007-06-30 | 2007-06-30 | 0 | 34136 | 45515 | Yanfeng Ouyang | Joseph Hill | OPS | No
309 | R27-SP05 |  | 2007-04-01 | 2007-06-30 | 2007-06-30 | 0 | 9923 | 13231 | Imad Al-Qadi | David Lippert | PVMT | No
310 | R27-SP06 |  | 2006-07-01 | 2008-06-30 | 2008-06-30 | 2 | 15000 | 20000 | Imad Al-Qadi | David Lippert | PVMT | No
311 | R27-SP07 |  | 2007-09-12 | 2008-06-30 | 2008-06-30 | 1 | 20500 | 27333 | Imad Al-Qadi | David Lippert | PVMT | No
312 | R27-SP08 |  | 2007-10-01 | 2007-12-31 | 2007-12-31 | 0 | 47336 | 63115 | R. Sreenivas | Mark Kinkaid | MFM | No
313 | R27-SP09 |  | 2008-02-16 | 2008-06-30 | 2008-06-30 | 0 | 16248 | 21664 | Imad Al-Qadi | David Lippert | PVMT | No
314 | R27-SP10 |  | 2008-04-15 | 2008-06-30 | 2008-06-30 | 0 | 24125 | 32167 | James Hall | Kevin Burke | OPS | No
315 | R27-SP11 |  | 2008-07-01 | 2008-09-30 | 2008-09-30 | 0 | 10000 | 13333 | Jeffery Roesler | Mark Gawedzinski | PVMT | No
316 | R27-SP12 |  | 2008-09-10 | 2008-12-31 | 2009-05-15 | 1 | 15210 | 20280 | Bassem Andrawes | James Klein | BAF | No
317 | R27-SP13 |  | 2009-04-01 | 2009-12-31 | 2010-06-30 | 1 | 33750 | 45000 | Imad Al-Qadi | LaDonna Rowden | PVMT | No
318 | R27-SP14 |  | 2009-05-01 | 2009-08-15 | 2009-09-30 | 0 | 20376 | 27168 | Liang Liu | Kelly Senger | PVMT | No
319 | R27-SP15 |  | 2009-11-01 | 2010-06-30 | 2010-09-30 | 1 | 20259 | 27012 | Thomas O'Rourke | Dave Johnson | OPS | No
320 | R27-SP16 |  | 2009-07-16 | 2009-12-31 | 2010-08-15 | 1 | 14920 | 19893 | Youssef Hashash | Terri Peterson | Other / Department Wide | No
321 | R27-SP17 |  | 2009-07-16 | 2010-03-15 | 2010-07-31 | 1 | 17556 | 23408 | Imad Al-Qadi | Tom Zehr | PVMT | No
322 | R27-SP18 |  | 2011-08-16 | 2012-02-15 | 2012-06-30 | 1 | 22500 | 30000 | Barry Dempsey | Todd Hill | ENV | No
323 | R27-SP19 |  | 2011-12-16 | 2012-06-15 | 2012-06-15 | 0 | 22500 | 30000 | Hasan Ozer | David Lippert | PVMT | No
324 | R27-SP20 |  | 2012-04-16 | 2012-09-15 | 2012-12-15 | 1 | 22500 | 30000 | Ray Benekohal | Kyle Armstrong | OPS | No
325 | R27-SP21 |  | 2012-06-01 | 2012-11-30 | 2013-04-30 | 1 | 19143 | 25524 | Scott Peters | Walt Zyznieuski | ENV | No
326 | R27-SP22 |  | 2013-03-01 | 2013-08-31 | 2014-04-30 | 1 | 19050 | 25400 | James Hall | William Morgan | PLAN | No
327 | R27-SP23 |  | 2013-09-16 | 2014-03-15 | 2014-07-31 | 1 | 22500 | 30000 | Art Schmidt | Thomas Winkelman | Other / Department Wide | No
328 | R27-SP24 |  | 2013-08-16 | 2014-02-15 | 2014-02-15 | 1 | 22500 | 30000 | Daniel Work | Paul Lorton | SAF | No
329 | R27-SP25 |  | 2013-11-01 | 2014-04-30 | 2014-04-30 | 0 | 22500 | 30000 | Yanfeng Ouyang | Mike Gillette | SAF | No
330 | R27-SP26-C |  | 2014-03-01 | 2014-08-28 | 2014-11-30 | 1 | 22500 | 30000 | Jim Meister | Tim Peters | OPS | No
331 | R27-SP27 |  | 2014-06-01 | 2015-01-31 | 2015-02-28 | 1 | 22500 | 30000 | Enad Mahmoud | Sheila Beshears | PVMT | No
332 | R27-SP28 |  | 2014-10-01 | 2015-05-31 | 2016-02-15 | 1 | 22500 | 30000 | Hasan Ozer | Ronald Price | SUS | No
333 | R27-SP29 |  | 2015-01-01 | 2015-10-31 | 2015-10-31 | 1 | 22500 | 30000 | Mohammad Hossain | Matt Mueller | PVMT | No
334 | R27-SP30 |  | 2015-09-16 | 2016-07-15 | 2016-10-15 | 1 | 22500 | 30000 | Yanfeng Ouyang | Kyle Armstrong | SAF | No
335 | R27-SP31 |  | 2016-08-16 | 2017-05-15 | 2017-06-30 | 1 | 22500 | 30000 | Hasan Ozer | Tom Zehr | PVMT | No
336 | R27-SP32 |  | 2016-08-16 | 2017-04-15 | 2017-04-15 | 1 | 22350 | 30000 | Kerrie Schattler | Paul Lorton | SAF | No
337 | R27-SP33 |  | 2016-08-16 | 2017-04-15 | 2017-04-15 | 1 | 22500 | 30000 | Yanfeng Ouyang | Paul Lorton | SAF | No
338 | R27-SP34 | In-State University | 2017-05-01 | 2017-12-31 | 2017-12-31 | 1 | 36813 | 46029 | Hasan Ozer | Jim Trepanier | PVMT | No
339 | R27-SP35 | In-State University | 2017-05-15 | 2018-01-31 | 2018-04-30 | 1 | 29198 | 38930 | Bassem Andrawes | Jayme Schiff | PVMT | No
340 | R27-SP36 | Private Industry | 2017-09-01 | 2018-05-31 | 2018-05-31 | 1 | 27000 | 36000 | Zina Eluri | John Senger | PVMT | No
341 | R27-SP37-C | In-State University | 2017-09-15 | 2018-06-30 | 2018-08-31 | 1 | 26990 | 35987 | Hadi Meidani | Kyle Armstrong | SAF | No
342 | R27-SP38 | In-State University | 2019-02-01 | 2019-10-31 | 2019-10-31 | 1 | 27000 | 36000 | Erol Tutumluer | Heather Shoup | PVMT | No
343 | R27-SP39 | In-State University | 2019-03-16 | 2019-09-15 | 2019-09-15 | 1 | 27000 | 36000 | Stacey DeLorenzo | Jon McCormick / Marshall Metcalf | SAF | No
344 | R27-SP40 | In-State University | 2019-04-01 | 2019-12-31 | 2020-04-30 | 1 | 39500 | 48500 | Yan Qi | Juan Pava / Adam Gabany | SAF | No
345 | R27-SP41 | In-State University | 2019-09-01 | 2019-11-30 | 2020-01-31 | 0 | 39500 | 48500 | Mohammad Hossain | Marshall Metcalf | OPS | No
346 | R27-SP42 | In-State University | 2019-11-16 | 2020-08-15 | 2020-08-15 | 1 | 27000 | 36000 | BF Spencer | Robert Perkins | BAF | No
347 | R27-SP43 | In-State University | 2020-05-16 | 2021-05-15 | 2021-06-30 | 1 | 27000 | 36000 | Erol Tutumluer | Michael Short | PVMT | No
348 | R27-SP44 | In-State University | 2020-05-01 | 2021-01-31 | 2021-02-28 | 1 | 27000 | 36000 | Ramez Hajj | Laura Shanley | OPS | No
349 | R27-SP45 | In-State University | 2020-11-16 | 2021-08-15 | 2021-09-15 | 1 | 27000 | 36000 | Yanfeng Ouyang | Charles Abraham / Jessica Hector-Hsu | MFM | No
350 | R27-SP46 | In-State University | 2021-01-01 | 2021-09-30 | 2021-09-30 | 1 | 39500 | 48500 | Gongkang Fu | Travis Lobmaster / William Morgan | PLAN | No
351 | R27-SP47 | In-State University | 2021-04-16 | 2022-01-15 | 2022-02-28 | 1 | 26997 | 35997 | Khaled El-Rayes | Laura Shanley | OPS | No
352 | R27-SP48 | In-State University | 2021-05-01 | 2022-01-31 | 2022-02-28 | 1 | 27000 | 36000 | Jeffery Roesler | Charles Wienrank | PVMT | No
353 | R27-SP49 | In-State University | 2021-08-16 | 2022-05-16 | 2022-05-16 | 1 | 39500 | 48500 | Matthew Gombeda | Jayme Schiff / Dan Tobias | BAF | No
354 | R27-SP50 | In-State University | 2021-09-01 | 2022-05-31 | 2022-05-31 | 1 | 27000 | 36000 | Marcelo Garcia | Timothy Armbrecht / Dan Brydl | BAF | No
355 | R27-SP51-HS | In-State University | 2021-09-01 | 2022-03-31 | 2022-06-30 | 1 | 28800 | 36000 | Imad Al-Qadi | Issam Rayyan | SAF | No
356 | R27-SP52 | In-State University | 2022-05-16 | 2023-02-15 | 2023-05-15 | 1 | 39500 | 48500 | Matthew Gombeda | Curt Evoy / Del Reeves | BAF | No
357 | R27-SP53 | In-State University | 2022-05-16 | 2023-02-15 | 2023-04-15 | 1 | 27000 | 36000 | Yanfeng Ouyang | Charles Abraham / Cemal Ayvalik | MFM | No
358 | R27-SP54 |  | 2023-01-11 | 2023-01-11 | 2023-01-11 | 0 |  |  |  |  | OPS | No
359 | R27-SP55 | In-State University | 2023-06-01 | 2024-02-29 | 2024-05-31 | 1 | 27000 | 36000 | Yanfeng Ouyang | Sean Martschinke | OPS | No
360 | R27-SP56 | In-State University | 2023-05-01 | 2023-10-31 | 2023-10-31 | 1 | 28800 | 36000 | Imad Al-Qadi | John Senger | PVMT | No
361 | R27-SP57 | In-State University | 2023-06-01 | 2024-02-29 | 2024-06-30 | 1 | 37814 | 46814 | Reggie Greenwood | Charles Abraham / Zoe Keller | MFM | No
362 | R27-SP58 | In-State University | 2023-04-01 | 2023-12-31 | 2023-12-31 | 1 | 27000 | 36000 | Yanfeng Ouyang | Charles Abraham / Zoe Keller | MFM | No
363 | R27-SP59 | In-State University | 2023-04-16 | 2024-01-15 | 2024-05-31 | 1 | 27000 | 36000 | Ramez Hajj | Douglas Dirks | CON | No
364 | R27-SP60 |  | 2023-01-19 | 2023-01-19 | 2023-01-19 | 0 |  |  |  |  | CON | No
365 | R27-SP61 | In-State University | 2023-05-16 | 2024-02-15 | 2024-02-15 | 1 | 27000 | 36000 | Geoffrey Pociask | Kimberly Burkwald / Shawn Wilcockson | ENV | No
366 | R27-SP62 | In-State University | 2023-07-01 | 2024-03-31 | 2024-03-31 | 1 | 27000 | 36000 | Mohsen Issa | Mark Shaffer | BAF | No
367 | R27-SP63 | In-State University | 2023-04-01 | 2023-12-31 | 2023-12-31 | 1 | 27000 | 36000 | Ramez Hajj | Kelly Senger | PVMT | No
368 | R27-SP64 | In-State University | 2023-05-16 | 2024-02-15 | 2024-02-15 | 1 | 27000 | 36000 | Wendy Schelsky | Kimberly Burkwald / Shawn Wilcockson | ENV | No
369 | R27-SP65 | In-State University | 2023-11-01 | 2024-07-31 | 2024-07-31 | 1 | 27000 | 36000 | Yanfeng Ouyang | Kyle Armstrong | OPS | No
370 | R27-SP66 | In-State University | 2024-01-16 | 2024-10-15 | 2024-10-15 | 1 | 67036 | 83286 | Yasser Khodair | Mark Shaffer | BAF | No
371 | R27-SP67 | In-State University | 2024-08-16 | 2025-05-15 | 2025-05-15 | 1 | 48733 | 64977 | Dusty Swedberg | Vincent Hamer | ENV | No
372 | R27-SP68 | In-State University | 2024-09-01 | 2025-05-31 | 2025-11-30 | 1 | 48750 | 65000 | Jason Robinson | Kimberly Burkwald | ENV | No
373 | R27-SP69 | In-State University | 2024-10-01 | 2025-06-30 | 2025-06-30 | 1 | 48750 | 65000 | David Zaya | Jake Vancil | ENV | No
374 | R27-SP70 | In-State University | 2024-10-01 | 2025-06-30 | 2025-06-30 | 1 | 43400 | 57867 | Kirk Stodola | Bradley Daugherty | ENV | No
375 | R27-SP71 | In-State University | 2024-02-16 | 2024-11-15 | 2024-12-15 | 1 | 48750 | 65000 | Alireza Talebpour | Stephane Seck-Birhame / Victoria Barrett | SAF | No
376 | R27-SP72 | In-State University | 2024-04-16 | 2025-01-15 | 2025-10-31 | 2 | 48750 | 65000 | Jeffery Roesler | John Senger | PVMT | No
377 | R27-SP73 |  | 2025-01-23 | 2025-01-23 | 2025-01-23 | 0 | 0 | 0 |  |  | ENV | No
378 | R27-SP74 | In-State University | 2024-11-16 | 2025-08-15 | 2025-09-30 | 1 | 48750 | 65000 | Jeffery Roesler | Charles Wienrank | PVMT | No
379 | R27-SP75 | In-State University | 2025-06-01 | 2026-02-28 | 2026-08-31 | 1 | 48750 | 65000 | Ramez Hajj | John Senger | PVMT | Yes
380 | R27-SP76 | In-State University | 2025-06-01 | 2026-02-28 | 2026-05-31 | 1 | 48750 | 65000 | Yanfeng Ouyang | Juan Pava | SAF | Yes
381 | R27-SP77 | In-State University | 2025-09-16 | 2026-06-15 | 2026-09-15 | 1 | 48748 | 64997 | Mohamad Alipour | Mark Shaffer | BAF | Yes
382 | R27-SP78 | In-State University | 2025-09-01 | 2026-05-31 | 2026-08-31 | 1 | 69698 | 85948 | Mohammad Hossain | Charles Wienrank / Xinyu Sun | PVMT | Yes
383 | R27-SP79 | In-State University | 2025-10-16 | 2026-07-15 | 2026-07-15 | 1 | 48750 | 65000 | Dan Salas | Kimberly Burkwald | ENV | Yes
384 | R27-SP80 | In-State University | 2026-04-01 | 2026-12-31 | 2026-12-31 | 1 | 48750 | 65000 | Nishant Garg | Andrew Stolba | PVMT | No
385 | R27-SP81 | In-State University | 2026-03-01 | 2026-11-30 | 2026-11-30 | 1 | 48750 | 65000 | Yanfeng Ouyang | Meiwu An / Greg Gurski | OPS | No
386 | R27-SP83 | In-State University | 2026-03-01 | 2026-11-30 | 2026-11-30 | 1 | 48750 | 65000 | Erol Tutumluer | Andrew Stolba | PVMT | Yes
387 | R27-ET2 (FY18-24 IGA) | In-State University | 2017-07-01 | 2020-06-30 | 2024-06-30 | 7 | 1135000 | 1135000 | Kristi Anderson | John Senger | Other / Department Wide | No
388 | R27-PC (FY18-24 IGA) | In-State University | 2017-07-01 | 2020-06-30 | 2024-06-30 | 7 | 2321525 | 2321525 | Kristi Anderson | John Senger | Other / Department Wide | No
389 | R27-RDI (FY18-24 IGA) | In-State University | 2017-07-01 | 2020-06-30 | 2024-06-30 | 7 | 772000 | 772000 | Kristi Anderson | John Senger | Other / Department Wide | No
390 | R27-ET2 (FY25-30 IGA) | In-State University | 2024-07-01 | 2030-06-30 | 2030-06-30 | 6 | 1095000 | 1095000 | Kristi Anderson | John Senger | Other / Department Wide | Yes
391 | R27-PC (FY25-30 IGA) | In-State University | 2024-07-01 | 2030-06-30 | 2030-06-30 | 6 | 2600000 | 2600000 | Kristi Anderson | John Senger | Other / Department Wide | Yes
392 | R27-RDI (FY25-30 IGA) | In-State University | 2024-07-01 | 2030-06-30 | 2030-06-30 | 6 | 660000 | 660000 | Kristi Anderson | John Senger | Other / Department Wide | Yes
393 | R60-ADMIN (FY25-30 IGA) | In-State University | 2024-07-01 | 2030-06-30 | 2030-06-30 | 6 | 3900000 | 3900000 | Kristi Anderson | John Senger | Other / Department Wide | Yes
394 | R27-ALS | In-State University | 2020-08-01 | 2022-01-31 | 2024-08-31 | 4 | 761429 | 951786 | Imad Al-Qadi | John Senger | Other / Department Wide | No
395 | R60-ADMIN (FY06-08 IGA) | In-State University | 2005-07-01 | 2008-06-30 | 2008-06-30 | 3 | 780000 | 1040000 | Kristi Anderson | Megan Swanson | Other / Department Wide | No
396 | R60-ADMIN (FY09-11 IGA) | In-State University | 2008-07-01 | 2011-06-30 | 2011-06-30 | 3 | 995000 | 995000 | Kristi Anderson | Megan Swanson | Other / Department Wide | No
397 | R60-ADMIN (FY12-17 IGA) | In-State University | 2011-07-01 | 2017-06-30 | 2017-06-30 | 6 | 2700000 | 2700000 | Kristi Anderson | Megan Swanson | Other / Department Wide | No
398 | R60-ADMIN (FY18-24 IGA) | In-State University | 2017-07-01 | 2020-06-30 | 2024-06-30 | 7 | 3290000 | 3290000 | Kristi Anderson | John Senger | Other / Department Wide | No
399 | R28-001 |  | 2005-07-01 | 2008-06-30 | 2008-06-30 | 3 | 95135 | 126846 | Marshall Thompson | David Lippert | PVMT | No
400 | R28-002 |  | 2008-01-01 | 2008-08-31 | 2008-08-31 | 1 | 31500 | 42000 | Samuel Carpenter | Amy Schutzbach | PVMT | No
401 | R39-001 |  | 2002-07-01 | 2006-06-30 | 2006-12-31 | 5 | 127514 | 170020 | Samuel Carpenter | Amy Schutzbach | PVMT | No
402 | R39-002 |  | 2004-08-01 | 2008-06-30 | 2008-08-31 | 4 | 63614 | 84818 | Erol Tutumluer | Charles Wienrank | PVMT | No
403 | R43 |  | 2005-07-01 | 2008-06-30 | 2008-06-30 | 3 | 333473 | 444631 | Ray Benekohal | Yogesh Gautam | OPS | No
404 | R44 |  | 2003-07-01 | 2007-09-15 | 2007-09-15 | 4 | 142646 | 190196 | David Lange | James Krstulovich | PVMT | No
405 | R53 |  | 2005-07-01 | 2006-06-30 | 2006-06-30 | 1 | 59176 | 78902 | Leslie Struble | Patricia Broers | PVMT | No
406 | R54 |  | 2005-07-01 | 2007-12-31 | 2008-09-30 | 3 | 209124 | 278832 | Dan Kuchma | Kevin Riechers | BAF | No
407 | R55 |  | 2005-07-01 | 2008-06-30 | 2008-12-31 | 4 | 520942 | 694590 | Imad Al-Qadi | Jim Trepanier | PVMT | No
408 | R56 |  | 2005-07-01 | 2007-06-30 | 2008-06-30 | 3 | 231821 | 309095 | Ray Benekohal | Priscilla Tobias | SAF | No
409 | R57 |  | 2005-09-01 | 2008-06-30 | 2008-12-31 | 3 | 226361 | 301814 | Jeffery Roesler | Amy Schutzbach | PVMT | No
410 | R58 |  | 2005-07-01 | 2008-06-30 | 2008-12-31 | 4 | 232192 | 309589 | William Buttlar | Joe Vespa | PVMT | No
411 | R59 |  | 2006-01-01 | 2008-12-31 | 2008-12-31 | 3 | 220420 | 293893 | Imad Al-Qadi | Mark Gawedzinski | PVMT | No

## Student
| Proj # | Name | Proj Start | Proj End | TAG | Active
0 | R27-001 | Characterization of IL Aggregates for Subgrade Replacement and Subbase | 2006-01-01 | 2009-06-30 | PVMT | No
1 | R27-002 | Nighttime Construction: Evaluation of Lighting Glare for Highway Construction in IL | 2006-01-01 | 2007-12-31 | SAF | No
2 | R27-003 | Design and Concrete Material Requirements for Ultra-Thin Whitetopping Procedures | 2006-01-01 | 2008-03-31 | PVMT | No
3 | R27-004 | Radiation Detection Pilot Program | 2006-01-01 | 2007-06-30 | OPS | No
4 | R27-005 | Bus-Only Shoulder Riding | 2007-08-16 | 2009-01-31 | MFM | No
5 | R27-006 | Illinois StreamStats | 2006-03-01 | 2008-06-30 | BAF | No
6 | R27-007 | Update the IL Carbon Monoxide Screen for Intersections Model (COSIM) | 2007-02-01 | 2007-08-31 | ENV | No
7 | R27-008 | Hot Mix Asphalt (HMA) Sampling | 2006-06-01 | 2007-06-30 | PVMT | No
8 | R27-009 | I-39 Kishwaukee Bridge Monitoring | 2006-07-01 | 2008-06-30 | BAF | No
9 | R27-010 | Mobile Source Air Toxics (MSAT): A Midwest Peer Exchange | 2006-07-01 | 2007-02-28 | ENV | No
10 | R27-011 | Determination of Usable Residual Asphalt Binder in RAP | 2006-07-01 | 2008-06-30 | PVMT | No
11 | R27-012 | Cold In-Place Recycling with Asphalt Products (CIRwAP) | 2006-07-01 | 2008-08-31 | PVMT | No
12 | R27-013 | Update Condition Rating Survey (CRS) Calculation/Prediction Models | 2006-07-01 | 2007-08-31 | PLAN | No
13 | R27-014 | Commercial Vehicle Information Systems and Networks (CVISN) | 2006-09-06 | 2007-03-31 | PLAN | No
14 | R27-015 | Regional Warehouse Trip Production | 2007-01-01 | 2008-07-31 | MFM | No
15 | R27-016 | Truck Parking Facilities Program Design | 2007-01-01 | 2008-03-31 | MFM | No
16 | R27-017 | Effectiveness of Transit Strategies Targeting Elderly People | 2006-07-01 | 2008-11-30 | MFM | No
17 | R27-018 | Crash Data Analysis and Engineering Solutions for Local Agencies | 2006-07-01 | 2008-12-31 | SAF | No
18 | R27-019 | Pier Scour Prediction in Cohesive Soils: Use of EFA-SRICOS Method in IL | 2006-08-01 | 2010-06-30 | BAF | No
19 | R27-020 | Develop Safety Performance Functions (SPF) for Illinois | 2007-01-01 | 2008-12-31 | SAF | No
20 | R27-021 | Alternative Intersections: Roundabout Evaluation and Design | 2007-01-01 | 2008-08-31 | SAF | No
21 | R27-022 | Regional Data Archiving and Management for Northeast Illinois | 2007-04-01 | 2008-08-31 | OPS | No
22 | R27-023 | Evaluation of HMA Overlays in Illinois | 2007-07-01 | 2008-08-31 | PLAN | No
23 | R27-024 | Evaluation/Modification of IDOT Foundation Piling Design and Construction Policy | 2007-01-01 | 2009-03-31 | BAF | No
24 | R27-025 | Modification of IDOT Integral Abutment Design Limitations and Details | 2007-01-01 | 2009-03-31 | BAF | No
25 | R27-026 | Free-Cutting Brass Breakaway Couplings | 2007-04-01 | 2009-04-30 | BAF | No
26 | R27-027 | Expansive Characteristics of Reclaimed Asphalt | 2007-02-01 | 2009-04-30 | PVMT | No
27 | R27-028-T1 | Conference and Training Support | 2007-09-01 | 2011-06-30 | Other / Department Wide | No
28 | R27-028-T2 | Utah LTAP GIS Software Replication/ Training in IL | 2007-11-01 | 2008-10-31 | Other / Department Wide | No
29 | R27-028-T3 | 8th International Conference on Bearing Capacity of Roads | 2009-05-01 | 2009-09-30 | PVMT | No
30 | R27-029 | Particulate Matter 2.5 and 10 Hot Spot Analysis: A Midwest Peer Exchange | 2007-07-01 | 2008-06-30 | ENV | No
31 | R27-030 | Evaluation of 3-D Laser Scanning for Construction Applications | 2007-09-16 | 2009-08-15 | CON | No
32 | R27-031 | Wind Powered Electrical Systems: Highway Rest Areas and Weigh Stations and Team Section Buildings | 2007-08-01 | 2008-12-31 | OPS | No
33 | R27-032 | Rolling Lane Closures | 2007-09-01 | 2008-12-31 | OPS | No
34 | R27-033 | Queue and Users' Cost in Highway Work Zones | 2007-10-01 | 2010-08-31 | OPS | No
35 | R27-034 | Pavement Program Planning Process Based on Benefit-Cost Analysis | 2007-10-01 | 2009-04-30 | PLAN | No
36 | R27-035 | Simple Cost Effective Scour Sensor | 2007-08-01 | 2008-10-31 | BAF | No
37 | R27-036 | Transfer and Development Length of Prestressing Tendons in Full-scale AASHTO Prestressed Concrete Girders using Self-Consolidating Concrete | 2007-08-01 | 2008-09-30 | BAF | No
38 | R27-037 | Impact of High RAP Content on Pavement Structural Performance | 2008-07-01 | 2011-12-31 | PVMT | No
39 | R27-038 | Development of an Improved Specification for Maximum Plastic Concrete Temperatures | 2007-09-01 | 2010-06-30 | PVMT | No
40 | R27-039 | Context Sensitive Solutions Online Training Course Development | 2008-02-16 | 2008-09-30 | PLAN | No
41 | R27-040 | Safety Impacts of Highway Shoulder Attributes in Illinois | 2008-01-01 | 2010-09-30 | SAF | No
42 | R27-041 | Performance of I-57 Recycled Concrete Pavement | 2008-01-01 | 2008-11-30 | PVMT | No
43 | R27-042 | Thin Quiet Long-Lasting High Friction Surface Layer | 2008-03-07 | 2013-03-31 | PVMT | No
44 | R27-043 | Utah LTAP GIS Software Conversion and Training for IL Use | 2007-11-01 | 2008-10-31 | Other / Department Wide | No
45 | R27-044-T1 | IDOT Pavement Design Course Development | 2012-06-01 | 2013-07-31 | PVMT | No
46 | R27-045-T1 | Evaluation of 3-D Laser Scanning Equipment | 2013-10-01 | 2018-06-30 | CON | No
47 | R27-047 | Illinois Tribunal Workshop | 2008-05-13 | 2008-05-13 | ENV | No
48 | R27-048 | Travel Demand Modeling for Small & Medium Size MPOs in Illinois | 2009-01-01 | 2011-06-30 | PLAN | No
49 | R27-049 | Documentation of Contract Quantities Training | 2008-05-01 | 2010-06-30 | CON | No
50 | R27-050 | Trip Chaining Behavior of Senior Travelers & Applications to Public Transportation Planning | 2008-08-16 | 2010-12-31 | MFM | No
51 | R27-051 | Guidelines, Site Selection, and Design for Implementing Truck Parking/Rest Facilities in Chicago's South Suburbs | 2008-11-01 | 2010-09-30 | MFM | No
52 | R27-052 | Studying & Minimizing Traffic Related Work Zone Crashes in Illinois | 2008-09-16 | 2010-09-15 | SAF | No
53 | R27-053 | Roadway Lighting Evaluation Tools | 2008-09-04 | 2008-09-04 | SAF | No
54 | R27-054 | Storm Water Pollution, Erosion & Sediment Control Products Demonstration & Training Center | 2009-01-01 | 2012-12-31 | ENV | No
55 | R27-055 | Instrumentation & Monitoring of Extreme Integral Abutment Bridges in Illinois | 2008-08-16 | 2012-03-31 | BAF | No
56 | R27-056 | Transfer & Development Lengths in Prestressed Self-Consolidating Concrete Bridge Box & I-Girders | 2008-07-16 | 2011-02-28 | BAF | No
57 | R27-057 | Superiority & Constructability of Fibrous Additives for Bridge Deck Overlays | 2009-01-01 | 2011-12-31 | BAF | No
58 | R27-058 | Evaluation of Wireless Detection Systems at RR Crossings & Signalized Intersections | 2008-07-01 | 2011-03-31 | OPS | No
59 | R27-059 | Evaluation of Performance of Solar Powered Flashing Beacons | 2008-07-01 | 2011-03-31 | OPS | No
60 | R27-060 | Mechanistic-Empirical Design, Implementation & Monitoring for Flexible Pavements | 2008-07-01 | 2014-06-30 | PVMT | No
61 | R27-061 | Mechanistic-Empirical Design, Implementation & Monitoring for Rigid Pavements | 2009-01-01 | 2014-08-31 | PVMT | No
62 | R27-062 | Material Quality Testing Risk Assessment & Multi-State Peer Exchange | 2009-02-01 | 2010-12-31 | PVMT | No
63 | R27-063 | Evaluation of the Long-Term Durability of Joints Cut Using Early-Entry Saws on Rigid Pavements | 2008-11-01 | 2010-09-30 | PVMT | No
64 | R27-064 | Development of a Highway Incident Management Operational & Training Guide | 2009-07-01 | 2011-06-30 | OPS | No
65 | R27-065 | Safety Analyst Software | 2009-09-11 | 2009-09-11 | SAF | No
66 | R27-066 | Effectiveness of Innovative Speed Enforcement Techniques in Illinois | 2009-11-01 | 2012-10-31 | SAF | No
67 | R27-067 | National Safety Performance (SPF) Summit | 2009-01-01 | 2009-12-31 | SAF | No
68 | R27-068 | Midwest Transportation Air Quality Summit | 2009-03-16 | 2009-12-31 | ENV | No
69 | R27-069 | Improved Design for Driven Piles Based on a Pile Load Test Program in Illinois | 2009-01-01 | 2012-06-30 | BAF | No
70 | R27-070 | Calibration & Refinement of Illinois' Earthquake Resisting System Bridge Design Methodology | 2009-01-01 | 2012-12-31 | BAF | No
71 | R27-071 | Field Implementation and Evaluation of the Simple Cost-Effective Scour Sensor | 2009-02-01 | 2010-06-30 | BAF | No
72 | R27-072 | Rolling Lane Closures - Phase II | 2009-01-16 | 2010-01-31 | OPS | No
73 | R27-073 | Distance Technology Transfer Course Content Development | 2009-02-01 | 2013-03-31 | Other / Department Wide | No
74 | R27-074 | Green Friendly Best Management Practices (BMP) for Interstate Rest Areas | 2010-01-01 | 2010-12-31 | ENV | No
75 | R27-075 | Clearview Font in Traffic Signs: Assessing IDOT Experiences and Needs | 2010-04-01 | 2012-03-31 | OPS | No
76 | R27-076 | LED Roadway Lighting Evaluation and Field Testing | 2009-11-01 | 2012-03-31 | OPS | No
77 | R27-077 | Evaluating Pavement Markings on Portland Cement Concrete (PCC) & Various Asphalt Surfaces | 2009-12-01 | 2013-11-30 | PVMT | No
78 | R27-078 | Evaluating the Effects of Various Asphalt Binder Additives/Modifiers on Moisture Sensitivity in HMA | 2010-02-16 | 2013-12-31 | PVMT | No
79 | R27-079 | Designing, Producing & Constructing Fine-Graded Hot Mix Asphalt (HMA) on IL Roadways | 2009-08-16 | 2013-12-31 | PVMT | No
80 | R27-080 | Fatigue Testing of Brass Breakaway Couplings | 2009-07-01 | 2010-12-31 | BAF | No
81 | R27-081 | Field Performance Evaluations of IL Aggregates for Subgrade Replacement & Subbase - Phase II | 2010-01-01 | 2011-12-31 | BAF | No
82 | R27-082 | Strength of Bridge Wood Pilings Retrofits for Moment Resistance | 2009-08-16 | 2012-08-15 | BAF | No
83 | R27-083 | Good Movement Study in IL: Applications to Freight Transportation & Logistics | 2010-01-01 | 2011-08-15 | PLAN | No
84 | R27-084 | Develop Travel Reliability Inventory for Highway Networks | 2010-04-01 | 2011-06-30 | PLAN | No
85 | R27-085 | R.E.'s Materials Mgmt. Training | 2010-03-03 | 2010-03-03 | PVMT | No
86 | R27-086 | An Expert Systems Approach to Highway Construction Scheduling | 2010-07-01 | 2011-06-30 | CON | No
87 | R27-087 | Implementing Pavement Management Systems for Local Agencies | 2010-05-01 | 2011-08-31 | PLAN | No
88 | R27-088 | Bridge Decks: Mitigation of Cracking & Increased Durability | 2010-05-16 | 2013-06-15 | BAF | No
89 | R27-089 | Illinois Highway Safety Manual Workshop | 2010-08-16 | 2011-06-30 | SAF | No
90 | R27-090 | Investigation of Contributing Factors of Wrong-Way Driving on Freeways | 2010-07-01 | 2015-09-30 | SAF | No
91 | R27-091 | Evaluating of Traffic Flow Monitoring Technologies: Cicero-Midway Smart Corridor Case Study | 2010-01-01 | 2010-12-31 | OPS | No
92 | R27-092 | Engineering Software Review: MicroStation vs. AutoCAD | 2009-11-13 | 2009-11-13 | Other / Department Wide | No
93 | R27-093 | Transportation Conformity Particulate Matter Hot-Spot Air Quality Modeling | 2010-11-01 | 2013-06-30 | ENV | No
94 | R27-094 | Performance Evaluation of Snow & Ice Plows | 2011-09-01 | 2015-11-30 | OPS | No
95 | R27-095 | Field Evaluation of Smart Sensor Vehicle Detectors at Intersections & RR Crossings | 2010-08-16 | 2014-12-31 | OPS | No
96 | R27-096 | Pedestrian/Bicyclist Warning Devices & Signs at Hwy.-Rail & Pathway-Rail Grade Crossings | 2011-01-01 | 2012-12-31 | OPS | No
97 | R27-097 | Evaluation of Flashing Yellow Arrows (FYA) for Protected/Permissive Left Turn (PPLT) Control | 2010-11-01 | 2016-03-31 | SAF | No
98 | R27-098 | Evaluation of Concrete Cylinder Match Curing & Evaluation of 4" x 8" Cylinders | 2010-08-16 | 2012-06-30 | BAF | No
99 | R27-099 | Improvement for Determining the Axial Capacity of Drilled Shafts in Shale in Illinois | 2011-11-01 | 2013-04-30 | BAF | No
100 | R27-100 | Best Practices for Implementation of Tack Coat TRP Recommendations | 2010-09-16 | 2013-03-15 | PVMT | No
101 | R27-101 | Funding Set Aside for B.S. & M.S. Students | 2011-01-01 | 2017-06-30 | Other / Department Wide | No
102 | R27-102 | Installation & Performance Testing of Ditch Checks & Inlet Protection Structures | 2011-08-16 | 2016-01-15 | ENV | No
103 | R27-103 | Green Friendly Best Management Practices (BMP) for Interstate Rest Areas - Phase 2 | 2011-01-01 | 2013-06-30 | ENV | No
104 | R27-104 | Native Vegetation Establishment for IDOT Erosion Control BMPs | 2012-01-01 | 2014-05-31 | ENV | No
105 | R27-105 | Improvement of IDOT Bridge Scour Estimation Method at Sites with Cohesive Soils Using SRICOS Zmax - Phase 2 | 2011-04-01 | 2013-03-31 | BAF | No
106 | R27-106 | Formability of New High Performance Grade 50 Structural Steel | 2011-12-01 | 2013-10-31 | BAF | No
107 | R27-108 | Improving the Effectiveness of Nighttime Temporary Traffic Control Warning Devices | 2011-09-01 | 2013-10-31 | OPS | No
108 | R27-107 | Plate & Tube Short-Span Bridges for Co Roads | 2013-07-02 | 2013-07-02 | BAF | No
109 | R27-109 | Effects of Flaggers & Spotters in Directing Work Zone Traffic for Illinois Freeways & Expressways | 2011-11-01 | 2013-10-31 | SAF | No
110 | R27-110 | Training & Implementing Findings of Queue & Users' Costs in Highway Work Zones - Phase 2 | 2012-04-16 | 2013-04-15 | SAF | No
111 | R27-111 | Effects of Intersection Right-Turn Lane Design & Skew on Safety & Operations | 2011-09-01 | 2016-06-30 | SAF | No
112 | R27-112 | Testing of Portland Cement (Current ASTM C150) with Limestone & Process Addition (ASTM C465) | 2011-05-01 | 2013-12-31 | PVMT | No
113 | R27-113 | Modeling Seniors Activity - Travel Data - Phase 2 | 2011-07-01 | 2013-08-15 | MFM | No
114 | R27-114 | Restoration Progress & Flood Disturbance at IDOT Wetland Mitigation Sites | 2011-10-01 | 2013-03-31 | ENV | No
115 | R27-115 | Analysis of Superstructures of Integral Abutment Bridges | 2012-03-01 | 2017-08-15 | BAF | No
116 | R27-116 | Investigation of Methods & Approaches for Collecting & Recording Highway Inventory Data | 2012-01-01 | 2013-06-30 | SAF | No
117 | R27-117 | National State Safety Engineers and Traffic Engineers Peer to Peer Workshop | 2012-08-01 | 2013-06-30 | SAF | No
118 | R27-118 | Development of a Highway Incident Management Operational & Training Guide - Phase 2 | 2011-08-16 | 2014-06-30 | OPS | No
119 | R27-119 | Real-Time Information Dissemination Requirements for Illinois per New Federal Rules | 2013-08-16 | 2016-02-15 | PLAN | No
120 | R27-120 | Evaluating All-Weather Pavement Markings & Lab Methods to Simulate Field Exposure | 2012-04-01 | 2019-06-30 | OPS | No
121 | R27-121 | Polymer-Modified HMA & WMA Mixtures w/ RAP & RAS (Phase 1) | 2015-03-05 | 2015-03-05 | PVMT | No
122 | R27-122 | Improvement of Driven Pile Installation and Design in Illinois: Phase 2 | 2012-07-01 | 2014-08-31 | BAF | No
123 | R27-123 | Street Lighting Technologies--LED Street Lighting Evaluation, Phase 2 | 2012-10-16 | 2015-01-15 | OPS | No
124 | R27-124 | Evaluation of Porous Granular Embankment Materials Used as Pavement Subgrade/Granular Subbase | 2012-08-16 | 2015-07-31 | PVMT | No
125 | R27-125 | Sustainable Aggregates Production -- Green Applications for Aggregate By-Products | 2013-02-01 | 2015-05-31 | PVMT | No
126 | R27-126 | Temporary Stabilization Specification Improvements | 2012-08-01 | 2014-09-30 | ENV | No
127 | R27-127 | Safety and Efficiency Benefits of Implementing Adaptive Signal Control Technology in Illinois | 2013-01-01 | 2019-06-30 | OPS | No
128 | R27-128 | Testing Protocols to Ensure Performance of High Asphalt Binder Replacement Mixes Using RAP & RAS | 2013-01-01 | 2015-12-31 | PVMT | No
129 | R27-129 | Implementation of AIMS in Measuring Aggregate Resistance to Polishing, Abrasion, Breakage | 2012-12-01 | 2014-02-28 | PVMT | No
130 | R27-130 | Development of Improved Overlay Thickness Design Alternatives for Local Roads | 2012-08-16 | 2015-07-31 | PVMT | No
131 | R27-131 | Leveraging Traffic and Surveillance Video Cameras for Urban Traffic | 2012-07-01 | 2014-12-31 | PLAN | No
132 | R27-132 | Incorporating NEPA into the IDOT and MPO Planning Process | 2012-07-01 | 2014-06-30 | PLAN | No
133 | R27-133 | Calibration and Refinement of Illinois Earthquake Resisting System Bridge Design Methodology, Phase II | 2013-10-01 | 2018-08-31 | BAF | No
134 | R27-134 | Strengthening of Bridge Wood Pilings Retrofits for Moment Resistance - Phase II | 2012-11-16 | 2016-05-15 | BAF | No
135 | R27-135 | Enhancements to the Highway Construction Expert System, Phase 2 | 2013-05-01 | 2015-05-31 | CON | No
136 | R27-136 | Development of Public Right-of Way Accessibility Guideline (PROWAG) Resource Material | 2013-10-01 | 2016-01-31 | OPS | No
137 | R27-137 | Evaluation of PCC Pavement and Structure Coring and In Situ Testing Alternatives | 2013-07-01 | 2016-12-31 | BAF | No
138 | R27-138 | Options & Recommendations for Web Data Base of Material & Construction Inspection | 2013-09-01 | 2014-04-30 | CON | No
139 | R27-139 | Bridge Decks: Mitigation of Shrinkage Cracking (Phase II) | 2013-07-01 | 2016-06-30 | PVMT | No
140 | R27-140 | Effectiveness of Exterior Beam Rotation Prevention Systems for Bridge Deck Construction | 2014-01-01 | 2016-06-30 | BAF | No
141 | R27-141 | Effective Post-Construction Best Management Practices to Infiltrate & Retain Storm Water Run-Off | 2014-02-01 | 2017-06-30 | OPS | No
142 | R27-142 | Evaluation of Software Simulation of Road Weather Information System | 2014-10-01 | 2016-09-30 | OPS | No
143 | R27-143 | Tree Establishment in Response to Hydrology at IDOT Wetland Mitigation Sites | 2013-09-01 | 2015-02-28 | ENV | No
144 | R27-144 | Development & Implementation of Updated Urban Regional Flood Frequency Equations for Illinois (Phase II) | 2013-08-01 | 2016-06-30 | BAF | No
145 | R27-145 | Modified Standard Penetration Test-based Drilled Shaft Design Method for Weak Rocks (Phase II) | 2014-01-01 | 2017-12-16 | BAF | No
146 | R27-146 | Ultrasonic Tomography for Concrete Infrastructure Condition Assessment and Quality Assurance | 2013-07-01 | 2017-04-30 | CON | No
147 | R27-147 | Chloride Reduction Training | 2014-03-17 | 2014-09-15 | OPS | No
148 | R27-148 | Development of Low-Water Crossing Design Guidelines for Very Low ADT Routes in Illinois | 2015-01-01 | 2016-12-31 | BAF | No
149 | R27-149-1 | Mechanistic-Empirical (M-E) Design Implementation & Monitoring for Flexible Pavements | 2014-07-01 | 2018-06-30 | PVMT | No
150 | R27-149-2 | Mechanistic-Empirical (M-E) Design Implementation & Monitoring for Rigid Pavements | 2014-07-01 | 2018-08-31 | PVMT | No
151 | R27-150 | Revised Condition Rating Survey models to Reflect All Distresses | 2015-01-01 | 2018-02-28 | PLAN | No
152 | R27-151 | Investigating the Optimum Performance of Reflective Pavement Markers | 2014-10-01 | 2019-11-30 | OPS | No
153 | R27-152 | Validation and Revision of Fees Charged for Oversize/Overweight Vehicle Permits | 2015-03-01 | 2017-02-28 | OPS | No
154 | R27-153 | Best Management Practices and Incentives to Expedite Utility Relocation | 2014-09-01 | 2017-07-31 | CON | No
155 | R27-154 | Effect of Early-Age Concrete Elastic Properties on Fatigue Damage in PCC Pavements Containing Fibers | 2015-01-01 | 2017-12-15 | PVMT | No
156 | R27-155 | Improving the Effectiveness of Smart Work Zone Technologies | 2014-10-15 | 2016-11-30 | SAF | No
157 | R27-156 | Repair & Strengthening of Distressed/Damaged Ends of Prestressed Beams with FRP Composites | 2014-11-01 | 2018-01-31 | BAF | No
158 | R27-157 | Plasticity Requrements of the Aggregates as Subbase, Base, Surface, and Shoulder Courses | 2015-01-01 | 2018-09-30 | PVMT | No
159 | R27-158 | Crack Induction in Cement Stabalized Layers | 2015-04-23 | 2015-04-23 | PVMT | No
160 | R27-159 | Transportation Problems - Sustainability | 2013-12-09 | 2013-12-09 | SUS | No
161 | R27-160 | Sustainability Engineering and Support | 2013-12-09 | 2017-06-30 | SUS | No
162 | R27-161 | Construction and Performance Monitoring of Various Asphalt Mixes | 2014-10-01 | 2017-12-31 | SUS | No
163 | R27-162 | Chemical and Compositional Characterization of Recycled Binders | 2015-01-01 | 2017-01-31 | PVMT | No
164 | R27-163 | Adapting Construction Staking and Inspection to Modern Technology | 2015-08-16 | 2017-08-15 | CON | No
165 | R27-164 | Design of Living Barriers to Reduce the Impacts of Snow Drifts on Illinois Freeways | 2015-11-01 | 2020-12-15 | OPS | No
166 | R27-165 | Determining Whether a Deck with a Microsilica or Latex Concrete Overlay in Place Can Be Overlaid | 2016-01-01 | 2016-02-08 | BAF | No
167 | R27-166 | Effectiveness of Waterproofing Systems for Bituminous Overlays on Bridge Decks | 2015-06-29 | 2015-06-29 | BAF | No
168 | R27-167 | Establishing Procedures and Guidelines for Pedestrian Treatments at Uncontrolled Locations | 2015-08-16 | 2017-08-15 | SAF | No
169 | R27-168 | Field Performance Evaluations of Sustainable Aggregate By-Product Applications (Phase II) | 2015-09-01 | 2018-09-30 | PVMT | No
170 | R27-169 | Opportunistic Traffic Sensing Using Existing Video Sources II (Phase II) | 2015-05-16 | 2018-08-15 | PLAN | No
171 | R27-170 | Pavement Rehabilitation Strategy Course Development | 2016-01-01 | 2019-03-31 | PVMT | No
172 | R27-171 | Refinement of load factors for Illinois-specific LRFR bridge load rating using WIM data | 2015-12-01 | 2019-02-28 | BAF | No
173 | R27-172 | Roadway Lighting's Impact on Altering Soybean Growth | 2016-01-01 | 2018-06-30 | ENV | No
174 | R27-173 | Thermodynamics of HMA Plant Production with ABR Mixes | 2014-11-01 | 2014-11-01 | PVMT | No
175 | R27-174 | Methodology for Evaluation of Seal Coat, Gravel, and Dirt Roads | 2016-01-01 | 2019-06-30 | PVMT | No
176 | R27-175 | Development of Long-Term Aging Protocol for Implementation of the Illinois Flexibility Index Test (I-FIT) | 2017-01-01 | 2019-08-31 | PVMT | No
177 | R27-176 | Alternative Noise Barriers | 2017-09-01 | 2018-11-30 | ENV | No
178 | R27-177 | Dynamic Travel Time Estimation for Northeast Illinois Expressways | 2017-09-01 | 2020-06-30 | PLAN | No
179 | R27-178-1 | Bridge Decks: Mitigation of Shrinkage Cracking Phase III | 2017-09-15 | 2020-12-15 | BAF | No
180 | R27-178-2 | Bridge Decks: Mitigation of Shrinkage Cracking Phase III | 2017-09-15 | 2020-12-15 | BAF | No
181 | R27-179 | Effectiveness of Exterior Beam Rotation Prevention Systems for Bridge Deck Construction - Phase II | 2017-09-15 | 2019-09-15 | CON | No
182 | R27-180 | Concrete Pavement Mixtures with High Supplementary Cementious Materials (SCM) Content | 2017-10-01 | 2021-09-30 | PVMT | No
183 | R27-181 | Updated and Unified StreamStats Peak Discharges for Streams of Illinois | 2017-10-01 | 2023-12-31 | BAF | No
184 | R27-182 | Size & Shape Determination of Rip Rap and Large-sized Aggregates using Field Imaging | 2018-01-01 | 2020-06-30 | PVMT | No
185 | R27-183-HS | Evaluation of On-Site and In-situ Treatment Alternatives for Contaminated Soils | 2018-02-01 | 2021-06-30 | ENV | No
186 | R27-184 | Evaluating the Beneficial Effects of Winter Maintenance Best Practices on Water Quality | 2017-10-31 | 2017-10-31 | OPS | No
187 | R27-185 | Evaluation of the HMA Resurfacing Policy for State Maintained Highways Other than Interstates | 2017-11-17 | 2017-11-17 | PVMT | No
188 | R27-186 | Correlation Between Work Zone Exposure and Work-Zone Related Fatal and A-Injury Crashes | 2018-02-01 | 2020-01-31 | SAF | No
189 | R27-187 | Pavement Surface Treatments for Ice-Prone Locations in the Illinois Highway System | 2018-02-01 | 2018-12-31 | SAF | No
190 | R27-188 | Evaluating the Accuracy and Use of Drilled Shaft Integrity Testing Methods in Illinois | 2018-02-01 | 2022-11-30 | BAF | No
191 | R27-189 | Evaluation of Data Trends and Variability in the Quality for Performance (QCP) and Pay for Performance (PFP) Programs | 2018-01-01 | 2020-06-30 | PVMT | No
192 | R27-190 | Evaluation of Various Products for Perimeter Barrier | 2018-05-16 | 2021-05-15 | ENV | No
193 | R27-191 | Evaluating the Costs & Benefits of Snow Fences in Illinois | 2018-08-16 | 2021-02-15 | OPS | No
194 | R27-192 | Maritime Freight Data Collection System & Database to Support Performance Measures & Market Analyses | 2018-05-16 | 2020-12-15 | PLAN | No
195 | R27-193-1 | Flexible Pavement Recycling Techniques | 2018-07-16 | 2021-07-15 | PVMT | No
196 | R27-193-2 | Flexible Pavement Design (Full-Depth and Rubblization) | 2018-07-16 | 2021-07-15 | PVMT | No
197 | R27-193-3 | Evaluation of Geosynthetics Use in Pavement Foundation Layers & Their Effects on Design Methods | 2018-08-16 | 2021-08-15 | PVMT | No
198 | R27-193-4 | Premature Cracking Mechanisms for Jointed Plain Concrete Pavement (JPCP) | 2018-08-16 | 2021-01-15 | PVMT | No
199 | R27-193-5 | Review of Improved Subgrade and Stabilized Subbases to Evaluate Performance of Concrete | 2019-06-16 | 2021-06-15 | PVMT | No
200 | R27-193-6 | Performance Evaluation of Stabilized Support Layers for Concrete Pavements | 2019-10-16 | 2022-02-28 | PVMT | No
201 | R27-194 | Evaluation of Spatial and Temporal Load Distribution in Steel Bridge Superstructures | 2018-07-01 | 2026-06-30 | BAF | Yes
202 | R27-195 | Best Practice Operation of Reversible Express Lanes for Kennedy Expressway | 2018-10-16 | 2021-10-31 | OPS | No
203 | R27-196-HS | Rheology-Chemical Based Procedure to Evaluate Additives/Modfiers used in Asphalt Binders for Performance Enhancements (Phase 2) | 2018-07-01 | 2021-06-30 | PVMT | No
204 | R27-197 | Characterization of the Bond Strength of Textured Epoxy-Coated (TEC) Reinforcement Bars (Phase 2) | 2018-07-16 | 2022-01-15 | BAF | No
205 | R27-198 | Development of Guidelines for Implementation of Horizontal Directional Drilling | 2018-07-16 | 2021-09-15 | BAF | No
206 | R27-199 | Optimizing the Benefits of Smoother Roads against the Increased Costs to Build Them | 2018-08-16 | 2020-10-15 | CON | No
207 | R27-200 | Construction of Pedestrian Infrastructure Along Transit Corridors | 2018-08-16 | 2021-03-15 | MFM | No
208 | R27-201 | Motor Vehicle Crashes Among Older Population | 2018-08-16 | 2020-10-15 | SAF | No
209 | R27-202 | Roadway Lighting's Effect on Pedestrian Safety at Intersection and Midblock Crosswalks | 2018-09-16 | 2021-09-15 | SAF | No
210 | R27-203 | Truck Platooning on Illinois Pavements | 2019-06-01 | 2021-05-31 | PVMT | No
211 | R27-204 | Optimized Hot-Mix Asphalt (HMA) Lift Configurations for Performance | 2019-08-16 | 2023-05-31 | PVMT | No
212 | R27-205 | Development of Bridge Load Testing Program for Load Rating of Concrete Bridges | 2019-07-16 | 2024-12-15 | BAF | No
213 | R27-206 | Evaluation of Roadway High Mast Tower Lighting | 2019-08-16 | 2023-10-31 | SAF | No
214 | R27-207 | Technical and Financial Feasibility Study for Installation of Solar Panels at IDOT Owned Facilities | 2019-08-16 | 2021-08-15 | PLAN | No
215 | R27-208 | Measuring Transport Properties of Portland Cement Concrete Using Electrical Resistivity | 2019-08-16 | 2023-08-15 | PVMT | No
216 | R27-209 | Report Tracking of Public Maintenance Needs/Requests | 2019-05-16 | 2019-05-16 | OPS | No
217 | R27-210 | Cone Penetration Testing (CPT) for Illinois Subsurface Characterization and Geotechnical Design | 2019-08-16 | 2024-05-31 | BAF | No
218 | R27-211 | Policy and Design Guidelines to Plan for Connected and Autonomous Vehicles (CAVs) | 2019-08-16 | 2022-08-15 | PLAN | No
219 | R27-212 | Beneficial Use of Dredged Material from the Illinois Marine Transportation System | 2019-09-01 | 2022-11-30 | PLAN | No
220 | R27-213 | Reducing Concrete Cure Times Based on a Quantitative Assessment of Resistivity and Porosity | 2020-08-16 | 2023-09-30 | CON | No
221 | R27-214 | 3D Image Analysis Using Deep Learning for Size and Shape Characterization of Stockpile Riprap Aggregates - Phase 2 | 2020-07-01 | 2023-06-30 | PVMT | No
222 | R27-215 | Analyzing the Impacts of a Successful Diffusion of Shared E-Scooters and Other Micromobility Devices and Efficient Management Strategies for Successful Operations in Illinois | 2020-05-16 | 2022-05-15 | MFM | No
223 | R27-216 | Optimizing the Use of Local Aggregates in Stone-Matrix Asphalt (SMA) | 2020-08-16 | 2026-04-30 | PVMT | Yes
224 | R27-217 | Taxation of Ridesharing | 2020-08-16 | 2021-12-15 | MFM | No
225 | R27-218 | Railroad-Highway Crossing (RHC) Safety Improvement Evaluation and Prioritization Tool | 2020-05-16 | 2023-06-30 | SAF | No
226 | R27-219 | Influence of Field-Curing Conditions on Strength of Concrete Test Specimens | 2020-08-16 | 2023-11-15 | CON | No
227 | R27-220 | Developing Scour-Depth Estimation Using the In Situ and Portable Scour Testing Devices (ISTD and PSTD) for Illinois Cohesive Soils | 2020-10-01 | 2026-10-31 | BAF | Yes
228 | R27-221 | Chip-Seal Quality Assurance Using Percent Embedment | 2020-08-16 | 2023-12-31 | PVMT | No
229 | R27-222 | Evaluating IDOT's Community Impact Assessment Manual to Determine Socioeconomic Impacts of Projects | 2020-08-16 | 2022-08-15 | ENV | No
230 | R27-223 | Crash Modification Factors (CMFs) for Contrast Pavement Markings on Light-Colored Pavements | 2020-08-16 | 2022-08-15 | OPS | No
231 | R27-224 | Developing an Effective Crack-Sealing Procedure by Leveraging Chemistry and Computer Vision | 2020-08-16 | 2022-06-30 | PVMT | No
232 | R27-225 | Strength and Serviceability of Damaged Steel Girders | 2020-10-01 | 2026-06-30 | BAF | Yes
233 | R27-226 | Residual Capacity of Precast Prestressed Concrete (PPC) Deck Beams with Transverse Cracks | 2020-08-16 | 2025-05-15 | BAF | No
234 | R27-227 | Moisture Content and In-Place Density of Cold Recycle Treatments | 2020-05-16 | 2022-05-15 | PVMT | No
235 | R27-228 | Illinois, a Leader in Mobility 4.0 and Beyond | 2021-04-16 | 2023-06-15 | PLAN | No
236 | R27-229 | Evaluation of Net-free Erosion Control Blankets | 2021-05-16 | 2023-12-15 | ENV | Yes
237 | R27-230 | Performance and Design of Continuously Reinforced Concrete Pavements (CRCP) | 2021-05-16 | 2024-05-31 | PVMT | No
238 | R27-231 | Evaluation of the Asphalt Mixture Design Framework for Airfield Pavements in Illinois | 2021-08-16 | 2023-08-15 | PVMT | No
239 | R27-232 | Utilizing a Particle Packing Approach for an Illinois-specific, Nonproprietary, Low-Shrinkage UHPC | 2021-07-01 | 2024-09-30 | BAF | No
240 | R27-233 | Mechanistic-Empirical Design Procedures for Flexible Pavements | 2021-05-16 | 2024-05-15 | PVMT | No
241 | R27-234 | Effectiveness of Geosynthetics in Soil/Aggregate Stabilization - Evaluation using Bender Element Sensor Technology | 2021-10-01 | 2025-06-30 | PVMT | No
242 | R27-235 | Thickness Design for Cement-Treated Base Pavements | 2021-07-01 | 2024-06-30 | PVMT | No
243 | R27-236 | Electric Vehicle Infrastructure Plan in Illinois | 2021-07-01 | 2022-12-31 | PLAN | Yes
244 | R27-238 | Developing Deterioration Curves for Bridge Elements | 2021-08-01 | 2024-02-29 | BAF | No
245 | R27-237 | 48-Volt Cabinets | 2021-07-09 | 2021-07-09 | OPS | No
246 | R27-239 | Development of Commercial Vehicle Emission Inventory and Analysis | 2021-08-16 | 2024-02-15 | PLAN | No
247 | R27-240 | Development of Potential Strategies for Unmarked and Low Traffic Volume Roadways in Illinois | 2021-09-01 | 2023-08-31 | OPS | No
248 | R27-241 | Air Mobility in Illinois | 2021-09-01 | 2024-02-29 | PLAN | No
249 | R27-242 | Economical Impact of Full Closure for Accelerated Bridge Construction and Conventional Staged Construction | 2021-08-16 | 2023-08-15 | BAF | No
250 | R27-243 | Pavement Friction | 2021-10-06 | 2021-10-06 | PVMT | No
251 | R27-244 | Improved Geotechnical Site Characterization Using Measurement While Drilling | 2021-08-16 | 2027-03-31 | BAF | Yes
252 | R27-245-HS | Quantification of the Effectiveness and External Noise of Rumble Strip Designs | 2021-11-01 | 2024-11-30 | SAF | No
253 | R27-246 | Development of Design Guidance for Smart Work Zone Systems | 2022-01-01 | 2024-01-31 | SAF | No
254 | R27-247 | Automated and Contactless Identification of Asphalt Pavement Surface Friction Based on Computer Vision Image-based 3D Reconstruction and Machine Learning Techniques | 2022-07-01 | 2026-09-30 | PVMT | Yes
255 | R27-248 | Investigation of Dolomite Aggregate Long-Term Cementation and Its Potential Advantage for Building Roads | 2022-07-01 | 2025-12-31 | PVMT | No
256 | R27-249 | Evaluating the Benefits of Implementing Mobile Road Weather Information Sensors (Phase II) | 2022-07-01 | 2026-06-30 | OPS | Yes
257 | R27-250 | Using Advanced Binder Rheological Parameters to Predict Cracking Potential of Hot-Mix Asphalt Mixtures with Modified Binders | 2022-08-16 | 2025-10-31 | PVMT | No
258 | R27-251 | Optimum Traffic Signal Condition Assessment and Strategic Maintenance Planning | 2022-08-16 | 2024-08-15 | OPS | No
259 | R27-252 | Impact of Commercial Electric Vehicles on Flexible Pavement Performance | 2022-08-16 | 2025-05-15 | PVMT | No
260 | R27-253 | Bicycle Detection | 2022-09-14 | 2021-09-14 | MFM | No
261 | R27-254 | Equipment Rental Schedule for Illinois | 2022-08-16 | 2026-01-15 | CON | No
262 | R27-255 | Illinois Department of Transportation's Seeding Standards and Best Management Practices | 2022-08-16 | 2025-06-15 | ENV | No
263 | R27-256 | Work Zone Queue Analysis Training Classes | 2022-04-16 | 2023-11-30 | SAF | No
264 | R27-257 | Seismic Damping Effects on Bridges | 2024-01-01 | 2026-10-31 | BAF | No
265 | R27-258 | Evaluation of Digital Alert Systems Associated to Emergency Response Vehicles and Compliance with Move Over Law | 2023-03-01 | 2026-02-28 | SAF | No
266 | R27-259 | State Department of Transportation Support for Operationalizing Transit Signal Priority | 2023-07-01 | 2025-06-30 | MFM | No
267 | R27-260 | Characterization of the Long-term Behavior of Textured Epoxy Coated Rebars in Bridge Decks | 2023-08-16 | 2026-12-15 | BAF | Yes
268 | R27-261 | Urban Mobility | 2022-12-13 | 2023-10-26 | MFM | No
269 | R27-262 | Developing a Framework for Establishing a Risk-Based Geotechnical Asset Management Program in Illinois | 2023-08-16 | 2026-08-15 | PVMT | Yes
270 | R27-263 | Advancements in Profiler Certification | 2024-08-01 | 2026-07-31 | PVMT | Yes
271 | R27-264 | Development of a Pavement Friction Management Program | 2023-09-01 | 2026-05-31 | PVMT | Yes
272 | R27-265 | Experimental and Numerical Investigation of Integral Abutment Bridges: Single and Group Pile Behavior | 2024-01-01 | 2026-12-31 | BAF | Yes
273 | R27-266 | Pavement Electromagnetic Energy Harvesting System from Highway-Speed Vehicles | 2024-05-16 | 2026-12-15 | PVMT | Yes
274 | R27-267 | Illinois Flexible Pavement Design and Monitoring | 2024-07-01 | 2027-06-30 | PVMT | Yes
275 | R27-268 | Quarry By-product Fines for Otta Seal Surfacing of Local Roads | 2024-08-16 | 2026-08-15 | PVMT | Yes
276 | R27-269 | Estimation of the Load Rating of Existing Highway Bridges Based on Bridge Weigh-in-Motion Data | 2024-08-16 | 2027-08-15 | BAF | Yes
277 | R27-270 | Field Assessment of Traffic Control Devices | 2024-08-16 | 2026-12-31 | CON | Yes
278 | R27-271 | Development of a Project-Scale Air Quality Screening Tool | 2024-08-16 | 2027-02-15 | ENV | Yes
279 | R27-272 | Identifying and Minimizing Illinois’ Transit Deserts and Gray Areas | 2024-08-16 | 2027-08-15 | MFM | Yes
280 | R27-273 | ITAG (Illinois TrAnsit GHG): a User-Friendly Tool to Estimate and Compare Greenhouse Gas Emissions from Transit Operations in Illinois | 2024-08-16 | 2027-08-15 | PLAN | Yes
281 | R27-274 | Mobility and Funding Assessment for the Expansion of Free and Reduced Fares | 2024-08-16 | 2026-12-31 | PLAN | Yes
282 | R27-275 | Seismic Ground Motions for IDOT Geotechnical Assets | 2025-08-16 | 2028-08-15 | BAF | Yes
283 | R27-276 | Investigation of Alternative Solvents for Asphalt Extraction and Recovery | 2024-10-01 | 2026-09-30 | PVMT | Yes
284 | R27-277 | Update of Traffic Factor Equations for IDOT Mechanistic-Empirical Pavement Designs | 2025-01-01 | 2027-06-30 | PVMT | No
285 | R27-278 | Requirements of Aggregate Materials as Subbase, Base, Surface, and Shoulder Courses | 2025-08-16 | 2028-08-15 | PVMT | Yes
286 | R27-279 | Advancing Self-explaining streets Phase 2: Evaluating the use of Roadway design elements and target speeds to reduce operating speed | 2025-07-01 | 2027-06-30 | SAF | Yes
287 | R27-280 | Economic, Environmental, and Equity Outcomes Assessment of the Electric Vehicle Charging Network Expansion in Illinois | 2025-07-01 | 2028-06-30 | PLAN | Yes
288 | R27-281 | IL-Pave: Development of an Integrated Tool to Optimize Pavement Energy and Cost | 2025-08-16 | 2028-08-15 | PVMT | Yes
289 | R27-282 | Effectiveness of Wearable Safety Lights for Nighttime Workers | 2025-08-16 | 2027-08-15 | SAF | Yes
290 | R27-283 | Turn-on-Red Prohibitions for Dual Right-Turn Lanes | 2025-08-16 | 2027-02-15 | OPS | Yes
291 | R27-284 | Utilizing Performance Measures for Metropolitan Planning Organizations | 2025-08-16 | 2027-08-15 | PLAN | Yes
292 | R27-285 | Replacing the Illinois Traffic Projection Tool | 2025-08-16 | 2027-08-15 | PLAN | Yes
293 | R27-286 | Laws, Ordinances, and Practices Related to AllTerrain Vehicles and Utility Task Vehicles | 2025-08-16 | 2027-02-15 | SAF | Yes
294 | R27-287 | Facilitating Scalability and Field Implementation of Illinois-Specific Non-Proprietary UHPC Mixes | 2025-08-16 | 2028-08-15 | BAF | Yes
295 | R27-288 | Modernization and Web-Based Implementation of the Illinois Pavement Feedback System | 2026-03-01 | 2028-02-29 | PVMT | Yes
296 | R27-289 | Effects of Target Air Voids on Hot Mix Asphalt (HMA) Performance Tests | 2026-05-01 | 2029-04-30 | PVMT | No
297 | R27-SP01 | Median Cable Scanning Tour (Special Project) | 2005-08-22 | 2006-01-31 | SAF | No
298 | R27-SP02 | Chicago Bridge Columns (Special Project) | 2006-01-01 | 2008-06-30 | BAF | No
299 | R27-SP03 | Profile Equipment Verification FY06 (Special Project) | 2006-04-17 | 2006-06-30 | PVMT | No
300 | R27-SP04 | Highway Maintenance Manpower Needs Study (Special Project) | 2007-01-01 | 2007-06-30 | OPS | No
301 | R27-SP05 | Profile Equipment Verification FY07 (Special Project) | 2007-04-01 | 2007-06-30 | PVMT | No
302 | R27-SP06 | 2008 RILEM Conference on Cracking in Pavement (Special Project) | 2006-07-01 | 2008-06-30 | PVMT | No
303 | R27-SP07 | Non-Destructive Evaluation of Reinforced Concrete Structures (Special Project) | 2007-09-12 | 2008-06-30 | PVMT | No
304 | R27-SP08 | Wireless Internet Service on Trains (Special Project) | 2007-10-01 | 2007-12-31 | MFM | No
305 | R27-SP09 | Profile Equipment Verification (Special Project) | 2008-02-16 | 2008-06-30 | PVMT | No
306 | R27-SP10 | Online Training Course Prototype (Special Project) | 2008-04-15 | 2008-06-30 | OPS | No
307 | R27-SP11 | Analysis of I-57 Recycled CRCP Cores (Special Project) | 2008-07-01 | 2008-09-30 | PVMT | No
308 | R27-SP12 | DeKalb County Bridge Collapse Investigation (Special Project) | 2008-09-10 | 2009-05-15 | BAF | No
309 | R27-SP13 | Profile Equipment Verification 2009 (Special Project) | 2009-04-01 | 2010-06-30 | PVMT | No
310 | R27-SP14 | Texas-AASHTO Retroreflective Sign Sheeting Specifications (Special Project) | 2009-05-01 | 2009-09-30 | PVMT | No
311 | R27-SP15 | Snowplow Simulator Training Study (Special Project) | 2009-11-01 | 2010-09-30 | OPS | No
312 | R27-SP16 | Evaluation of Horizontal Directional Drilling (HDD) (Special Project) | 2009-07-16 | 2010-08-15 | Other / Department Wide | No
313 | R27-SP17 | Warm Mix Asphalt Study (Special Project) | 2009-07-16 | 2010-07-31 | PVMT | No
314 | R27-SP18 | Developing Best Practices (BPs) for Bicycle Trail Construction & Maintenance in Illinois (Special Project) | 2011-08-16 | 2012-06-30 | ENV | No
315 | R27-SP19 | Evaluation of the Effect of RAS on IDOT Asphalt Mixtures (Special Project) | 2011-12-16 | 2012-06-15 | PVMT | No
316 | R27-SP20 | Safety Benefits of Implementing Adaptive Signal Control Technologies (ASCT) (Special Project) | 2012-04-16 | 2012-12-15 | OPS | No
317 | R27-SP21 | Illinois Carbon Monoxide Screen for Intersection Modeling (COSIM) 2012 Update (Special Project) | 2012-06-01 | 2013-04-30 | ENV | No
318 | R27-SP22 | Impact of HPMS Sample Counting for 24 Hours Versus 48 Hours (Special Project) | 2013-03-01 | 2014-04-30 | PLAN | No
319 | R27-SP23 | Illinois Drainage Laws Update (Special Project) | 2013-09-16 | 2014-07-31 | Other / Department Wide | No
320 | R27-SP24 | TrafficTurk Evaluation (Special Project) | 2013-08-16 | 2014-02-15 | SAF | No
321 | R27-SP25 | Data Analysis for Local Roadway Safety Assessments (Special Project) | 2013-11-01 | 2014-04-30 | SAF | No
322 | R27-SP26-C | Evaluation of Agricultural-Based Alternative Deicers (Confidential Special Project) | 2014-03-01 | 2014-11-30 | OPS | No
323 | R27-SP27 | AIMS Implementation - Investigation of Relationships between AIMS Shape Properties and VST Friction Values (Special Project) | 2014-06-01 | 2015-02-28 | PVMT | No
324 | R27-SP28 | Evaluation of PG graded Asphalts with Low-level of ReOB (Special Project) | 2014-10-01 | 2016-02-15 | SUS | No
325 | R27-SP29 | Thermodynamics between RAP/RAS and Virgin Aggregates during Asphalt Concrete Production - A Literature Review | 2015-01-01 | 2015-10-31 | PVMT | No
326 | R27-SP30 | Speed Harmonization - Design Speed vs. Operating Speed (Special Project) | 2015-09-16 | 2016-10-15 | SAF | No
327 | R27-SP31 | Evaluation of I-FIT Results and Machine Variability using MnRoad Test Track Mixtures | 2016-08-16 | 2017-06-30 | PVMT | No
328 | R27-SP32 | Crash-Based Evaluation of Red Light Running Cameras in Illinois | 2016-08-16 | 2017-04-15 | SAF | No
329 | R27-SP33 | Spillover Effects and Economic Analysis of Red Light Running Cameras in Illinois | 2016-08-16 | 2017-04-15 | SAF | No
330 | R27-SP34 | Evaluation of Various Tack Coat Materials Using Interface Shear Device and Recommendations on a Simplified Device | 2017-05-01 | 2017-12-31 | PVMT | No
331 | R27-SP35 | Behavior of Epoxy Coated Textured Reinforcement Bars | 2017-05-15 | 2018-04-30 | PVMT | No
332 | R27-SP36 | Modified Micro-Deval Procedure for Polishing of Fine Asphalt Mix Aggregates | 2017-09-01 | 2018-05-31 | PVMT | No
333 | R27-SP37-C | Effects of Higher Speed Limit on Accidents, Injuries, and Fatalities | 2017-09-15 | 2018-08-31 | SAF | No
334 | R27-SP38 | Durability Aspects of Stabilized Quarry By-product Pavement Applications | 2019-02-01 | 2019-10-31 | PVMT | No
335 | R27-SP39 | Current policies throughout the Nation for Pedestrian Hybrid Beacons (PHB) Installation | 2019-03-16 | 2019-09-15 | SAF | No
336 | R27-SP40 | Literature Review on Distracted Driving in Illinois | 2019-04-01 | 2020-04-30 | SAF | No
337 | R27-SP41 | Small Cell Installation in Transportation Infrastructure - A Literature Review | 2019-09-01 | 2020-01-31 | OPS | No
338 | R27-SP42 | Destructive Testing of IDOT Structure Number 020-3087 | 2019-11-16 | 2020-08-15 | BAF | No
339 | R27-SP43 | Aggregate Subgrade Improvements Using Quarry By-Products: A Field Investigation | 2020-05-16 | 2021-06-30 | PVMT | No
340 | R27-SP44 | HMA Pothole Maintenance Best Practices | 2020-05-01 | 2021-02-28 | OPS | No
341 | R27-SP45 | Quantifying Impacts of Prolonged Events on Transit System Ridership | 2020-11-16 | 2021-09-15 | MFM | No
342 | R27-SP46 | Bridge Deterioration and Preservation Model Refinement / Development | 2021-01-01 | 2021-09-30 | PLAN | No
343 | R27-SP47 | Evaluating the Benefits of Implementing Mobile Road Weather Information Sensors | 2021-04-16 | 2022-02-28 | OPS | No
344 | R27-SP48 | Longitudinal Cracking Investigation on I-72 Experimental Unbonded Concrete | 2021-05-01 | 2022-02-28 | PVMT | No
345 | R27-SP49 | Optimal Approach for Addressing Reinforcement Corrosion for Concrete Bridge Decks in Illinois | 2021-08-16 | 2022-05-16 | BAF | No
346 | R27-SP50 | Review of Methodologies to Assess Bridge Safety During and After Floods | 2021-09-01 | 2022-05-31 | BAF | No
347 | R27-SP51-HS | Effectiveness and External Noise of Transverse Rumble Strip Designs | 2021-09-01 | 2022-06-30 | SAF | No
348 | R27-SP52 | Optimal Approach for Addressing Reinforcement Corrosion for Concrete Bridge Decks in Illinois - Phase II | 2022-05-16 | 2023-05-15 | BAF | No
349 | R27-SP53 | Statistical Analysis of COVID-19's Impact on Transit Ridership for CTA Rail, CTA Bus, PACE and METRA (Pilot Study) | 2022-05-16 | 2023-04-15 | MFM | No
350 | R27-SP54 | Brine Rates | 2023-01-11 | 2023-01-11 | OPS | No
351 | R27-SP55 | Development of Guidelines for Messages in Dynamic Messaging Signs to Improve Safety, Compliance, and Avoid Distraction | 2023-06-01 | 2024-05-31 | OPS | No
352 | R27-SP56 | Investigating the use of Reclaimed Asphalt Pavement in Pavement Preservation Treatments | 2023-05-01 | 2023-10-31 | PVMT | No
353 | R27-SP57 | Investigating Statewide Alternative Fuel Technician Needs | 2023-06-01 | 2024-06-30 | MFM | No
354 | R27-SP58 | Investigating Statewide Transit Maintenance Needs | 2023-04-01 | 2023-12-31 | MFM | No
355 | R27-SP59 | Field Performance of Unacceptable Hot Mix Asphalt Test Parameters | 2023-04-16 | 2024-05-31 | CON | No
356 | R27-SP60 | E-Ticketing | 2023-01-19 | 2023-01-19 | CON | No
357 | R27-SP61 | Illinois Department of Transportation Wetland and Stream Mitigation Needs Assessment, Phase I | 2023-05-16 | 2024-02-15 | ENV | No
358 | R27-SP62 | Concrete Bridge Deck Crack Sealing | 2023-07-01 | 2024-03-31 | BAF | No
359 | R27-SP63 | Data Analysis and Review of Multiple Stress Creep and Recovery (MSCR) vs. Performance-graded High temperature Test Results, Including Binder Elastic Behavior/Response | 2023-04-01 | 2023-12-31 | PVMT | No
360 | R27-SP64 | Environmental – Endangered Species Mitigation Needs Assessment | 2023-05-16 | 2024-02-15 | ENV | No
361 | R27-SP65 | Low-Clearance Early Warning Devices | 2023-11-01 | 2024-07-31 | OPS | No
362 | R27-SP66 | Anti-Graffiti Protection Systems | 2024-01-16 | 2024-10-15 | BAF | No
363 | R27-SP67 | Avoiding and Minimizing Impacts to Aquatic Resources through Construction Design Standards | 2024-08-16 | 2025-05-15 | ENV | No
364 | R27-SP68 | Development of Recommended Best Management Practices for IDOT Related to the Rusty Patched Bumblebee | 2024-09-01 | 2025-11-30 | ENV | No
365 | R27-SP69 | IDOT Development of Special Management Areas | 2024-10-01 | 2025-06-30 | ENV | No
366 | R27-SP70 | Understanding Wildlife Vehicle Collisions in Illinois | 2024-10-01 | 2025-06-30 | ENV | No
367 | R27-SP71 | Advancing Our Understanding of Self-enforcing Streets and the Use of Target Speeds to Improve Safety. | 2024-02-16 | 2024-12-15 | SAF | No
368 | R27-SP72 | Field and Lab Evaluation of Roller Compacted Concrete (RCC) Mixtures for Pavements | 2024-04-16 | 2025-10-31 | PVMT | No
369 | R27-SP73 | Mussel Relication | 2025-01-23 | 2025-01-23 | ENV | No
370 | R27-SP74 | Evaluation of Concrete Overlays | 2024-11-16 | 2025-09-30 | PVMT | No
371 | R27-SP75 | Development of Pavement Temperature Measurement System for ICART | 2025-06-01 | 2026-08-31 | PVMT | Yes
372 | R27-SP76 | In-Service Evaluation of Temporary Sign Support Systems Against Wind Load | 2025-06-01 | 2026-05-31 | SAF | Yes
373 | R27-SP77 | Synthesis of Capabilities, Opportunities, and Research Needs in UAS Technology for High-Precision Bridge Inspection | 2025-09-16 | 2026-09-15 | BAF | Yes
374 | R27-SP78 | Concrete Strength Sensing Using REBEL Sensors | 2025-09-01 | 2026-08-31 | PVMT | Yes
375 | R27-SP79 | IDOT, FHWA, USFWS, USACE Aquatic Species Bridge Replacement Programmatic Agreement | 2025-10-16 | 2026-07-15 | ENV | Yes
376 | R27-SP80 | Statistical Evaluation of Illinois Modified AASHTO T161 Freeze–Thaw Testing Following Laboratory Relocation | 2026-04-01 | 2026-12-31 | PVMT | No
377 | R27-SP81 | Audible Warning System on TMA and Maintenance Trucks | 2026-03-01 | 2026-11-30 | OPS | No
378 | R27-SP83 | Ladle Furnace Slag Properties When Blended with Dolomitic Underutilized Quarry Materials | 2026-03-01 | 2026-11-30 | PVMT | No
379 | R28-001 | Mechanistic-Empirical Design, Implementation & Monitoring for Flexible Pavements (Ended 6/08) | 2005-07-01 | 2008-06-30 | PVMT | No
380 | R28-002 | Binder / Mixture Testing & Analysis - Addition to R28 Mechanistic Design | 2008-01-01 | 2008-08-31 | PVMT | No
381 | R39-001 | Validation Of Extended Life HMA Pavement Design Concepts | 2002-07-01 | 2006-12-31 | PVMT | No
382 | R39-002 | Nondestructive Pavement Evaluation Using ILLI-PAVE Based Artificial Neural Network Models | 2004-08-01 | 2008-08-31 | PVMT | No
383 | R43 | Traffic Operations Lab - Signal Systems Testing | 2005-07-01 | 2008-06-30 | OPS | No
384 | R44 | Performance and Acceptance of Self-Consolidating Concrete | 2003-07-01 | 2007-09-15 | PVMT | No
385 | R53 | Concrete Distress Identification | 2005-07-01 | 2006-06-30 | PVMT | No
386 | R54 | Development of Standard for Lifting Loops in Shallow Precast Deck Beams | 2005-07-01 | 2008-09-30 | BAF | No
387 | R55 | Tack Coat Optimization For HMA Overlays | 2005-07-01 | 2008-12-31 | PVMT | No
388 | R56 | Speed Photo-Enforcement in Illinois Work Zones | 2005-07-01 | 2008-06-30 | SAF | No
389 | R57 | Evaluation and Implementation of Improved CRCP And JPCP Design | 2005-09-01 | 2008-12-31 | PVMT | No
390 | R58 | Cost-Effectiveness and Performance of Overlay Systems in IL / Reflective Crack Control | 2005-07-01 | 2008-12-31 | PVMT | No
391 | R59 | Evaluation of Pavement Damage Due to New Tire Designs | 2006-01-01 | 2008-12-31 | PVMT | No
392 | R60-ADMIN (FY25-30 IGA) | R60-ADMIN (FY25-30 IGA) | 2024-07-01 | 2030-06-30 | Other / Department Wide | Yes
393 | R27-SP# (FY06-08 IGA) | R27-SP# (FY06-08 IGA) | 2005-07-01 | 2008-06-30 | Other / Department Wide | No
394 | R27-SP# (FY09-11 IGA) | R27-SP# (FY09-11 IGA) | 2008-07-01 | 2011-06-30 | Other / Department Wide | No
395 | R60-ADMIN (FY06-08 IGA) | R60-ADMIN (FY06-08 IGA) | 2005-07-01 | 2008-06-30 | Other / Department Wide | No
396 | R60-ADMIN (FY09-11 IGA) | R60-ADMIN (FY09-11 IGA) | 2008-07-01 | 2011-06-30 | Other / Department Wide | No
397 | R60-ADMIN (FY12-17 IGA) | R60-ADMIN (FY12-17 IGA) | 2011-07-01 | 2017-06-30 | Other / Department Wide | No
398 | R60-ADMIN (FY18-24 IGA) | R60-ADMIN (FY18-24 IGA) | 2017-07-01 | 2024-06-30 | Other / Department Wide | No
399 | R27-044 (FY09-11 IGA) | Tech Transfer (FY09-11 IGA) | 2008-07-01 | 2011-06-30 | Other / Department Wide | No
400 | R27-044 (FY12-17 IGA) | Tech Transfer (FY12-17 IGA) | 2011-07-01 | 2017-06-30 | Other / Department Wide | No
401 | R27-045 (FY09-11 IGA) | IT Support (FY09-11IGA) | 2008-07-01 | 2011-06-30 | Other / Department Wide | No
402 | R27-045 (FY12-17 IGA) | IT Support (FY12-17 IGA) | 2011-07-01 | 2017-06-30 | Other / Department Wide | No
403 | R27-046 (FY09-11 IGA) | Special Projects Eng (FY09-11 IGA) | 2008-07-01 | 2011-06-30 | Other / Department Wide | No
404 | R27-046 (FY12-17 IGA) | Special Projects Eng. (FY12-17 IGA) | 2011-07-01 | 2017-06-30 | Other / Department Wide | No
405 | R27-PC (FY18-24 IGA) | RD&T Activity Management – Project Coordination (FY18-24 IGA) | 2017-07-01 | 2024-06-30 | Other / Department Wide | No
406 | R27-ET2 (FY18-24 IGA) | Editorial Support and Technology Transfer (FY18-24 IGA) | 2017-07-01 | 2024-06-30 | Other / Department Wide | No
407 | R27-RDI (FY18-24 IGA) | Research Dissemination and Implementation (FY18-24 IGA) | 2017-07-01 | 2024-06-30 | Other / Department Wide | No
408 | R27-PC (FY25-30 IGA) | RD&T Activity Management – Project Coordination (FY25-30 IGA) | 2024-07-01 | 2030-06-30 | Other / Department Wide | Yes
409 | R27-ET2 (FY25-30 IGA) | Editorial Support and Technology Transfer (FY25-30 IGA) | 2024-07-01 | 2030-06-30 | Other / Department Wide | Yes
410 | R27-RDI (FY25-30 IGA) | Research Dissemination and Implementation (FY25-30 IGA) | 2024-07-01 | 2030-06-30 | Other / Department Wide | Yes
411 | R27-ALS | Accelerated Transportation Loading Assembly Repairs and Upgrades Project | 2020-08-01 | 2024-08-31 | Other / Department Wide | Yes

## Portfolio
| Project ID | Project Title | Project Manager | TAG | Current Project Budget
0 | R27-001 | Char. IL Aggregates Subgrade/Subbase | Brian Lorbiecki | PVMT | 399101
1 | R27-002 | Lighting Glare | Nick York | SAF | 223573
2 | R27-003 | Ultra-Thin Whitetopping | Nick York | PVMT | 247685
3 | R27-004 | Radiation Detection | Nick York | OPS | 59789
4 | R27-005 | Bus-Only Shoulder Riding | Nick York | MFM | 90603
5 | R27-006 | Illinois StreamStats | Nick York | BAF | 120000
6 | R27-007 | Carbon Monoxide Screen | Nick York | ENV | 22181
7 | R27-008 | Hot Mix Asphalt | Nick York | PVMT | 22100
8 | R27-009 | Kishwaukee Bridge Monitoring | Nick York | BAF | 133849
9 | R27-010 | Mobile Source Air Toxics | Nick York | ENV | 50266
10 | R27-011 | Residual Asphalt Binder in RAP | Nick York | PVMT | 210340
11 | R27-012 | CI & FDRwAP | Brian Lorbiecki | PVMT | 150000
12 | R27-013 | Calculation/Prediction Models | Nick York | PLAN | 139874
13 | R27-014 | Commercial Vehicle Information Systems | Nick York | PLAN | 69297
14 | R27-015 | Regional Warehouse Trip Production | Nick York | MFM | 66667
15 | R27-016 | Truck Parking Facilities | Nick York | MFM | 56132
16 | R27-017 | Traffic Strategies Targeting Elderly People | Brian Lorbiecki | MFM | 82500
17 | R27-018 | Crash Data Analysis | Nick York | SAF | 165001
18 | R27-019 | Pier Scour Prediction | Brian Lorbiecki | BAF | 352167
19 | R27-020 | Safety Performance Functions | Nick York | SAF | 140000
20 | R27-021 | Alternative Intersections | Brian Lorbiecki | SAF | 57824
21 | R27-022 | Regional Data Archiving | Nick York | OPS | 150000
22 | R27-023 | HMA Overlays | Brian Lorbiecki | PLAN | 134940
23 | R27-024 | Foundation Piling Design | Nick York | BAF | 158045
24 | R27-025 | Integral Abutment Design | Brian Lorbiecki | BAF | 119780
25 | R27-026 | Brass Breakaway Couplings | Nick York | BAF | 119647
26 | R27-027 | Reclaimed Asphalt | Brian Lorbiecki | PVMT | 75000
27 | R27-028-T1 | Conference and Training Support | Nick York | Other / Department Wide | 194025
28 | R27-028-T2 | LTAP GIS Software | Brian Lorbiecki | Other / Department Wide | 75165
29 | R27-028-T3 | Bearing Capacity Conference | Nick York | PVMT | 15000
30 | R27-029 | Particulate Matter 2.5 | Nick York | ENV | 60000
31 | R27-030 | 3-D Laser Scanning for Constr. | Brian Lorbiecki | CON | 199246
32 | R27-031 | Wind Powered Electrical Systems | Nick York | OPS | 70000
33 | R27-032 | Rolling Lane Closures | Brian Lorbiecki | OPS | 103779
34 | R27-033 | Cost in Highway Work Zones | Nick York | OPS | 160000
35 | R27-034 | Benefit-Cost Program Planning | Brian Lorbiecki | PLAN | 80000
36 | R27-035 | Cost Effective Scour Sensor | Nick York | BAF | 77617
37 | R27-036 | Tendons in SCC Girders | Brian Lorbiecki | BAF | 50000
38 | R27-037 | High RAP Content on Pavement | Nick York | PVMT | 320937
39 | R27-038 | Concrete Temperatures | Nick York | PVMT | 247098
40 | R27-039 | Context Sensitive Solns Training | Brian Lorbiecki | PLAN | 50000
41 | R27-040 | Highway Shoulder Attributes | Nick York | SAF | 140000
42 | R27-041 | I-57 Recycled Concrete Pvmt. | Brian Lorbiecki | PVMT | 54000
43 | R27-042 | High Friction Surface Layer | Brian Lorbiecki | PVMT | 697405
44 | R27-043 | Utah LTAP GIS Software Conversion | Nick York | Other / Department Wide | 20000
45 | R27-044 (FY09-11 IGA) | Tech Transfer (FY09-11 IGA) | Audrey Donoho | Other / Department Wide | 455539
46 | R27-044 (FY12-17 IGA) | Tech Transfer (FY12-17 IGA) | Audrey Donoho | Other / Department Wide | 1650000
47 | R27-044-T1 | Pavement Design Course | Brian Lorbiecki | PVMT | 150000
48 | R27-045 (FY09-11 IGA) | IT Support (FY09-11 IGA) | Audrey Donoho | Other / Department Wide | 447603
49 | R27-045 (FY12-17 IGA) | IT Support (FY12-17 IGA) | Audrey Donoho | Other / Department Wide | 1002720
50 | R27-045-T1 | Laser Scanner | ICT Project Management | CON | 286102
51 | R27-046 (FY09-11 IGA) | Special Projects Eng (FY09-11 IGA) | Audrey Donoho | Other / Department Wide | 480000
52 | R27-046 (FY12-17 IGA) | Special Projects Eng (FY12-17 IGA) | Audrey Donoho | Other / Department Wide | 1600000
53 | R27-047 | Illinois Tribunal Workshop | Nick York | ENV | 0
54 | R27-048 | Travel Demand Modeling for IL MPOs | Brian Lorbiecki | PLAN | 160000
55 | R27-049 | Documentation | Nick York | CON | 200000
56 | R27-050 | Seniors' Trip Chaining Behavior | Brian Lorbiecki | MFM | 110887
57 | R27-051 | Truck Parking/Rest Facilities | Nick York | MFM | 80536
58 | R27-052 | Traffic Related WZ Crashes | Brian Lorbiecki | SAF | 209999
59 | R27-053 | Roadway Lighting Evaluation Tools | Nick York | SAF | 0
60 | R27-054 | Storm Water P. E.&S. | Nick York | ENV | 499229
61 | R27-055 | Integral Abutment Bridges | AKSHITI MODI | BAF | 362999
62 | R27-056 | Prestressed SCC Girders | Nick York | BAF | 190000
63 | R27-057 | Fibrous Additives | AKSHITI MODI | BAF | 160000
64 | R27-058 | Wireless Detection Systems Eval | Brian Lorbiecki | OPS | 219624
65 | R27-059 | Solar Powered Flashing Beacons | Nick York | OPS | 218925
66 | R27-060 | Flexible Pavements (Mechanistic) | Brian Lorbiecki | PVMT | 484158
67 | R27-061 | Rigid Pavements | AKSHITI MODI | PVMT | 488675
68 | R27-062 | Material Quality Testing & Peer Exchange | Brian Lorbiecki | PVMT | 110934
69 | R27-063 | Joints Cut Using Early-Entry Saws | Nick York | PVMT | 94574
70 | R27-064 | Incident Mgmt Operational/Training Guide | Brian Lorbiecki | OPS | 136400
71 | R27-065 | Safety Analyst Study | Nick York | SAF | 0
72 | R27-066 | IL Speed Enforcement Techniques | AKSHITI MODI | SAF | 300397
73 | R27-067 | National Safety Performance Summit | Nick York | SAF | 100000
74 | R27-068 | Midwest Air Quality Summit | Brian Lorbiecki | ENV | 45513
75 | R27-069 | Pile Load Test | AKSHITI MODI | BAF | 457091
76 | R27-070 | Earthquake Resisting System | AKSHITI MODI | BAF | 750080
77 | R27-071 | Bridge Scour Sensor - Phase 2 | Nick York | BAF | 215267
78 | R27-072 | Rolling Lane Closures - Phase II | Brian Lorbiecki | OPS | 175000
79 | R27-073 | Distance Technology Transfer | Nick York | Other / Department Wide | 300000
80 | R27-074 | Best Management Practices (BMP) for Interstate Rest Areas | Nick York | ENV | 100000
81 | R27-075 | Traffic Signs | AKSHITI MODI | OPS | 230000
82 | R27-076 | LED Roadway Lighting | Brian Lorbiecki | OPS | 302599
83 | R27-077 | Durable Pavement Markings on HMA Mixes | Nick York | PVMT | 369284
84 | R27-078 | Asphalt Binder Additives/Modifiers | Brian Lorbiecki | PVMT | 546077
85 | R27-079 | Fine-Graded Hot Mix Asphalt | Nick York | PVMT | 692716
86 | R27-080 | Fatigue Testing of Brass Breakaway Couplings | Brian Lorbiecki | BAF | 85000
87 | R27-081 | Performance of IL Aggregates | AKSHITI MODI | BAF | 335017
88 | R27-082 | Bridge Wood Pilings Retrofits | Brian Lorbiecki | BAF | 200000
89 | R27-083 | Good Movement Study in IL | AKSHITI MODI | PLAN | 159920
90 | R27-084 | Highway Networks | Nick York | PLAN | 125407
91 | R27-085 | Materials Management Training | Nick York | PVMT | 0
92 | R27-086 | Hwy Construction Scheduling with Systems Approach | Brian Lorbiecki | CON | 89113
93 | R27-087 | Pavement Management Systems | AKSHITI MODI | PLAN | 99851
94 | R27-088 | Bridge Decks (Durability) | Nick York | BAF | 334372
95 | R27-089 | Illinois Highway Safety Manual Workshop | Nick York | SAF | 153333
96 | R27-090 | Investigation Wrong-Way Driving | AKSHITI MODI | SAF | 474421
97 | R27-091 | Traffic Flow Monitoring Technologies | Brian Lorbiecki | OPS | 99938
98 | R27-092 | Engineering Software Review | Nick York | Other / Department Wide | 0
99 | R27-093 | Hot-Spot Air Quality Modeling | AKSHITI MODI | ENV | 97749
100 | R27-094 | Snow & Ice Plows | AKSHITI MODI | OPS | 338708
101 | R27-095 | RR Crossings | Nick York | OPS | 340887
102 | R27-096 | Pedestrian/Bicyclist Warning Devices | Nick York | OPS | 202658
103 | R27-097 | Yellow Arrows | Nick York | SAF | 399153
104 | R27-098 | Concrete Cylinder | Brian Lorbiecki | BAF | 230000
105 | R27-099 | Drilled Shafts | Nick York | BAF | 172500
106 | R27-100 | Tack Coat Phase 2 | Nick York | PVMT | 529445
107 | R27-101 | BS/MS Student Scholarships | Brian Lorbiecki | Other / Department Wide | 275000
108 | R27-102 | Ditch Checks & Inlet Protection Structures | AKSHITI MODI | ENV | 411244
109 | R27-103 | Interstate Rest Areas | AKSHITI MODI | ENV | 220000
110 | R27-104 | Native Vegetation | AKSHITI MODI | ENV | 192090
111 | R27-105 | Bridge Scour Estimates w/ Sricos Phjase 2 | Nick York | BAF | 204000
112 | R27-106 | High Performance Grade 50 Structural Steel | Nick York | BAF | 103500
113 | R27-107 | Short-Span Plate & Tube Bridge | Nick York | BAF | 0
114 | R27-108 | Night Traffic Warning Devices | Nick York | OPS | 240000
115 | R27-109 | Flaggers & Spotters | Nick York | SAF | 167066
116 | R27-110 | Highway Work Zones | Nick York | SAF | 85303
117 | R27-111 | Right-Turn Lane Design | Nick York | SAF | 255415
118 | R27-112 | Testing of Portland Cement | AKSHITI MODI | PVMT | 399987
119 | R27-113 | Modeling Seniors Activity | AKSHITI MODI | MFM | 125063
120 | R27-114 | Restoration Progress at IDOT | AKSHITI MODI | ENV | 81214
121 | R27-115 | Superstructures | ICT Project Management | BAF | 345571
122 | R27-116 | Highway Inventory Data | Nick York | SAF | 215000
123 | R27-117 | Engineers Peer to Peer Workshop | Nick York | SAF | 50000
124 | R27-118 | Traffic Incident Management | Nick York | OPS | 374668
125 | R27-119 | Real-Time Information Dissemination | Nick York | PLAN | 235770
126 | R27-120 | All Weather | ICT Project Management | OPS | 500614
127 | R27-121 | Polymer-Modified HMA & WMA Mixtures w/ RAP & RAS (Phase 1) | Nick York | PVMT | 0
128 | R27-122 | Driven Pile Installation | Nick York | BAF | 304792
129 | R27-123 | Street Lighting Technologies | Nick York | OPS | 282000
130 | R27-124 | Evaluation of Porous Materials | AKSHITI MODI | PVMT | 486617
131 | R27-125 | Sustainable Aggregates | AKSHITI MODI | PVMT | 220000
132 | R27-126 | Temporary Stabilization | AKSHITI MODI | ENV | 249996
133 | R27-127 | ASCT | ICT Project Management | OPS | 1019832
134 | R27-128 | Binder Replacement | Nick York | PVMT | 779997
135 | R27-129 | AIMS | Nick York | PVMT | 125000
136 | R27-130 | Overlay Thickness | Nick York | PVMT | 120000
137 | R27-131 | Urban Traffic | Nick York | PLAN | 199980
138 | R27-132 | Incorporating NEPA into the IDOT and MPO Planning Process | Nick York | PLAN | 179703
139 | R27-133 | Earthquake Resisting System | ICT Project Management | BAF | 301129
140 | R27-134 | Bridge Wood Pilings | Nick York | BAF | 350000
141 | R27-135 | Hwy Construction Mgmt 2 | AKSHITI MODI | CON | 180968
142 | R27-136 | PROWAG | AKSHITI MODI | OPS | 216665
143 | R27-137 | Evaluation of PCC | AKSHITI MODI | BAF | 287500
144 | R27-138 | Material & Construction Inspection | Nick York | CON | 80000
145 | R27-139 | Bridge Decks 2 | Nick York | PVMT | 367740
146 | R27-140 | Exterior Beam | Nick York | BAF | 300000
147 | R27-141 | Storm Water Run | Nick York | OPS | 344303
148 | R27-142 | Road Weather Information System | Nick York | OPS | 283440
149 | R27-143 | Tree Establishment | Nick York | ENV | 79843
150 | R27-144 | Urban Flood Frequency Equations | ICT Project Management | BAF | 466000
151 | R27-145 | Drill Shafts Weak Rocks | ICT Project Management | BAF | 736267
152 | R27-146 | (MIRA) Ultrasonic Imaging for Concrete Infrastructures | ICT Project Management | CON | 500000
153 | R27-147 | Chloride Reduction | ICT Project Management | OPS | 100000
154 | R27-148 | Low-Water Crossing Design for Very Low ADT | ICT Project Management | BAF | 200000
155 | R27-149-1 | M-E Design Flexible Pavements | ICT Project Management | PVMT | 275863
156 | R27-149-2 | M-E Design Rigid Pavements | ICT Project Management | PVMT | 389592
157 | R27-150 | Condition Rating Models | ICT Project Management | PLAN | 203343
158 | R27-151 | RPM | Brian Lorbiecki | OPS | 466640
159 | R27-152 | Fees Charged for Oversize/Overweight Vehicle Permits | ICT Project Management | OPS | 300001
160 | R27-153 | Utility Relocation | ICT Project Management | CON | 230000
161 | R27-154 | Early-Age Concrete | ICT Project Management | PVMT | 355313
162 | R27-155 | Smart Work Zone | ICT Project Management | SAF | 225000
163 | R27-156 | Prestressed Beams | ICT Project Management | BAF | 312165
164 | R27-157 | Plasticity Index | ICT Project Management | PVMT | 210218
165 | R27-158 | Crack Induction in Cement Stabalized Layers | Nick York | PVMT | 0
166 | R27-159 | Transportation Problems - Sustainability | Nick York | SUS | 0
167 | R27-160 | Sustainability Engineering | ICT Project Management | SUS | 1000000
168 | R27-161 | Performance Monitoring | ICT Project Management | SUS | 969729
169 | R27-162 | Chemical/BK Project | ICT Project Management | PVMT | 144345
170 | R27-163 | Staking and Inspection | ICT Project Management | CON | 226651
171 | R27-164 | Living Snow Fences | Brian Lorbiecki | OPS | 373806
172 | R27-165 | Determine whether a Deck with a Microsilica or Latex Concrete Overlay | ICT Project Management | BAF | 3524
173 | R27-166 | Effectiveness of Waterproofing Systems for Bituminous Overlays on Bridge Decks | Nick York | BAF | 0
174 | R27-167 | Pedestrian Treatments | ICT Project Management | SAF | 176109
175 | R27-168 | Sustainable Aggregates Ph. II | ICT Project Management | PVMT | 696537
176 | R27-169 | Opportunistic Traffic Sensing | ICT Project Management | PLAN | 237117
177 | R27-170 | Rehab Course | Audrey Donoho | PVMT | 527045
178 | R27-171 | Load Factors | Audrey Donoho | BAF | 353343
179 | R27-172 | Soybean | ICT Project Management | ENV | 156952
180 | R27-173 | Thermodynamics of HMA Plant Production with ABR Mixes | Nick York | PVMT | 0
181 | R27-174 | Chip, Crack & Seal | ICT Project Management | PVMT | 337953
182 | R27-175 | Long-Term Aging | ICT Project Management | PVMT | 880546
183 | R27-176 | Noise Barriers | Audrey Donoho | ENV | 115384
184 | R27-177 | Dynamic Travel Time | Audrey Donoho | PLAN | 258892
185 | R27-178-1 | Bridge Decks Phase III | Brian Lorbiecki | BAF | 200000
186 | R27-178-2 | Bridge Decks Phase III Hindi | Brian Lorbiecki | BAF | 233700
187 | R27-179 | Beam Rotation | Brian Lorbiecki | CON | 262500
188 | R27-180 | SCM | Audrey Donoho | PVMT | 750000
189 | R27-181 | StreamStats | Brian Lorbiecki | BAF | 596300
190 | R27-182 | Riprap Phase I | Audrey Donoho | PVMT | 392716
191 | R27-183-HS | Contaminated Soil | Audrey Donoho | ENV | 611898
192 | R27-184 | Evaluating the Beneficial Effects of Winter Maintenance Best Practices | Nick York | OPS | 0
193 | R27-185 | Evaluation of the HMA Resurfacing Policy for State Maintained Highways | Nick York | PVMT | 0
194 | R27-186 | Work Zone | Brian Lorbiecki | SAF | 262500
195 | R27-187 | Surface Treatments | Audrey Donoho | SAF | 209845
196 | R27-188 | Drilled Shaft | Brian Lorbiecki | BAF | 537551
197 | R27-189 | QCP/PFP | Audrey Donoho | PVMT | 572397
198 | R27-190 | Perimeter Barriers | Audrey Donoho | ENV | 299997
199 | R27-191 | Snow Fences | Brian Lorbiecki | OPS | 187500
200 | R27-192 | Maritime Freight | Audrey Donoho | PLAN | 375000
201 | R27-193-1 | CIR and FDR | Audrey Donoho | PVMT | 125220
202 | R27-193-2 | Flexible Pavements (Rubblization) | Audrey Donoho | PVMT | 125220
203 | R27-193-3 | Geosynthetics | Audrey Donoho | PVMT | 198520
204 | R27-193-4 | JCPC | Audrey Donoho | PVMT | 152047
205 | R27-193-5 | M-E Pavement Design | Audrey Donoho | PVMT | 74497
206 | R27-193-6 | Stabilized Support Layers | Audrey Donoho | PVMT | 89322
207 | R27-194 | Steel Bridges | Brian Lorbiecki | BAF | 1238597
208 | R27-195 | Reversible Lanes | Brian Lorbiecki | OPS | 260777
209 | R27-196-HS | Rheology-Chemical | Audrey Donoho | PVMT | 415873
210 | R27-197 | TEC Bars | Brian Lorbiecki | BAF | 357889
211 | R27-198 | Horizontal Directional Drilling | Brian Lorbiecki | BAF | 400000
212 | R27-199 | Smoother Roads | Audrey Donoho | CON | 237500
213 | R27-200 | Pedestrian Infrastructure | Brian Lorbiecki | MFM | 248915
214 | R27-201 | Older Population | Brian Lorbiecki | SAF | 112500
215 | R27-202 | Roadway Lighting | Brian Lorbiecki | SAF | 406080
216 | R27-203 | Truck Platooning | Audrey Donoho | PVMT | 380000
217 | R27-204 | HMA | Brian Lorbiecki | PVMT | 767785
218 | R27-205 | Bridge Load Testing | Brian Lorbiecki | BAF | 741208
219 | R27-206 | High Mast Towers | Nick York | SAF | 447766
220 | R27-207 | Solar Panels | Brian Lorbiecki | PLAN | 347500
221 | R27-208 | Resistivity | Brian Lorbiecki | PVMT | 318276
222 | R27-209 | Report Tracking of Public Maintenance Needs/Requests | Nick York | OPS | 0
223 | R27-210 | CPT for Illinois Subsurface | Brian Lorbiecki | BAF | 512500
224 | R27-211 | Policy and Design for CAV's | Brian Lorbiecki | PLAN | 215753
225 | R27-212 | Dredge Material | Brian Lorbiecki | PLAN | 179998
226 | R27-213 | Concrete Cure Times | Nick York | CON | 237856
227 | R27-214 | RipRap Phase II | Brian Lorbiecki | PVMT | 390000
228 | R27-215 | E-Scooters | Brian Lorbiecki | MFM | 200000
229 | R27-216 | SMA | Brian Lorbiecki | PVMT | 1245362
230 | R27-217 | Rideshare Taxation | Brian Lorbiecki | MFM | 160000
231 | R27-218 | Railroad-Highway Tool | Nick York | SAF | 385000
232 | R27-219 | Field Curing | Nick York | CON | 262497
233 | R27-220 | Scour Depth Estimation | Brian Lorbiecki | BAF | 963765
234 | R27-221 | Chip-Seal | Brian Lorbiecki | PVMT | 445436
235 | R27-222 | Community Impact | Audrey Donoho | ENV | 209128
236 | R27-223 | CMFs for Contrast Pavement Markings | Brian Lorbiecki | OPS | 91986
237 | R27-224 | Bridge Deck Crack-Sealing | Audrey Donoho | PVMT | 313242
238 | R27-225 | Damaged Steel Girders | Brian Lorbiecki | BAF | 931064
239 | R27-226 | PPC Deck Beams with Transverse Cracks | Brian Lorbiecki | BAF | 359704
240 | R27-227 | Cold Recycle Treatments | Audrey Donoho | PVMT | 295000
241 | R27-228 | Mobility | Nick York | PLAN | 399745
242 | R27-229 | Erosion Control Blankets | Nick York | ENV | 240000
243 | R27-230 | CRCP Performance and Design | Brian Lorbiecki | PVMT | 285000
244 | R27-231 | Airfield Pavements | Brian Lorbiecki | PVMT | 368000
245 | R27-232 | UHPC | Brian Lorbiecki | BAF | 329680
246 | R27-233 | M-E Design Procedures | Brian Lorbiecki | PVMT | 350000
247 | R27-234 | Bender Elements | Brian Lorbiecki | PVMT | 436130
248 | R27-235 | Cement-treated Base Pavements | Brian Lorbiecki | PVMT | 120000
249 | R27-236 | EV Charging | Brian Lorbiecki | PLAN | 238415
250 | R27-237 | 48-Volt Cabinets | Brian Lorbiecki | OPS | 0
251 | R27-238 | Deterioration Curves | Brian Lorbiecki | BAF | 212497
252 | R27-239 | Commercial Vehicle Emission | Nick York | PLAN | 500000
253 | R27-240 | Low Traffic Volume Roadways | Nick York | OPS | 261610
254 | R27-241 | Air Mobility | Nick York | PLAN | 462500
255 | R27-242 | Accelerated Bridge Construction | Brian Lorbiecki | BAF | 149982
256 | R27-243 | Pavement Friction | Brian Lorbiecki | PVMT | 0
257 | R27-244 | MWD | Brian Lorbiecki | BAF | 662192
258 | R27-245-HS | Rumble Strip Designs | Nick York | SAF | 662478
259 | R27-246 | Smart Work Zones | Nick York | SAF | 219912
260 | R27-247 | Surface Friction | Brian Lorbiecki | PVMT | 750000
261 | R27-248 | Dolomite Aggregate | Brian Lorbiecki | PVMT | 645974
262 | R27-249 | Mobile RWIS Phase 2 | Nick York | OPS | 836585
263 | R27-250 | Delta G | Brian Lorbiecki | PVMT | 540443
264 | R27-251 | Traffic Signals | Nick York | OPS | 198243
265 | R27-252 | Increased Torque | Brian Lorbiecki | PVMT | 418052
266 | R27-253 | Bicycle Detection | Brian Lorbiecki | MFM | 0
267 | R27-254 | Equipment Rental | Nick York | CON | 273243
268 | R27-255 | Seeding Standards | Nick York | ENV | 269953
269 | R27-256 | Work Zone Training | Nick York | SAF | 52940
270 | R27-257 | Seismic Events | Brian Lorbiecki | BAF | 281586
271 | R27-258 | Digital Alert Systems | Nick York | SAF | 444344
272 | R27-259 | Transit Signal Priority | Nick York | MFM | 321487
273 | R27-260 | TEC Rebars | Brian Lorbiecki | BAF | 1093340
274 | R27-261 | Urban Mobility | Nick York | MFM | 0
275 | R27-262 | Geotech Asset Management | Brian Lorbiecki | PVMT | 521486
276 | R27-263 | Profiler Certification | Brian Lorbiecki | PVMT | 381981
277 | R27-264 | Friction Management | Brian Lorbiecki | PVMT | 360745
278 | R27-265 | Integral Abutment Testing | Brian Lorbiecki | BAF | 540254
279 | R27-266 | Energy Harvesting | Brian Lorbiecki | PVMT | 575225
280 | R27-267 | Flexible Pavement | Brian Lorbiecki | PVMT | 400000
281 | R27-268 | Quarry By-Product Fines | Brian Lorbiecki | PVMT | 367000
282 | R27-269 | Weigh-In-Motion | Brian Lorbiecki | BAF | 500000
283 | R27-270 | Traffic Control Devices | Nick York | CON | 299817
284 | R27-271 | Air Quality Screening | Nick York | ENV | 300000
285 | R27-272 | Gray Areas | Nick York | MFM | 299771
286 | R27-273 | Emissions Transparency | Nick York | PLAN | 300000
287 | R27-274 | Free and Reduced Fares | Nick York | PLAN | 400000
288 | R27-275 | Seismic Ground Motions | Brian Lorbiecki | BAF | 799999
289 | R27-276 | TCE Alternatives | Brian Lorbiecki | PVMT | 481011
290 | R27-277 | Traffic Factor Equations | Brian Lorbiecki | PVMT | 488510
291 | R27-278 | Aggregate Materials Requirements | Brian Lorbiecki | PVMT | 970846
292 | R27-279 | SER Phase II | Nick York | SAF | 300000
293 | R27-280 | EV Charging Network | Nick York | PLAN | 280000
294 | R27-281 | IL-Pave | Brian Lorbiecki | PVMT | 960000
295 | R27-282 | Wearable Safety Lights | Nick York | SAF | 196485
296 | R27-283 | Right Turn on Red | Nick York | OPS | 171485
297 | R27-284 | MPO Performance Measures | Nick York | PLAN | 421487
298 | R27-285 | Traffic Projection Tool | Nick York | PLAN | 421485
299 | R27-286 | ATV/UTV Ordinanaces | Nick York | SAF | 199917
300 | R27-287 | UHPC Scalability and Implementation | Brian Lorbiecki | BAF | 521484
301 | R27-288 | IL Pavement Feedback System | Brian Lorbiecki | PVMT | 653944
302 | R27-289 | Air Voids | Brian Lorbiecki | PVMT | 300000
303 | R27-290 | AI for Bridge Management | Brian Lorbiecki | BAF | 220000
304 | R27-291 | CRS Calculation Models | Brian Lorbiecki | PVMT | 930000
305 | R27-292 | CRS for Pavement Treatments | Brian Lorbiecki | PVMT | 373000
306 | R27-293 | LLM-STARS | Nick York | PLAN | 400000
307 | R27-294 | Congestion Pricing | Nick York | MFM | 500000
308 | R27-295 | Mussel Movement | Nick York | ENV | 1021485
309 | R27-296 | C1157 Hydraulic Cements | Brian Lorbiecki | PVMT | 930000
310 | R27-ALS | ATLAS Repairs and Upgrades | Kristi Anderson | Other / Department Wide | 951786
311 | R27-ET2 (FY18-24 IGA) | R27-ET2 (FY18-24 IGA) | Kristi Anderson | Other / Department Wide | 1135000
312 | R27-ET2 (FY25-30 IGA) | R27-ET2 (FY25-30 IGA) | Nick York | Other / Department Wide | 1095000
313 | R27-PC (FY18-24 IGA) | R27-PC (FY18-24 IGA) | Kristi Anderson | Other / Department Wide | 2321525
314 | R27-PC (FY25-30 IGA) | R27-PC (FY25-30 IGA) | Nick York | Other / Department Wide | 2600000
315 | R27-RDI (FY18-24 IGA) | R27-RDI (FY18-24 IGA) | Kristi Anderson | Other / Department Wide | 772000
316 | R27-RDI (FY25-30 IGA) | R27-RDI (FY25-30 IGA) | Nick York | Other / Department Wide | 660000
317 | R27-SP# (FY06-08 IGA) | R27-SP# (FY06-08 IGA) | Nick York | Other / Department Wide | 225000
318 | R27-SP# (FY09-11 IGA) | R27-SP# (FY09-11 IGA) | Brian Lorbiecki | Other / Department Wide | 450000
319 | R27-SP01 | Median Cable Scanning Tour | Nick York | SAF | 9969
320 | R27-SP02 | Chicago Bridge Columns | Nick York | BAF | 24673
321 | R27-SP03 | Profile Equipment Verification FY06 | Nick York | PVMT | 5567
322 | R27-SP04 | Highway Maintenance Manpower | Nick York | OPS | 45515
323 | R27-SP05 | Profile Equipment Verification FY07 | Nick York | PVMT | 13231
324 | R27-SP06 | Cracking in Pavement | Nick York | PVMT | 20000
325 | R27-SP07 | Reinforced Concrete Structures | Nick York | PVMT | 27333
326 | R27-SP08 | Wireless Internet Service on Trains | Nick York | MFM | 63115
327 | R27-SP09 | Profile Equipment Verification 2008 | Nick York | PVMT | 21664
328 | R27-SP10 | Online Training Course Prototype | Nick York | OPS | 32167
329 | R27-SP11 | Recycled CRCP Cores | Nick York | PVMT | 13333
330 | R27-SP12 | Bridge Collapse Investigation | Brian Lorbiecki | BAF | 20280
331 | R27-SP13 | Profile Equipment Verification 2009 | Nick York | PVMT | 45000
332 | R27-SP14 | Retroreflective Sign Sheeting | Brian Lorbiecki | PVMT | 27168
333 | R27-SP15 | Snowplow Simulator Training | Nick York | OPS | 27012
334 | R27-SP16 | Horizontal Directional Drilling Eval | Brian Lorbiecki | Other / Department Wide | 19893
335 | R27-SP17 | Warm Mix Asphalt Study | Nick York | PVMT | 23408
336 | R27-SP18 | Bicycle Trail | AKSHITI MODI | ENV | 30000
337 | R27-SP19 | Effect of RAS | ICT Project Management | PVMT | 30000
338 | R27-SP20 | Signal Control Technologies | AKSHITI MODI | OPS | 30000
339 | R27-SP21 | COSIM | Nick York | ENV | 25524
340 | R27-SP22 | HPMS Sample Counting | Nick York | PLAN | 25400
341 | R27-SP23 | Drainage Laws | Nick York | Other / Department Wide | 30000
342 | R27-SP24 | TrafficTurk Evaluation | Nick York | SAF | 30000
343 | R27-SP25 | Local Roadway Safety Assessments | Nick York | SAF | 30000
344 | R27-SP26-C | Alternative Deicers | Nick York | OPS | 30000
345 | R27-SP27 | AIMS Implementation | AKSHITI MODI | PVMT | 30000
346 | R27-SP28 | PG Asphalts ReOB | AKSHITI MODI | SUS | 30000
347 | R27-SP29 | Thermodynamics | AKSHITI MODI | PVMT | 30000
348 | R27-SP30 | Speed Harmonization | AKSHITI MODI | SAF | 30000
349 | R27-SP31 | Evaluation of I-FIT Results | AKSHITI MODI | PVMT | 30000
350 | R27-SP32 | Red Light Running Cameras | AKSHITI MODI | SAF | 30000
351 | R27-SP33 | Red Light Running Cameras | Nick York | SAF | 30000
352 | R27-SP34 | Shear Tack | Brian Lorbiecki | PVMT | 46029
353 | R27-SP35 | Textured Rebar | Brian Lorbiecki | PVMT | 38930
354 | R27-SP36 | AIMS-MD | Brian Lorbiecki | PVMT | 36000
355 | R27-SP37-C | Speed Limits | Brian Lorbiecki | SAF | 35987
356 | R27-SP38 | QBP Durability | Audrey Donoho | PVMT | 36000
357 | R27-SP39 | Hybrid Beacons | Brian Lorbiecki | SAF | 36000
358 | R27-SP40 | Distracted Driving | Brian Lorbiecki | SAF | 48500
359 | R27-SP41 | Small Cells | Brian Lorbiecki | OPS | 48500
360 | R27-SP42 | Bridge Beams | Brian Lorbiecki | BAF | 36000
361 | R27-SP43 | Quarry By-products | Audrey Donoho | PVMT | 36000
362 | R27-SP44 | HMA Potholes | Audrey Donoho | OPS | 36000
363 | R27-SP45 | Transit System Ridership | Brian Lorbiecki | MFM | 36000
364 | R27-SP46 | Bridge Deterioration | Brian Lorbiecki | PLAN | 48500
365 | R27-SP47 | Mobile Road Weather | Brian Lorbiecki | OPS | 35997
366 | R27-SP48 | Longitudinal Cracking | Audrey Donoho | PVMT | 36000
367 | R27-SP49 | Corrosion on Bridge Decks | Brian Lorbiecki | BAF | 48500
368 | R27-SP50 | Bridge Safety | Brian Lorbiecki | BAF | 36000
369 | R27-SP51-HS | Transverse Rumble Strips | Brian Lorbiecki | SAF | 36000
370 | R27-SP52 | Corrosion on Bridge Decks Phase II | Brian Lorbiecki | BAF | 48500
371 | R27-SP53 | Transit Ridership Analysis | Brian Lorbiecki | MFM | 36000
372 | R27-SP54 | Brine Rates | Nick York | OPS | 0
373 | R27-SP55 | Dynamic Messaging | Nick York | OPS | 36000
374 | R27-SP56 | RAP in Pavement Preservation | Brian Lorbiecki | PVMT | 36000
375 | R27-SP57 | Transit Vehicle Technician Needs | Nick York | MFM | 46814
376 | R27-SP58 | IDOT Maintenance Needs | Nick York | MFM | 36000
377 | R27-SP59 | Asphalt Replacement Credits | Nick York | CON | 36000
378 | R27-SP60 | E-Ticketing | Nick York | CON | 0
379 | R27-SP61 | Wetland Mitigation | Nick York | ENV | 36000
380 | R27-SP62 | Bridge Deck Crack Sealing | Brian Lorbiecki | BAF | 36000
381 | R27-SP63 | MSCR | Brian Lorbiecki | PVMT | 36000
382 | R27-SP64 | Endangered Species | Nick York | ENV | 36000
383 | R27-SP65 | Low-Clearance Early Warning Devices | Nick York | OPS | 36000
384 | R27-SP66 | Anti-Graffiti | Brian Lorbiecki | BAF | 83286
385 | R27-SP67 | Minimizing Impacts to Aquatic Resources | Nick York | ENV | 64977
386 | R27-SP68 | Rusty Patched Bumblebee | Nick York | ENV | 65000
387 | R27-SP69 | Specialized Management Areas | Nick York | ENV | 65000
388 | R27-SP70 | Wildlife Crossings | Nick York | ENV | 57867
389 | R27-SP71 | Target Speeds | Nick York | SAF | 65000
390 | R27-SP72 | Roller Compacted Concrete | Brian Lorbiecki | PVMT | 65000
391 | R27-SP73 | Mussel Relocation | Nick York | ENV | 0
392 | R27-SP74 | Concrete Overlays | Brian Lorbiecki | PVMT | 65000
393 | R27-SP75 | Pavement Temperature Measurement System | Brian Lorbiecki | PVMT | 65000
394 | R27-SP76 | Temporary Sign Support Systems | Nick York | SAF | 65000
395 | R27-SP77 | UAS 3D Bridge Inspection | Brian Lorbiecki | BAF | 64997
396 | R27-SP78 | Concrete Strength Sensing | Brian Lorbiecki | PVMT | 85948
397 | R27-SP79 | Aquatic Species Bridge PA | Nick York | ENV | 65000
398 | R27-SP80 | Freeze-Thaw Chambers Data | Brian Lorbiecki | PVMT | 65000
399 | R27-SP81 | Audible Warnings | Nick York | OPS | 65000
400 | R27-SP82 | Oxidation of Pavement Preservation | Brian Lorbiecki | PVMT | 65000
401 | R27-SP83 | Ladle Slag | Brian Lorbiecki | PVMT | 65000
402 | R28-001 | Flexible Pavements (Ended 6/08) | Nick York | PVMT | 126846
403 | R28-002 | Binder / Mixture Testing & Analysis | Brian Lorbiecki | PVMT | 42000
404 | R39-001 | Extended Life HMA Pavement Design | Nick York | PVMT | 170020
405 | R39-002 | Nondestructive Pavement Evaluation | Nick York | PVMT | 84818
406 | R43 | Traffic Operations Lab | Nick York | OPS | 444631
407 | R44 | Self-Consolidating Concrete | Nick York | PVMT | 190196
408 | R53 | Concrete Distress Identification | Nick York | PVMT | 78902
409 | R54 | Lifting Loops in Shallow Precast Deck Beams | Brian Lorbiecki | BAF | 278832
410 | R55 | Tack Coat Optimization | Nick York | PVMT | 694590
411 | R56 | Speed Photo-Enforcement | Nick York | SAF | 309095
412 | R57 | CRCP and JPCP Design | Brian Lorbiecki | PVMT | 301814
413 | R58 | Reflective Crack Control | Nick York | PVMT | 309589
414 | R59 | Pavement Damage | Nick York | PVMT | 293893
415 | R60-ADMIN (FY06-08 IGA) | R60-ADMIN (FY06-08 IGA) | Nick York | Other / Department Wide | 1040000
416 | R60-ADMIN (FY09-11 IGA) | R60-ADMIN (FY09-11 IGA) | Audrey Donoho | Other / Department Wide | 995000
417 | R60-ADMIN (FY12-17 IGA) | R60-ADMIN (FY12-17 IGA) | Audrey Donoho | Other / Department Wide | 2700000
418 | R60-ADMIN (FY18-24 IGA) | R60-ADMIN (FY18-24 IGA) | Kristi Anderson | Other / Department Wide | 3290000
419 | R60-ADMIN (FY25-30 IGA) | R60-ADMIN (FY25-30 IGA) | Nick York | Other / Department Wide | 3900000